## Sheet3
PIC | Schedule Kirim tgl 04/03/26 |  | Schedule Kirim tgl 03/03/26 |  | Schedule Kirim tgl 02/03/26 |  | Schedule Kirim tgl 20/02/26 |  | Schedule Kirim tgl 04/02/26 |  | Schedule Kirim tgl 02/02/26 |  | Schedule Kirim tgl 12/01/26 |  | Schedule Kirim tgl 09/01/26 |  | Schedule Kirim tgl 23/12/25
|  | Days |  | Days |  | Days |  | Days |  | Days |  | Days |  | Days |  | Days
Baim, Budi | 7 | 60 | 7 | 60 | 7 | 60 | 7 | 61 | 6 | 58 | 6 | 58 | 6 | 80 | 6 | 80 | 4
Baim | 14 | 44 | 20 | 60 | 22 | 64 | 23 | 63 | 24 | 56 | 23 | 54 | 17 | 148 | 16 | 138 | 4
Budi | 15 | 38 | 19 | 46 | 20 | 48 | 21 | 47 | 21 | 36 | 21 | 36 | 15 | 130 | 16 | 140 | 4
Star | 4 | 9 | 0 | 0 | 1 | 3
Jali | 11 | 22 | 15 | 38 | 1 | 3
Baim/Star | 0 | 0 | 2 | 4
Budi/Star | 0 | 0 | 2 | 4
Baim/Jali | 0 | 0 | 1 | 2
Baim, Budi, Jali, Star | 1 | 6
| 52 | 179 | 66 | 214 | 51 | 178 | 51 | 171 | 51 | 150 | 50 | 148 | 38 | 358 | 38 | 358 | 12
|  | 179 |  | 214 |  | 178 |  | 171 |  | 150 |  | 148 |  | 358 |  | 358
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Note on A1: Task Lead Enter the name of the Task Lead in this column.

## Memo
No | Tgl Terima Memo | Memo Dari | Kode Memo
1 | 2026-02-25 | BC | 010/SL-AAA/LJ1/0226
2 | 2026-02-25 | BC | 009/SL-OFF/LJ1/0126
3 | 2026-03-12 | BC | 015/SL-AAA/LJ1/0326

## ToDo
|  | Done | 161 |  |  |  | 2026-03-30 08:07
|  | On Progres | 0
|  | All | 163
No |  | Tgl | Kategori | Req | Task | Status | Done Date | Work Day
1 | 1 | 2026-01-26 | SAP |  | Belajar SAP (Custom Logic) | Done | 2026-01-26 08:58 | 0.37346
2 | 1 | 2026-01-27 | Tiket |  | Tiket #DV-DT224000007044 | Done | 2026-01-27 08:58 | 0.37346
3 | 1 | 2026-01-27 | Tiket |  | Tiket #DV-DT224000007053 | Done | 2026-01-27 08:58 | 0.37346
4 | 1 | 2026-01-27 | Memo |  | Revisi Memo PO 79260003 (LJM) | Done | 2026-01-27 08:58 | 0.37346
5 | 1 | 2026-01-27 | Memo |  | Revisi Memo PO 79704844 (LJU) | Done | 2026-01-27 08:58 | 0.37346
6 | 1 | 2026-01-27 | WA | Bu Atin | Ganti Material PR 399 (material Kelebihan) | Done | 2026-01-27 08:58 | 0.37346
7 | 1 | 2026-01-27 | WA | Bu Atin | PO 878 ganti purchase group | Done | 2026-01-27 08:58 | 0.37346
8 | 1 | 2026-01-27 | WA | Sandi | Upload stock Gd Packing (LJU) periode 26/01/26 | Done | 2026-01-27 08:58 | 0.37346
9 | 1 | 2026-01-27 | Telphone | Ratna | Revisi Harga PO 72600928 (LJU) | Done | 2026-01-27 08:58 | 0.37346
10 | 1 | 2026-01-27 | SAP |  | Pull template PASSAP | Done | 2026-01-27 08:58 | 0.37346
11 | 1 | 2026-01-27 | WA | Evi | Ganti satuan BBK BG-2601-00002 | Done | 2026-01-27 08:58 | 0.37346
12 | 1 | 2026-01-28 | WA | Evi | Ganti satuan SJ G-2610073 | Done | 2026-01-28 09:08 | 0.38064
13 | 1 | 2026-01-28 | SAP |  | Penambahan Modul Print Barcode Final | Done | 2026-01-29 09:01 | 1.3757
14 | 1 | 2026-01-28 | Langsung | Kevin | Cek PR 10260424, 10805832 | Done | 2026-01-28 10:42 | 0.44551
15 | 1 | 2026-01-28 | Telphone | Bagus | Menambah kolom inputan Gross Weight dan Nett Weight di modul print Invoice BC (khusus mesin) | Done | 2026-01-28 13:24 | 0.55843
16 | 1 | 2026-01-28 | Tiket |  | Tiket #DV-DT24000006841 | Done | 2026-01-28 13:34 | 0.56503
17 | 1 | 2026-01-28 | WA | Reza | Revisi harga PO 78260301 (LJK) | Done | 2026-01-28 15:14 | 0.63453
18 | 1 | 2026-01-28 | WA | Bu Yani | Cek data Report Jasa LJU bulan Agustus 2025 web dan dekstop varian | Done | 2026-01-28 16:16 | 0.67794
19 | 1 | 2026-01-28 | WA | Reza | Revisi Harga PO 72600961 (LJU) | Done | 2026-01-28 16:21 | 0.68099
20 | 1 | 2026-01-29 | WA | Bu Tati | Ganti Alamat di Invoice 055/PI/JAN/2026 (LJU) Di Forward ke pa budi | Done | 2026-01-29 09:00 | 0.37492
21 | 1 | 2026-01-29 | SAP |  | Diskusi Penarikan Data API dan data API Barcode SAP | Done | 2026-01-29 10:14 | 0.42625
22 | 1 | 2026-01-29 | WA | Bu Tati | Ganti Final Destination di Invoice 055/PI/JAN/2026 (LJU) | Done | 2026-01-29 11:08 | 0.46413
23 | 1 | 2026-01-29 | SAP |  | Create Module Master PO template (belum tarik data) | Done | 2026-01-29 13:35 | 0.56626
24 | 1 | 2026-01-30 | WA | Meris | Perbaikan Sistem Puzzle LJM (material tidak bisa ditransaksikan) | Done | 2026-01-30 09:09 | 0.38092
25 | 1 | 2026-01-30 | WA | Evi | Permintaan pembuatan SKEP : S-168/KBC.0903/2026 (LJK) | Done | 2026-01-30 09:59 | 0.41579
26 | 1 | 2026-01-30 | Langsung | Taufik | ganti pengkodean no aju BC30 per tgl 28 januari 2026 asal -014481- menjadi -LEC395- req pa taufik | Done | 2026-01-30 11:10 | 0.46502
27 | 1 | 2026-01-30 | WA | Putri | Revisi No AJU 000030-LEC395-20260127-000130 (LJU) | Done | 2026-01-30 13:32 | 0.56405
28 | 1 | 2026-01-30 | WA | Bara | ganti no aju BC 30 asal 25 karakter jadi 22 karakter, req bara | Done | 2026-01-30 13:45 | 0.573
29 | 1 | 2026-01-30 | Telphone | Visqia | Data AJU BC25 tidak muncul di menu audit pengeluaran beacukai | Done | 2026-01-30 14:31 | 0.60491
30 | 1 | 2026-01-31 | SAP |  | Mapping tabel untuk API Delivery(SJ) | Done | 2026-01-31 09:49 | 0.40917
31 | 1 | 2026-01-31 | SAP |  | Buat UI penarikan data dari API dan insert data Master Delivery | Done | 2026-02-02 16:01 | 2.6675
32 | 1 | 2026-01-31 | WA | Dini | Cek reservasi 92603964 (LJU) material tidak muncul | Done | 2026-01-31 09:48 | 0.40841
33 | 1 | 2026-01-31 | WA | Taufik | hilangkan radiobuton TPB dan otomatis ceklis Ceisa di Update Dok Export BC req pa taufik | Done | 2026-01-31 11:50 | 0.49273
34 | 1 | 2026-02-02 | Tiket |  | Tiket #DV-DT24000007117 (tunggu Memo) (diforward ke star) | Done | 2026-02-02 13:49 | 0.57549
35 | 1 | 2026-02-02 | WA | Meris | Cek Data Material LJK 4000051495 beda satuan | Done | 2026-02-02 10:11 | 0.42408
36 | 1 | 2026-02-02 | WA | Bu Apri | Cek Packing list LJK 003 (diforward ke pa budi) | Done | 2026-02-02 11:27 | 0.47677
37 | 1 | 2026-02-02 | Telphone | Bara | Doc SJ G-2600235 di pengeluaran BC kode material tidak sesuai | Done | 2026-02-02 13:26 | 0.55959
38 | 1 | 2026-02-02 | Telphone | Ledy | PO 79704844 belum ada penambahan PPN padahal sudah dibuatkan memonya | Done | 2026-02-02 14:08 | 0.58904
39 | 1 | 2026-02-02 | WA | Evi | Perbedaan Qty Kode material 1000000018 | Done | 2026-02-02 14:17 | 0.59547
40 | 1 | 2026-02-02 | WA | Dea | Stockoverview LJOI material 1000001877 | Done | 2026-02-02 14:50 | 0.61773
41 | 1 | 2026-02-02 | WA | Evi | Revisi PO 78260083 (LJK) Tambah keterangan | Done | 2026-02-02 15:01 | 0.62588
42 | 1 | 2026-02-02 | Tiket |  | Ticket #DV-DT24000007129 | Done | 2026-02-02 16:11 | 0.67441
43 | 1 | 2026-02-03 | SAP |  | Buat UI penarikan data dari API dan insert data Master Supplier | Done | 2026-02-03 10:14 | 0.42614
44 | 1 | 2026-02-03 | Tiket |  | Ticket #DV-DT24000006839 (PR.10260529 ganti LS11) | Done | 2026-02-03 09:57 | 0.41433
45 | 1 | 2026-02-03 | Tiket |  | Ticket #DV-DT24000007138 (ganti sub vendor dan nilai kontrak) | Done | 2026-02-03 11:58 | 0.49853
46 | 1 | 2026-02-03 | SAP |  | Menambah Custom Logic di Form Invoice | Done | 2026-02-04 14:28 | 1.6026 | Pending Lanjut lagi ke Form UI
47 | 1 | 2026-02-04 | SAP |  | Buat UI penarikan data dari API dan insert data Asset | Done | 2026-02-04 13:27 | 0.56039
48 | 1 | 2026-02-04 | Telphone | Bu Desi | Skep 419/TPB-SK.01/KBC.0903/2026 dan 291/TPB-SK.01/KBC.0903/2026 tidak muncul saat buat BPB | Done | 2026-02-04 11:31 | 0.48006
49 | 1 | 2026-02-04 | SAP |  | Diskusi Mapping Tabel Delivery dengan tim Soltius | Done | 2026-02-04 14:28 | 0.60263 | Batal Tim Soltius Masih Sibuk
50 | 1 | 2026-02-04 | WA | Putri | No Invoice 088/CI/FEB/2026 (LJU) Satuan Null (minta diisi jadi Meter) | Done | 2026-02-04 14:26 | 0.60168
51 | 1 | 2026-02-04 | WA | Putri | No Invoice 069/PI/FEB/2026 (LJU) data ambigu | Done | 2026-02-04 14:45 | 0.61485
52 | 1 | 2026-02-04 | SAP |  | Buat UI penarikan data dari API dan insert data PO | Done | 2026-02-05 14:23 | 1.5993
53 | 1 | 2026-02-06 | SAP |  | Buat UI penarikan data dari API dan insert data BOM | Done | 2026-02-16 11:20 | 10.4726 | Ikut KUT dan UAT
54 | 1 | 2026-02-06 | Telphone | Bara | ubah order by laporan balance skep dari asal order by no daftar, menjadi order by tgl daftar req bara | Done | 2026-02-06 14:48 | 0.6166
55 | 1 | 2026-02-06 | Telphone | Ledy | Permintaan Data Vendor beserta TOPnya (LJU, LJK, LJM) | Done | 2026-02-06 15:48 | 0.65826
56 | 1 | 2026-02-07 | SAP |  | Meeting di 234 | Done | 2026-02-07 10:29 | 0.4365
57 | 1 | 2026-02-07 | Tiket |  | #DV-DT24000007191 ganti tgl aju dan tgl daftar asal 06-02-26 jadi 05-02-26 | Done | 2026-02-07 10:41 | 0.44493
58 | 1 | 2026-02-07 | Tiket |  | #DV-DT24000007187 edit nilai kontrak dan SKEP | Done | 2026-02-07 11:10 | 0.46502
59 |  | 2026-02-09 |  |  | TIDAK MASUK SAKIT
60 | 1 | 2026-02-10 | WA | Visqia | Material 9000000458 (LJK) tidak bisa ditransaksikan | Done | 2026-02-10 10:10 | 0.42349
61 | 1 | 2026-02-10 | Telphone | Ledy | Permintaan Data Vendor terbaru dari periode PO awal 2024 sampai sekarang (LJU, LJK, LJM) | Done | 2026-02-10 15:13 | 0.63397
62 | 1 | 2026-02-10 | Tiket |  | #DV-DT24000007220 ganti no Aju dan no daftar | Done | 2026-02-10 15:31 | 0.64619
63 | 1 | 2026-02-10 | Telphone | Teti | Ubah No Invoice PL-2602-00049 (LJK) | Done | 2026-02-10 18:13 | 0.75929
64 | 1 | 2026-02-11 | WA | Sandi | Upload stock Gd Packing (LJU) periode 10/02/26 | Done | 2026-02-11 09:06 | 0.37942
65 | 1 | 2026-02-11 | WA | Sandi | Upload stock Gd Packing (LJU) periode 10/02/26 (rev1) | Done | 2026-02-11 09:46 | 0.40701
66 | 1 | 2026-02-11 | Telphone | Ledy | Permintaan Data Vendor terbaru dari periode PO awal 2024 sampai sekarang (LJU, LJK, LJM) | Done | 2026-02-12 08:43 | 1.3635
67 | 1 | 2026-02-11 | WA | Meris | Data SJ G-2600382 (LJU) Error saat di print | Done | 2026-02-11 09:36 | 0.40007
68 | 1 | 2026-02-11 | SAP |  | UAT selama 3 hari dari jam 10.00 WIB sampai jam 16.00 WIB (Hari Ke-1) | Done | 2026-02-11 16:00 | 0.66694
69 | 1 | 2026-02-12 08:49 | Langsung | Meris | Menu Puzzle Dekstop PO dicancel masih muncul di PR list
70 | 1 | 2026-02-12 09:17 | Tiket |  | #DV-DT24000007231 ganti sub vendor jadi DODO SL | Done | 2026-02-12 09:45 | 0.01944
71 | 1 | 2026-02-12 10:01 | SAP |  | UAT selama 3 hari dari jam 10.00 WIB sampai jam 16.00 WIB (Hari Ke-2) | Done | 2026-02-12 16:00 | 0.24963
72 | 1 | 2026-02-13 09:31 | SAP |  | UAT selama 3 hari dari jam 10.00 WIB sampai jam 16.00 WIB (Hari Ke-3) | Done | 2026-02-13 16:00 | 0.27028
73 |  | 2026-02-14 |  |  | TIDAK MASUK CUTI
74 | 1 | 2026-02-16 09:17 | WA | Visqia | Material 7000001564 (LJU) pak kode ini di panggil di menu IV25AC ngak muncul | Done | 2026-02-16 09:29 | 0.0082919
75 | 1 | 2026-02-16 10:12 | Telphone | Nisa | Invoice 091/PI/FEB/2026 revisi gross weight dan nett weight asal 6.8 dan 6.6 menjadi 12 dan 11.4 | Done | 2026-02-16 10:12 | 0.00025012
76 | 1 | 2026-02-16 11:29 | SAP |  | Melanjutkan no 52 (API baru bisa diakses tgl 13/02/26) | Done | 2026-02-16 13:12 | 0.072058 | Pending, API masih di cek oleh pihak Soltius
77 | 1 | 2026-02-16 11:51 | WA | Ibu Tina | Ubah packing list PL-2602-00077 (LJU) no invoice nya asal 1258/CI/FEB/2026 menjadi 128/CI/FEB/2026 | Done | 2026-02-16 11:53 | 0.0012921
78 | 1 | 2026-02-16 13:13 | SAP |  | Buat UI Report Laporan Surat Jalan (P) | Done | 2026-02-16 15:40 | 0.10204 | Data sebagian masih ambigu (belum konfirmasi dengan pihak soltius)
79 | 1 | 2026-02-16 13:45 | SAP |  | Diskusi dengan pihak soltius (Pa agung) tentang Batch Karakter intruksi pa Bily di showroom 2 jam 2 siang | Done | 2026-02-16 15:40 | 0.079857 | Batal, info dari pa agus belum ada kabar lagi dari pihak soltius
80 | 1 | 2026-02-16 16:05 | SAP |  | Diskusi dengan pihak soltius (Pa agung) tentang Batch Karakter intruksi pa Bily | Done | 2026-02-16 17:28 | 0.05737
81 | 1 | 2026-02-18 08:23 | SAP |  | Melanjutkan no 43 | Done | 2026-02-20 14:16 | 2.2447 | Pending Ada UAT poin 82
82 | 1 | 2026-02-18 09:23 | SAP |  | UAT di gedung meting BC jam 10.00 WIB | Done | 2026-02-18 16:31 | 0.29731
83 | 1 | 2026-02-18 09:41 | WA | Meris | Reservasi 91261046 (LJK) material tidak muncul seluruhnya | Done | 2026-02-18 09:52 | 0.0082428
84 | 1 | 2026-02-18 13:16 | WA | Evi | Material 3000000113 (LJK) tidak muncul di BBK | Done | 2026-02-18 13:27 | 0.0074187
85 | 1 | 2026-02-18 13:29 | WA | Evi | Create SKEP S-32/KBC.0903/2026 dan S-33/KBC.0903/2026 (LJK) | Done | 2026-02-18 13:30 | 0.00055671
86 | 1 | 2026-02-20 14:16 | SAP |  | Melanjutkan no 52 (API baru bisa diakses tgl 19/02/26) | Done | 2026-02-21 11:39 | 0.89055 | Pending API masih tidak bisa dipakai (error)
87 | 1 | 2026-02-20 14:38 | SAP |  | Meting di Showroom 2 terkait BBK | Done | 2026-02-20 15:38 | 0.04172
88 | 1 | 2026-02-20 15:00 | WA | Bu Tati | Revisi No Invoice (LJU) asa 700/PI/FEB/2026 menjadi 100/PI/FEB/2026 | Done | 2026-02-20 15:39 | 0.027006
89 | 1 | 2026-02-21 08:23 | WA | Bu Ade | Cek data PR 11260169 (LJK) belum rilis | Done | 2026-02-21 09:23 | 0.041563
90 | 1 | 2026-02-21 10:03 | Tiket |  | Ticket #DV-DT24000007302 data duplicat | Done | 2026-02-21 10:16 | 0.008972
91 | 1 | 2026-02-23 08:26 | SAP |  | Laporan Surat Jalan (P) menambahkan data BBK, SO, Invoice, Tujuan, Nama Material | Done | 2026-02-23 09:18 | 0.036127 | Kolom penghubung dengan tabel Invoice [ReferenceSDDocument] tidak ada pada APInya
92 | 1 | 2026-02-23 09:19 | SAP |  | LAPORAN GUDANG PACKING LEAD TIME (template) | Done | 2026-02-24 10:43 | 1.058
93 | 1 | 2026-02-23 10:06 | Tiket |  | Ticket #DV-DT24000007310 revisi atas no doc 5026003475 no aju asal 000040LEC39520260221001137 menjadi 000040LEC39520260221001138 | Done | 2026-02-23 10:22 | 0.011062
94 | 1 | 2026-02-23 14:12 | Telphone | Taufik | Menambahkan kolom LOT pada menu cek Invoice (BC) | Done | 2026-02-24 10:29 | 0.84482 | Tunggu Memo
95 | 1 | 2026-02-24 09:25 | Telphone | Bara | BBK BG-2602-00072 penamaann barangnya aneh (penamaan digabung antara desc, batch, dan beam) | Done | 2026-02-24 09:28 | 0.0019727
96 | 1 | 2026-02-24 10:30 | WA | Evi | PO 78260247 sama 78260234 amount tidak muncul di laproran pembelian | Done | 2026-02-24 10:41 | 0.0075668
97 | 1 | 2026-02-24 10:43 | SAP |  | Alihkan data API Batch ke Testenan, dan update mapping batch char terbarunya | Done | 2026-02-24 15:39 | 0.2053
98 | 1 | 2026-02-25 08:10 | SAP |  | LAPORAN GUDANG PACKING LIST KARTON PER KODE ORDER (template) | Done | 2026-02-25 15:36 | 0.30978
99 | 1 | 2026-02-25 08:10 | SAP |  | Penambahan Fitur print barcode bisa print banyak barcode | Done | 2026-02-25 14:04 | 0.24566
100 | 1 | 2026-02-25 08:29 | WA | Evi | vendor tidak muncul di BBK : AG-2602-00066 (LJK) | Done | 2026-02-25 08:29 | 0.00016481
101 | 1 | 2026-02-25 10:09 | WA | Dea OI | Material 1000001879 tidak bisa di GI (LJU) | Done | 2026-02-25 10:10 | 0.00059826
102 | 1 | 2026-02-25 11:23 | Telphone | Pa yedi | PO 72602048 edit keterangan | Done | 2026-02-25 11:24 | 0.00079803
103 | 1 | 2026-02-25 13:31 | Langsung | Taufik | GRS atas PO 72601746 (LJU) satuan tidak muncul | Done | 2026-02-25 13:32 | 0.00092002
104 | 1 | 2026-02-25 13:36 | Tiket |  | Ticket #DV-DT24000007338 revisi no aju 00040LEC39520260224001180 & 00040LEC39520260224001184 menjadi 000040LEC39520260224001180 & 000040LEC39520260224001184 | Done | 2026-02-25 14:13 | 0.02566
105 | 1 | 2026-02-26 08:23 | SAP |  | Melanjutkan no 52 (API baru bisa diakses tgl 25/02/26) | Done | 2026-02-26 16:04 | 0.32047
106 | 1 | 2026-02-26 10:00 | SAP |  | Belajar cara menambahkan batch char dan menampilkannya di form aplikasi SAP dengan Soltius | Done | 2026-02-26 12:03 | 0.085289
107 | 1 | 2026-02-26 14:47 | SAP |  | Ambil data barcode versi 2 (ambill all) | Done | 2026-02-28 09:01 | 1.7595 | Pending Dahulukan yang marketing intruksi Pa Bily
108 |  | 2026-02-14 |  |  | TIDAK MASUK CUTI
109 | 1 | 2026-02-28 08:11 | WA | Dea OI | Material 1000001880 (LJU) tidak bisa di transaksikan | Done | 2026-02-28 08:31 | 0.013734
110 | 1 | 2026-02-28 09:01 | Langsung | Pa Billy | Menambahkan kolom Batch/Lot di pembuatan SO Non Packing marketing (LJU) | Done | 2026-03-02 08:45 | 1.9892
111 | 1 | 2026-02-28 09:01 | Langsung | Pa Billy | Menambahkan kolom Batch/Lot di pembuatan Invoice Non Kain marketing (LJU) | Done | 2026-03-02 08:45 | 1.9892
112 | 1 | 2026-02-28 09:16 | WA | Evi | SJ SRJ-2602-010046 (LJK) ganti status kirim dari jual lokal jadi "-" | Done | 2026-02-28 09:21 | 0.0034141
113 | 1 | 2026-02-28 10:11 | Tiket |  | Ticket #DV-DT24000007371 | Done | 2026-02-28 10:47 | 0.02488
114 | 1 | 2026-03-02 10:11 | Telphone | Ibu Dea | Invoice no SJ G-26000493 dan G-26000495 harga tidak muncul | Done | 2026-03-02 10:22 | 0.0070501
115 | 1 | 2026-03-02 10:24 | Telphone | Pa Billy | Menambahkan kolom Batch/Lot di pembuatan SO Non Packing Cost Acounting (LJU) | Done | 2026-03-04 09:43 | 1.9717
116 | 1 | 2026-03-02 10:45 | Tiket |  | #DV-DT24000007392 no doc 5026003945 ganti tgl daftar jadi 28-02-2026 | Done | 2026-03-02 10:50 | 0.0033149
117 | 1 | 2026-03-03 08:39 | Telphone | Bagus | Menambahkan Lot di menu update BC | Done | 2026-03-03 13:56 | 0.22044
118 | 1 | 2026-03-03 11:11 | Tiket |  | Ticket #DV-DT24000007407 | Done | 2026-03-03 11:10 | -0.00010116
119 | 1 | 2026-03-03 11:11 | Tiket |  | Ticket #DV-DT24000007415 | Done | 2026-03-03 11:10 | -0.00010116
120 | 1 | 2026-03-03 13:57 | WA | Taufik | Revisi tgl daftar no doc 5026003967 (LJU) ke tgl 28-02-26 | Done | 2026-03-03 13:57 | 0
121 | 1 | 2026-03-03 14:11 | Telphone | Ibu Tina | SJ Ekport ganti total pcs jadi 211 asal 127 di invoice 171/CI/MARCH/2026 (LJU) | Done | 2026-03-03 14:12 | 0.00013889
122 | 1 | 2026-03-04 09:43 | SAP |  | Menambah fungsi onconflic saat pull data Asset pada menu master Asset | Done | 2026-03-04 13:42 | 0.166
123 | 1 | 2026-03-04 09:43 | SAP |  | Menambah fungsi onconflic saat pull data Delivery pada menu master Delivery | Done | 2026-03-04 14:10 | 0.18549
124 | 1 | 2026-03-04 10:27 | WA | Putri | Ubah Kontrak 06/KK-LJM/II/2026 (LJU) menjadi 06/KK-LJM/WVG/II/2026 | Done | 2026-03-04 10:37 | 0.00695
125 | 1 | 2026-03-04 14:10 | SAP |  | Menambah fungsi onconflic saat pull data Supplier pada menu master Supplier | Done | 2026-03-04 15:30 | 0.055556 | API tidak bisa diakses pertgl 04-03-26
126 | 1 | 2026-03-04 14:10 | SAP |  | Menambah fungsi onconflic saat pull data PO pada menu master PO | Done | 2026-03-04 15:30 | 0.055553
127 | 1 | 2026-03-05 09:21 | SAP |  | Buat UI penarikan data dari API dan insert data HandlingUnit | Done | 2026-03-05 10:56 | 0.066126
128 | 1 | 2026-03-05 10:27 | WA | Taufik | Penambahan Lot/Batch di modul BC (laporan Masuk dan keluar) Pzzl | Done | 2026-03-05 11:55 | 0.060878
129 | 1 | 2026-03-05 11:50 | Tiket |  | Ticket #DV-DT24000007452 update nilai kontrak asal 0 jadi 18600000 | Done | 2026-03-05 11:59 | 0.0062487
130 | 1 | 2026-03-05 13:01 | SAP |  | Transfering Knowledge BASIC | Done | 2026-03-05 14:37 | 0.066963
131 | 1 | 2026-03-05 15:28 | WA | Putri | Ubah SKEP, SJ, BBK 61/TPB-PR.01/KBC.09203/2026 menjadi 61/TPB-PR.01/KBC.0903/2026 | Done | 2026-03-05 15:43 | 0.010576
132 | 1 | 2026-03-06 08:21 | SAP |  | Menambah fungsi onconflic saat pull data BOM pada menu master BOM | Done | 2026-03-06 08:53 | 0.021993
133 | 1 | 2026-03-06 08:53 | SAP |  | Menambah fungsi pull data barcode final all | Done | 2026-03-10 10:59 | 4.0876
134 | 1 | 2026-03-06 10:23 | SAP |  | Pendampingan EUT di final LJ1 | Done | 2026-03-06 11:29 | 0.045324
135 | 1 | 2026-03-06 14:00 | SAP |  | Pendampingan EUT di final LJ2 | Done | 2026-03-06 16:03 | 0.085648
136 | 1 | 2026-03-07 08:20 | Langsung | Taufik | Menyiapkan data requesan Pa taufik | Done | 2026-03-07 10:12 | 0.07784
137 | 1 | 2026-03-09 08:23 | SAP |  | fix data Char Id no warna, tgl potong dan kartu proses belum keambil, dan fix layouting print barcode | Done | 2026-03-09 11:52 | 0.14523
138 | 1 | 2026-03-09 09:13 | WA | Visqia | Tautkan Lot material 7000005057 (LJK) error | Done | 2026-03-09 09:14 | 0.00045417
139 | 1 | 2026-03-09 10:13 | WA | Taufik | Lot di laporan pengeluaran BC geser | Done | 2026-03-09 11:14 | 0.042249
140 | 1 | 2026-03-09 10:13 | WA | Evi | Judul Report persediaan tidak sesuai | Done | 2026-03-09 10:44 | 0.021135
141 | 1 | 2026-03-09 11:15 | WA | Dini | Material 4000037436 tidak bisa didaftarkan batch REPAIRED (LJU) | Done | 2026-03-09 11:18 | 0.0021392
142 | 1 | 2026-03-09 11:15 | WA | Putri | Skep S-4200/KBC.0904/KBC.090407/2022 minta diinput perpanjangan oleh Skep S-1852/KBC.0903/2025. | Done | 2026-03-09 11:52 | 0.026253
143 | 1 | 2026-03-09 11:22 | SAP |  | Pelatihan Tambah Field SAP jam 14.00 di R.Manager Enginering | Done | 2026-03-09 16:05 | 0.19676
144 | 1 | 2026-03-10 08:16 | SAP |  | Fix Bug Error Penambahan Menu ke dalam Role | Done | 2026-03-10 15:04 | 0.28353
145 | 1 | 2026-03-10 11:00 | SAP |  | Buat UI report LAPORAN SURAT JALAN SLOC | Done | 2026-03-12 14:03 | 2.1272
146 | 1 | 2026-03-10 09:30 | WA | Evi | PO 78260512 seq 2 amount tidak muncul | Done | 2026-03-10 09:46 | 0.011108
147 | 1 | 2026-03-10 11:18 | WA | Evi | Sj SRJ-2603-010019 (LJK) tambah keterangan | Done | 2026-03-10 11:20 | 0.0014583
148 | 1 | 2026-03-10 15:21 | Tiket |  | Ticket #DV-DT24000007539 | Done | 2026-03-10 15:33 | 0.0084235
149 | 1 | 2026-03-11 10:38 | Telphone | Bagus | Data Pengeluaran BC netto 0 | Done | 2026-03-11 11:16 | 0.026586
150 | 1 | 2026-03-12 08:17 | Telphone | Ibu Desy | SKEP 981/TPB-SK.01/KBC.0903/2026 tidak bisa muncul di pembuatan BPB | Done | 2026-03-12 08:18 | 0.00049653
151 | 1 | 2026-03-12 08:51 | Langsung | Pa Billy | Create Module Pembuatan Batch Panjang (LJM) (mis_ljm) | Done | 2026-03-12 11:46 | 0.12127
152 | 1 | 2026-03-12 09:27 | WA | Ibu Indah | Ubah Satuan di PR 10260742 (LJU) atas kode material '4000054380','4000054381','4000054382','4000054388','4000054383','4000054379' asal BH jadi PCE | Done | 2026-03-12 09:28 | 0.00061169
153 | 1 | 2026-03-12 13:23 | BC | Memo | Memo 015/SL-AAA/LJ1/0326 Poin No 1 | Done | 2026-03-12 14:40 | 0.053563
154 | 1 | 2026-03-12 14:43 | BC | Memo | Memo 015/SL-AAA/LJ1/0326 Poin No 2 | Done | 2026-03-13 08:39 | 0.74697
155 | 1 | 2026-03-13 08:39 | BC | Memo | Memo 015/SL-AAA/LJ1/0326 Poin No 3 | Done | 2026-03-13 15:40 | 0.2925
156 | 1 | 2026-03-13 09:57 | BC | Pa Dian | Transfering Knowledge dari Star terkait Host to Host | Done | 2026-03-13 14:40 | 0.19656 | Batal Meting di 234
157 |  | 2026-03-14 |  |  | TIDAK MASUK SAKIT |  |  | -46095
158 | 1 | 2026-03-16 08:19 | BC | Pa Dian | Transfering Knowledge dari Star terkait Host to Host | Done | 2026-03-16 14:30 | 0.25763
159 | 1 | 2026-03-17 08:07 | BC | Memo | Memo 015/SL-AAA/LJ1/0326 Poin No 5 | Done | 2026-03-17 10:03 | 0.080523
160 | 1 | 2026-03-17 10:31 | Langsung | Pa Billy | DRM | Done | 2026-03-17 11:01 | 0.020764
161 | 1 | 2026-03-17 10:27 | Tiket |  | Ticket #DV-DT24000007598 | Done | 2026-03-17 11:53 | 0.059648
162 | 1 | 2026-03-25 06:31 | BC | Memo | Memo 015/SL-AAA/LJ1/0326 Poin No 3 (Create BOM) | Done | 2026-03-25 13:23 | 0.28593
163 | 1 | 2026-03-26 06:41 | BC | Memo | Memo 015/SL-AAA/LJ1/0326 Poin No 4 | Done | 2026-03-26 12:58 | 0.26171
164 | 1 | 2026-03-27 10:00 | BC | Memo | Memo 015/SL-AAA/LJ1/0326 Poin No 6 | Done | 2026-03-27 15:51 | 0.24325
165 | 1 | 2026-03-27 15:19 | WA | Bu Desi | Upload SKEP LJU ke LJK | Done | 2026-03-27 15:52 | 0.023008
166 | 1 | 2026-03-28 08:24 | BC | Memo | Memo 015/SL-AAA/LJ1/0326 Poin No 7 | Done | 2026-03-28 10:03 | 0.06887
167 | 1 | 2026-03-28 10:12 | BC | Bu Desi | Update menu create Kontrak dan SKEP jika LJK maka otomatis simpan di DB LJK juga |  |  | -46109.4251
168 | [7 empty] | 0
169 | [7 empty] | 0
170 | [7 empty] | 0
171 | [7 empty] | 0
172 | [7 empty] | 0
173 | [7 empty] | 0
174 | [7 empty] | 0
175 | [7 empty] | 0
176 | [7 empty] | 0
177 | [7 empty] | 0
178 | [7 empty] | 0
179 | [7 empty] | 0
180 | [7 empty] | 0
181 | [7 empty] | 0
182 | [7 empty] | 0
183 | [7 empty] | 0
184 | [7 empty] | 0
185 | [7 empty] | 0
186 | [7 empty] | 0
187 | [7 empty] | 0
188 | [7 empty] | 0
189 | [7 empty] | 0
190 | [7 empty] | 0
191 | [7 empty] | 0
192 | [7 empty] | 0
193 | [7 empty] | 0
194 | [7 empty] | 0
195 | [7 empty] | 0
196 | [7 empty] | 0
197 | [7 empty] | 0
198 | [7 empty] | 0
199 | [7 empty] | 0
200 | [7 empty] | 0
201 | [7 empty] | 0
202 | [7 empty] | 0
203 | [7 empty] | 0
204 | [7 empty] | 0
205 | [7 empty] | 0
206 | [7 empty] | 0
207 | [7 empty] | 0
208 | [7 empty] | 0
209 | [7 empty] | 0
210 | [7 empty] | 0
211 | [7 empty] | 0
212 | [7 empty] | 0
213 | [7 empty] | 0
214 | [7 empty] | 0
215 | [7 empty] | 0
216 | [7 empty] | 0
217 | [7 empty] | 0
218 | [7 empty] | 0
219 | [7 empty] | 0
220 | [7 empty] | 0
221 | [7 empty] | 0
222 | [7 empty] | 0
223 | [7 empty] | 0
224 | [7 empty] | 0
225 | [7 empty] | 0
226 | [7 empty] | 0
227 | [7 empty] | 0
228 | [7 empty] | 0
229 | [7 empty] | 0
230 | [7 empty] | 0
231 | [7 empty] | 0
232 | [7 empty] | 0
233 | [7 empty] | 0
234 | [7 empty] | 0
235 | [7 empty] | 0
236 | [7 empty] | 0
237 | [7 empty] | 0
238 | [7 empty] | 0
239 | [7 empty] | 0
240 | [7 empty] | 0
241 | [7 empty] | 0
242 | [7 empty] | 0
243 | [7 empty] | 0
244 | [7 empty] | 0
245 | [7 empty] | 0
246 | [7 empty] | 0
247 | [7 empty] | 0
248 | [7 empty] | 0
249 | [7 empty] | 0
250 | [7 empty] | 0
251 | [7 empty] | 0
252 | [7 empty] | 0
253 | [7 empty] | 0
254 | [7 empty] | 0
255 | [7 empty] | 0
256 | [7 empty] | 0
257 | [7 empty] | 0
258 | [7 empty] | 0
259 | [7 empty] | 0
260 | [7 empty] | 0
261 | [7 empty] | 0
262 | [7 empty] | 0
263 | [7 empty] | 0
264 | [7 empty] | 0
265 | [7 empty] | 0
266 | [7 empty] | 0
267 | [7 empty] | 0
268 | [7 empty] | 0
269 | [7 empty] | 0
270 | [7 empty] | 0
271 | [7 empty] | 0
272 | [7 empty] | 0
273 | [7 empty] | 0
274 | [7 empty] | 0
275 | [7 empty] | 0
276 | [7 empty] | 0
277 | [7 empty] | 0
278 | [7 empty] | 0
279 | [7 empty] | 0
280 | [7 empty] | 0
281 | [7 empty] | 0
282 | [7 empty] | 0
283 | [7 empty] | 0
284 | [7 empty] | 0
285 | [7 empty] | 0
286 | [7 empty] | 0
287 | [7 empty] | 0
288 | [7 empty] | 0
289 | [7 empty] | 0
290 | [7 empty] | 0
291 | [7 empty] | 0
292 | [7 empty] | 0
293 | [7 empty] | 0
294 | [7 empty] | 0
295 | [7 empty] | 0
296 | [7 empty] | 0
297 | [7 empty] | 0
298 | [7 empty] | 0
299 | [7 empty] | 0
300 | [7 empty] | 0
301 | [7 empty] | 0
302 | [7 empty] | 0
303 | [7 empty] | 0
304 | [7 empty] | 0
305 | [7 empty] | 0
306 | [7 empty] | 0
307 | [7 empty] | 0
308 | [7 empty] | 0
309 | [7 empty] | 0
310 | [7 empty] | 0
311 | [7 empty] | 0
312 | [7 empty] | 0
313 | [7 empty] | 0
314 | [7 empty] | 0
315 | [7 empty] | 0
316 | [7 empty] | 0
317 | [7 empty] | 0
318 | [7 empty] | 0
319 | [7 empty] | 0
320 | [7 empty] | 0
321 | [7 empty] | 0
322 | [7 empty] | 0
323 | [7 empty] | 0
324 | [7 empty] | 0
325 | [7 empty] | 0
326 | [7 empty] | 0
327 | [7 empty] | 0
328 | [7 empty] | 0
329 | [7 empty] | 0
330 | [7 empty] | 0
331 | [7 empty] | 0
332 | [7 empty] | 0
333 | [7 empty] | 0
334 | [7 empty] | 0
335 | [7 empty] | 0
336 | [7 empty] | 0
337 | [7 empty] | 0
338 | [7 empty] | 0
339 | [7 empty] | 0
340 | [7 empty] | 0
341 | [7 empty] | 0
342 | [7 empty] | 0
343 | [7 empty] | 0
344 | [7 empty] | 0
345 | [7 empty] | 0
346 | [7 empty] | 0
347 | [7 empty] | 0
348 | [7 empty] | 0
349 | [7 empty] | 0
350 | [7 empty] | 0
351 | [7 empty] | 0
352 | [7 empty] | 0
353 | [7 empty] | 0
354 | [7 empty] | 0
355 | [7 empty] | 0
356 | [7 empty] | 0
357 | [7 empty] | 0
358 | [7 empty] | 0
359 | [7 empty] | 0
360 | [7 empty] | 0
361 | [7 empty] | 0
362 | [7 empty] | 0
363 | [7 empty] | 0
364 | [7 empty] | 0
365 | [7 empty] | 0
366 | [7 empty] | 0
367 | [7 empty] | 0
368 | [7 empty] | 0
369 | [7 empty] | 0
370 | [7 empty] | 0
371 | [7 empty] | 0
372 | [7 empty] | 0
373 | [7 empty] | 0
374 | [7 empty] | 0
375 | [7 empty] | 0
376 | [7 empty] | 0
377 | [7 empty] | 0
378 | [7 empty] | 0
379 | [7 empty] | 0
380 | [7 empty] | 0
381 | [7 empty] | 0
382 | [7 empty] | 0
383 | [7 empty] | 0
384 | [7 empty] | 0
385 | [7 empty] | 0
386 | [7 empty] | 0
387 | [7 empty] | 0
388 | [7 empty] | 0
389 | [7 empty] | 0
390 | [7 empty] | 0
391 | [7 empty] | 0
392 | [7 empty] | 0
393 | [7 empty] | 0
394 | [7 empty] | 0
395 | [7 empty] | 0
396 | [7 empty] | 0
397 | [7 empty] | 0
398 | [7 empty] | 0
399 | [7 empty] | 0
400 | [7 empty] | 0
401 | [7 empty] | 0
402 | [7 empty] | 0
403 | [7 empty] | 0
404 | [7 empty] | 0
405 | [7 empty] | 0
406 | [7 empty] | 0
407 | [7 empty] | 0
408 | [7 empty] | 0
409 | [7 empty] | 0
410 | [7 empty] | 0
411 | [7 empty] | 0
412 | [7 empty] | 0
413 | [7 empty] | 0
414 | [7 empty] | 0
415 | [7 empty] | 0
416 | [7 empty] | 0
417 | [7 empty] | 0
418 | [7 empty] | 0
419 | [7 empty] | 0
420 | [7 empty] | 0
421 | [7 empty] | 0
422 | [7 empty] | 0
423 | [7 empty] | 0
424 | [7 empty] | 0
425 | [7 empty] | 0
426 | [7 empty] | 0
427 | [7 empty] | 0
428 | [7 empty] | 0
429 | [7 empty] | 0
430 | [7 empty] | 0
431 | [7 empty] | 0
432 | [7 empty] | 0
433 | [7 empty] | 0
434 | [7 empty] | 0
435 | [7 empty] | 0
436 | [7 empty] | 0
437 | [7 empty] | 0
438 | [7 empty] | 0
439 | [7 empty] | 0
440 | [7 empty] | 0
441 | [7 empty] | 0
442 | [7 empty] | 0
443 | [7 empty] | 0
444 | [7 empty] | 0
445 | [7 empty] | 0
446 | [7 empty] | 0
447 | [7 empty] | 0
448 | [7 empty] | 0
449 | [7 empty] | 0
450 | [7 empty] | 0
451 | [7 empty] | 0
452 | [7 empty] | 0
453 | [7 empty] | 0
454 | [7 empty] | 0
455 | [7 empty] | 0
456 | [7 empty] | 0
457 | [7 empty] | 0
458 | [7 empty] | 0
459 | [7 empty] | 0
460 | [7 empty] | 0
461 | [7 empty] | 0
462 | [7 empty] | 0
463 | [7 empty] | 0
464 | [7 empty] | 0
465 | [7 empty] | 0
466 | [7 empty] | 0
467 | [7 empty] | 0
468 | [7 empty] | 0
469 | [7 empty] | 0
470 | [7 empty] | 0
471 | [7 empty] | 0
472 | [7 empty] | 0
473 | [7 empty] | 0
474 | [7 empty] | 0
475 | [7 empty] | 0
476 | [7 empty] | 0
477 | [7 empty] | 0
478 | [7 empty] | 0
479 | [7 empty] | 0
480 | [7 empty] | 0
481 | [7 empty] | 0
482 | [7 empty] | 0
483 | [7 empty] | 0
484 | [7 empty] | 0
485 | [7 empty] | 0
486 | [7 empty] | 0
487 | [7 empty] | 0
488 | [7 empty] | 0
489 | [7 empty] | 0
490 | [7 empty] | 0
491 | [7 empty] | 0
492 | [7 empty] | 0
493 | [7 empty] | 0
494 | [7 empty] | 0
495 | [7 empty] | 0
496 | [7 empty] | 0
497 | [7 empty] | 0
498 | [7 empty] | 0
499 | [7 empty] | 0
500 | [7 empty] | 0
501 | [7 empty] | 0
502 | [7 empty] | 0
503 | [7 empty] | 0
504 | [7 empty] | 0
505 | [7 empty] | 0
506 | [7 empty] | 0
507 | [7 empty] | 0
508 | [7 empty] | 0
509 | [7 empty] | 0
510 | [7 empty] | 0
511 | [7 empty] | 0
512 | [7 empty] | 0
513 | [7 empty] | 0
514 | [7 empty] | 0
515 | [7 empty] | 0
516 | [7 empty] | 0
517 | [7 empty] | 0
518 | [7 empty] | 0
519 | [7 empty] | 0
520 | [7 empty] | 0
521 | [7 empty] | 0
522 | [7 empty] | 0
523 | [7 empty] | 0
524 | [7 empty] | 0
525 | [7 empty] | 0
526 | [7 empty] | 0
527 | [7 empty] | 0
528 | [7 empty] | 0
529 | [7 empty] | 0
530 | [7 empty] | 0
531 | [7 empty] | 0
532 | [7 empty] | 0
533 | [7 empty] | 0
534 | [7 empty] | 0
535 | [7 empty] | 0
536 | [7 empty] | 0
537 | [7 empty] | 0
538 | [7 empty] | 0
539 | [7 empty] | 0
540 | [7 empty] | 0
541 | [7 empty] | 0
542 | [7 empty] | 0
543 | [7 empty] | 0
544 | [7 empty] | 0
545 | [7 empty] | 0
546 | [7 empty] | 0
547 | [7 empty] | 0
548 | [7 empty] | 0
549 | [7 empty] | 0
550 | [7 empty] | 0
551 | [7 empty] | 0
552 | [7 empty] | 0
553 | [7 empty] | 0
554 | [7 empty] | 0
555 | [7 empty] | 0
556 | [7 empty] | 0
557 | [7 empty] | 0
558 | [7 empty] | 0
559 | [7 empty] | 0
560 | [7 empty] | 0
561 | [7 empty] | 0
562 | [7 empty] | 0
563 | [7 empty] | 0
564 | [7 empty] | 0
565 | [7 empty] | 0
566 | [7 empty] | 0
567 | [7 empty] | 0
568 | [7 empty] | 0
569 | [7 empty] | 0
570 | [7 empty] | 0
571 | [7 empty] | 0
572 | [7 empty] | 0
573 | [7 empty] | 0
574 | [7 empty] | 0
575 | [7 empty] | 0
576 | [7 empty] | 0
577 | [7 empty] | 0
578 | [7 empty] | 0
579 | [7 empty] | 0
580 | [7 empty] | 0
581 | [7 empty] | 0
582 | [7 empty] | 0
583 | [7 empty] | 0
584 | [7 empty] | 0
585 | [7 empty] | 0
586 | [7 empty] | 0
587 | [7 empty] | 0
588 | [7 empty] | 0
589 | [7 empty] | 0
590 | [7 empty] | 0
591 | [7 empty] | 0
592 | [7 empty] | 0
593 | [7 empty] | 0
594 | [7 empty] | 0
595 | [7 empty] | 0
596 | [7 empty] | 0
597 | [7 empty] | 0
598 | [7 empty] | 0
599 | [7 empty] | 0
600 | [7 empty] | 0
601 | [7 empty] | 0
602 | [7 empty] | 0
603 | [7 empty] | 0
604 | [7 empty] | 0
605 | [7 empty] | 0
606 | [7 empty] | 0
607 | [7 empty] | 0
608 | [7 empty] | 0
609 | [7 empty] | 0
610 | [7 empty] | 0
611 | [7 empty] | 0
612 | [7 empty] | 0
613 | [7 empty] | 0
614 | [7 empty] | 0
615 | [7 empty] | 0
616 | [7 empty] | 0
617 | [7 empty] | 0
618 | [7 empty] | 0
619 | [7 empty] | 0
620 | [7 empty] | 0
621 | [7 empty] | 0
622 | [7 empty] | 0
623 | [7 empty] | 0
624 | [7 empty] | 0
625 | [7 empty] | 0
626 | [7 empty] | 0
627 | [7 empty] | 0
628 | [7 empty] | 0
629 | [7 empty] | 0
630 | [7 empty] | 0
631 | [7 empty] | 0
632 | [7 empty] | 0
633 | [7 empty] | 0
634 | [7 empty] | 0
635 | [7 empty] | 0
636 | [7 empty] | 0
637 | [7 empty] | 0
638 | [7 empty] | 0
639 | [7 empty] | 0
640 | [7 empty] | 0
641 | [7 empty] | 0
642 | [7 empty] | 0
643 | [7 empty] | 0
644 | [7 empty] | 0
645 | [7 empty] | 0
646 | [7 empty] | 0
647 | [7 empty] | 0
648 | [7 empty] | 0
649 | [7 empty] | 0
650 | [7 empty] | 0
651 | [7 empty] | 0
652 | [7 empty] | 0
653 | [7 empty] | 0
654 | [7 empty] | 0
655 | [7 empty] | 0
656 | [7 empty] | 0
657 | [7 empty] | 0
658 | [7 empty] | 0
659 | [7 empty] | 0
660 | [7 empty] | 0
661 | [7 empty] | 0
662 | [7 empty] | 0
663 | [7 empty] | 0
664 | [7 empty] | 0
665 | [7 empty] | 0
666 | [7 empty] | 0
667 | [7 empty] | 0
668 | [7 empty] | 0
669 | [7 empty] | 0
670 | [7 empty] | 0
671 | [7 empty] | 0
672 | [7 empty] | 0
673 | [7 empty] | 0
674 | [7 empty] | 0
675 | [7 empty] | 0
676 | [7 empty] | 0
677 | [7 empty] | 0
678 | [7 empty] | 0
679 | [7 empty] | 0
680 | [7 empty] | 0
681 | [7 empty] | 0
682 | [7 empty] | 0
683 | [7 empty] | 0
684 | [7 empty] | 0
685 | [7 empty] | 0
686 | [7 empty] | 0
687 | [7 empty] | 0
688 | [7 empty] | 0
689 | [7 empty] | 0
690 | [7 empty] | 0
691 | [7 empty] | 0
692 | [7 empty] | 0
693 | [7 empty] | 0
694 | [7 empty] | 0
695 | [7 empty] | 0
696 | [7 empty] | 0
697 | [7 empty] | 0
698 | [7 empty] | 0
699 | [7 empty] | 0
700 | [7 empty] | 0
701 | [7 empty] | 0
702 | [7 empty] | 0
703 | [7 empty] | 0
704 | [7 empty] | 0
705 | [7 empty] | 0
706 | [7 empty] | 0
707 | [7 empty] | 0
708 | [7 empty] | 0
709 | [7 empty] | 0
710 | [7 empty] | 0
711 | [7 empty] | 0
712 | [7 empty] | 0
713 | [7 empty] | 0
714 | [7 empty] | 0
715 | [7 empty] | 0
716 | [7 empty] | 0
717 | [7 empty] | 0
718 | [7 empty] | 0
719 | [7 empty] | 0
720 | [7 empty] | 0
721 | [7 empty] | 0
722 | [7 empty] | 0
723 | [7 empty] | 0
724 | [7 empty] | 0
725 | [7 empty] | 0
726 | [7 empty] | 0
727 | [7 empty] | 0
728 | [7 empty] | 0
729 | [7 empty] | 0
730 | [7 empty] | 0
731 | [7 empty] | 0
732 | [7 empty] | 0
733 | [7 empty] | 0
734 | [7 empty] | 0
735 | [7 empty] | 0
736 | [7 empty] | 0
737 | [7 empty] | 0
738 | [7 empty] | 0
739 | [7 empty] | 0
740 | [7 empty] | 0
741 | [7 empty] | 0
742 | [7 empty] | 0
743 | [7 empty] | 0
744 | [7 empty] | 0
745 | [7 empty] | 0
746 | [7 empty] | 0
747 | [7 empty] | 0
748 | [7 empty] | 0
749 | [7 empty] | 0
750 | [7 empty] | 0
751 | [7 empty] | 0
752 | [7 empty] | 0
753 | [7 empty] | 0
754 | [7 empty] | 0
755 | [7 empty] | 0
756 | [7 empty] | 0
757 | [7 empty] | 0
758 | [7 empty] | 0
759 | [7 empty] | 0
760 | [7 empty] | 0
761 | [7 empty] | 0
762 | [7 empty] | 0
763 | [7 empty] | 0
764 | [7 empty] | 0
765 | [7 empty] | 0
766 | [7 empty] | 0
767 | [7 empty] | 0
768 | [7 empty] | 0
769 | [7 empty] | 0
770 | [7 empty] | 0
771 | [7 empty] | 0
772 | [7 empty] | 0
773 | [7 empty] | 0
774 | [7 empty] | 0
775 | [7 empty] | 0
776 | [7 empty] | 0
777 | [7 empty] | 0
778 | [7 empty] | 0
779 | [7 empty] | 0
780 | [7 empty] | 0
781 | [7 empty] | 0
782 | [7 empty] | 0
783 | [7 empty] | 0
784 | [7 empty] | 0
785 | [7 empty] | 0
786 | [7 empty] | 0
787 | [7 empty] | 0
788 | [7 empty] | 0
789 | [7 empty] | 0
790 | [7 empty] | 0
791 | [7 empty] | 0
792 | [7 empty] | 0
793 | [7 empty] | 0
794 | [7 empty] | 0
795 | [7 empty] | 0
796 | [7 empty] | 0
797 | [7 empty] | 0
798 | [7 empty] | 0
799 | [7 empty] | 0
800 | [7 empty] | 0
801 | [7 empty] | 0
802 | [7 empty] | 0
803 | [7 empty] | 0
804 | [7 empty] | 0
805 | [7 empty] | 0
806 | [7 empty] | 0
807 | [7 empty] | 0
808 | [7 empty] | 0
809 | [7 empty] | 0
810 | [7 empty] | 0
811 | [7 empty] | 0
812 | [7 empty] | 0
813 | [7 empty] | 0
814 | [7 empty] | 0
815 | [7 empty] | 0
816 | [7 empty] | 0
817 | [7 empty] | 0
818 | [7 empty] | 0
819 | [7 empty] | 0
820 | [7 empty] | 0
821 | [7 empty] | 0
822 | [7 empty] | 0
823 | [7 empty] | 0
824 | [7 empty] | 0
825 | [7 empty] | 0
826 | [7 empty] | 0
827 | [7 empty] | 0
828 | [7 empty] | 0
829 | [7 empty] | 0
830 | [7 empty] | 0
831 | [7 empty] | 0
832 | [7 empty] | 0
833 | [7 empty] | 0
834 | [7 empty] | 0
835 | [7 empty] | 0
836 | [7 empty] | 0
837 | [7 empty] | 0
838 | [7 empty] | 0
839 | [7 empty] | 0
840 | [7 empty] | 0
841 | [7 empty] | 0
842 | [7 empty] | 0
843 | [7 empty] | 0
844 | [7 empty] | 0
845 | [7 empty] | 0
846 | [7 empty] | 0
847 | [7 empty] | 0
848 | [7 empty] | 0
849 | [7 empty] | 0
850 | [7 empty] | 0
851 | [7 empty] | 0
852 | [7 empty] | 0
853 | [7 empty] | 0
854 | [7 empty] | 0
855 | [7 empty] | 0
856 | [7 empty] | 0
857 | [7 empty] | 0
858 | [7 empty] | 0
859 | [7 empty] | 0
860 | [7 empty] | 0
861 | [7 empty] | 0
862 | [7 empty] | 0
863 | [7 empty] | 0
864 | [7 empty] | 0
865 | [7 empty] | 0
866 | [7 empty] | 0
867 | [7 empty] | 0
868 | [7 empty] | 0
869 | [7 empty] | 0
870 | [7 empty] | 0
871 | [7 empty] | 0
872 | [7 empty] | 0
873 | [7 empty] | 0
874 | [7 empty] | 0
875 | [7 empty] | 0
876 | [7 empty] | 0
877 | [7 empty] | 0
878 | [7 empty] | 0
879 | [7 empty] | 0
880 | [7 empty] | 0
881 | [7 empty] | 0
882 | [7 empty] | 0
883 | [7 empty] | 0
884 | [7 empty] | 0
885 | [7 empty] | 0
886 | [7 empty] | 0
887 | [7 empty] | 0
888 | [7 empty] | 0
889 | [7 empty] | 0
890 | [7 empty] | 0
891 | [7 empty] | 0
892 | [7 empty] | 0
893 | [7 empty] | 0
894 | [7 empty] | 0
895 | [7 empty] | 0
896 | [7 empty] | 0
897 | [7 empty] | 0
898 | [7 empty] | 0
899 | [7 empty] | 0
900 | [7 empty] | 0
901 | [7 empty] | 0
902 | [7 empty] | 0
903 | [7 empty] | 0
904 | [7 empty] | 0
905 | [7 empty] | 0
906 | [7 empty] | 0
907 | [7 empty] | 0
908 | [7 empty] | 0
909 | [7 empty] | 0
910 | [7 empty] | 0
911 | [7 empty] | 0
912 | [7 empty] | 0
913 | [7 empty] | 0
914 | [7 empty] | 0
915 | [7 empty] | 0
916 | [7 empty] | 0
917 | [7 empty] | 0
918 | [7 empty] | 0
919 | [7 empty] | 0
920 | [7 empty] | 0
921 | [7 empty] | 0
922 | [7 empty] | 0
923 | [7 empty] | 0
924 | [7 empty] | 0
925 | [7 empty] | 0
926 | [7 empty] | 0
927 | [7 empty] | 0
928 | [7 empty] | 0
929 | [7 empty] | 0
930 | [7 empty] | 0
931 | [7 empty] | 0
932 | [7 empty] | 0
933 | [7 empty] | 0
934 | [7 empty] | 0
935 | [7 empty] | 0
936 | [7 empty] | 0
937 | [7 empty] | 0
938 | [7 empty] | 0
939 | [7 empty] | 0
940 | [7 empty] | 0
941 | [7 empty] | 0
942 | [7 empty] | 0
943 | [7 empty] | 0
944 | [7 empty] | 0
945 | [7 empty] | 0
946 | [7 empty] | 0
947 | [7 empty] | 0
948 | [7 empty] | 0
949 | [7 empty] | 0
950 | [7 empty] | 0
951 | [7 empty] | 0
952 | [7 empty] | 0
953 | [7 empty] | 0
954 | [7 empty] | 0
955 | [7 empty] | 0
956 | [7 empty] | 0
957 | [7 empty] | 0
958 | [7 empty] | 0
959 | [7 empty] | 0
960 | [7 empty] | 0
961 | [7 empty] | 0
962 | [7 empty] | 0
963 | [7 empty] | 0
964 | [7 empty] | 0
965 | [7 empty] | 0
966 | [7 empty] | 0
967 | [7 empty] | 0
968 | [7 empty] | 0
969 | [7 empty] | 0
970 | [7 empty] | 0
971 | [7 empty] | 0
972 | [7 empty] | 0
973 | [7 empty] | 0
974 | [7 empty] | 0
975 | [7 empty] | 0
976 | [7 empty] | 0
977 | [7 empty] | 0
978 | [7 empty] | 0
979 | [7 empty] | 0
980 | [7 empty] | 0
981 | [7 empty] | 0
982 | [7 empty] | 0
983 | [7 empty] | 0
984 | [7 empty] | 0
985 | [7 empty] | 0
986 | [7 empty] | 0
987 | [7 empty] | 0
988 | [7 empty] | 0
989 | [7 empty] | 0
990 | [7 empty] | 0
991 | [7 empty] | 0
992 | [7 empty] | 0
993 | [7 empty] | 0
994 | [7 empty] | 0
995 | [7 empty] | 0
996 | [7 empty] | 0
997 | [7 empty] | 0
998 | [7 empty] | 0
999 | [7 empty] | 0
1000 | [7 empty] | 0
1001 | [7 empty] | 0
1002 | [7 empty] | 0
1003 | [7 empty] | 0
1004 | [7 empty] | 0
1005 | [7 empty] | 0
1006 | [7 empty] | 0
1007 | [7 empty] | 0
1008 | [7 empty] | 0
1009 | [7 empty] | 0
1010 | [7 empty] | 0
1011 | [7 empty] | 0
1012 | [7 empty] | 0
1013 | [7 empty] | 0
1014 | [7 empty] | 0
1015 | [7 empty] | 0
1016 | [7 empty] | 0
1017 | [7 empty] | 0
1018 | [7 empty] | 0
1019 | [7 empty] | 0
1020 | [7 empty] | 0
1021 | [7 empty] | 0
1022 | [7 empty] | 0
1023 | [7 empty] | 0
1024 | [7 empty] | 0
1025 | [7 empty] | 0
1026 | [7 empty] | 0
1027 | [7 empty] | 0
1028 | [7 empty] | 0
1029 | [7 empty] | 0
1030 | [7 empty] | 0
1031 | [7 empty] | 0
1032 | [7 empty] | 0
1033 | [7 empty] | 0
1034 | [7 empty] | 0
1035 | [7 empty] | 0
1036 | [7 empty] | 0
1037 | [7 empty] | 0
1038 | [7 empty] | 0
1039 | [7 empty] | 0
1040 | [7 empty] | 0
1041 | [7 empty] | 0
1042 | [7 empty] | 0
1043 | [7 empty] | 0
1044 | [7 empty] | 0
1045 | [7 empty] | 0
1046 | [7 empty] | 0
1047 | [7 empty] | 0
1048 | [7 empty] | 0
1049 | [7 empty] | 0
1050 | [7 empty] | 0
1051 | [7 empty] | 0
1052 | [7 empty] | 0
1053 | [7 empty] | 0
1054 | [7 empty] | 0
1055 | [7 empty] | 0
1056 | [7 empty] | 0
1057 | [7 empty] | 0
1058 | [7 empty] | 0
1059 | [7 empty] | 0
1060 | [7 empty] | 0
1061 | [7 empty] | 0
1062 | [7 empty] | 0
1063 | [7 empty] | 0
1064 | [7 empty] | 0
1065 | [7 empty] | 0
1066 | [7 empty] | 0
1067 | [7 empty] | 0
1068 | [7 empty] | 0
1069 | [7 empty] | 0
1070 | [7 empty] | 0
1071 | [7 empty] | 0
1072 | [7 empty] | 0
1073 | [7 empty] | 0
1074 | [7 empty] | 0
1075 | [7 empty] | 0
1076 | [7 empty] | 0
1077 | [7 empty] | 0
1078 | [7 empty] | 0
1079 | [7 empty] | 0
1080 | [7 empty] | 0
1081 | [7 empty] | 0
1082 | [7 empty] | 0
1083 | [7 empty] | 0
1084 | [7 empty] | 0
1085 | [7 empty] | 0
1086 | [7 empty] | 0
1087 | [7 empty] | 0
1088 | [7 empty] | 0
1089 | [7 empty] | 0
1090 | [7 empty] | 0
1091 | [7 empty] | 0
1092 | [7 empty] | 0
1093 | [7 empty] | 0
1094 | [7 empty] | 0
1095 | [7 empty] | 0
1096 | [7 empty] | 0
1097 | [7 empty] | 0
1098 | [7 empty] | 0
1099 | [7 empty] | 0
1100 | [7 empty] | 0
1101 | [7 empty] | 0
1102 | [7 empty] | 0
1103 | [7 empty] | 0
1104 | [7 empty] | 0
1105 | [7 empty] | 0
1106 | [7 empty] | 0
1107 | [7 empty] | 0
1108 | [7 empty] | 0
1109 | [7 empty] | 0
1110 | [7 empty] | 0
1111 | [7 empty] | 0
1112 | [7 empty] | 0
1113 | [7 empty] | 0
1114 | [7 empty] | 0
1115 | [7 empty] | 0
1116 | [7 empty] | 0
1117 | [7 empty] | 0
1118 | [7 empty] | 0
1119 | [7 empty] | 0
1120 | [7 empty] | 0
1121 | [7 empty] | 0
1122 | [7 empty] | 0
1123 | [7 empty] | 0
1124 | [7 empty] | 0
1125 | [7 empty] | 0
1126 | [7 empty] | 0
1127 | [7 empty] | 0
1128 | [7 empty] | 0
1129 | [7 empty] | 0
1130 | [7 empty] | 0
1131 | [7 empty] | 0
1132 | [7 empty] | 0
1133 | [7 empty] | 0
1134 | [7 empty] | 0
1135 | [7 empty] | 0
1136 | [7 empty] | 0
1137 | [7 empty] | 0
1138 | [7 empty] | 0
1139 | [7 empty] | 0
1140 | [7 empty] | 0
1141 | [7 empty] | 0
1142 | [7 empty] | 0
1143 | [7 empty] | 0
1144 | [7 empty] | 0
1145 | [7 empty] | 0
1146 | [7 empty] | 0
1147 | [7 empty] | 0
1148 | [7 empty] | 0
1149 | [7 empty] | 0
1150 | [7 empty] | 0
1151 | [7 empty] | 0
1152 | [7 empty] | 0
1153 | [7 empty] | 0
1154 | [7 empty] | 0
1155 | [7 empty] | 0
1156 | [7 empty] | 0
1157 | [7 empty] | 0
1158 | [7 empty] | 0
1159 | [7 empty] | 0
1160 | [7 empty] | 0
1161 | [7 empty] | 0
1162 | [7 empty] | 0
1163 | [7 empty] | 0
1164 | [7 empty] | 0
1165 | [7 empty] | 0
1166 | [7 empty] | 0
1167 | [7 empty] | 0
1168 | [7 empty] | 0
1169 | [7 empty] | 0
1170 | [7 empty] | 0
1171 | [7 empty] | 0
1172 | [7 empty] | 0
1173 | [7 empty] | 0
1174 | [7 empty] | 0
1175 | [7 empty] | 0
1176 | [7 empty] | 0
1177 | [7 empty] | 0
1178 | [7 empty] | 0
1179 | [7 empty] | 0
1180 | [7 empty] | 0
1181 | [7 empty] | 0
1182 | [7 empty] | 0
1183 | [7 empty] | 0
1184 | [7 empty] | 0
1185 | [7 empty] | 0
1186 | [7 empty] | 0
1187 | [7 empty] | 0
1188 | [7 empty] | 0
1189 | [7 empty] | 0
1190 | [7 empty] | 0
1191 | [7 empty] | 0
1192 | [7 empty] | 0
1193 | [7 empty] | 0
1194 | [7 empty] | 0
1195 | [7 empty] | 0
1196 | [7 empty] | 0
1197 | [7 empty] | 0
1198 | [7 empty] | 0
1199 | [7 empty] | 0
1200 | [7 empty] | 0
1201 | [7 empty] | 0
1202 | [7 empty] | 0
1203 | [7 empty] | 0
1204 | [7 empty] | 0
1205 | [7 empty] | 0
1206 | [7 empty] | 0
1207 | [7 empty] | 0
1208 | [7 empty] | 0
1209 | [7 empty] | 0
1210 | [7 empty] | 0
1211 | [7 empty] | 0
1212 | [7 empty] | 0
1213 | [7 empty] | 0
1214 | [7 empty] | 0
1215 | [7 empty] | 0
1216 | [7 empty] | 0
1217 | [7 empty] | 0
1218 | [7 empty] | 0
1219 | [7 empty] | 0
1220 | [7 empty] | 0
1221 | [7 empty] | 0
1222 | [7 empty] | 0
1223 | [7 empty] | 0
1224 | [7 empty] | 0
1225 | [7 empty] | 0
1226 | [7 empty] | 0
1227 | [7 empty] | 0
1228 | [7 empty] | 0
1229 | [7 empty] | 0
1230 | [7 empty] | 0
1231 | [7 empty] | 0
1232 | [7 empty] | 0
1233 | [7 empty] | 0
1234 | [7 empty] | 0
1235 | [7 empty] | 0
1236 | [7 empty] | 0
1237 | [7 empty] | 0
1238 | [7 empty] | 0
1239 | [7 empty] | 0
1240 | [7 empty] | 0
1241 | [7 empty] | 0
1242 | [7 empty] | 0
1243 | [7 empty] | 0
1244 | [7 empty] | 0
1245 | [7 empty] | 0
1246 | [7 empty] | 0
1247 | [7 empty] | 0
1248 | [7 empty] | 0
1249 | [7 empty] | 0
1250 | [7 empty] | 0
1251 | [7 empty] | 0
1252 | [7 empty] | 0
1253 | [7 empty] | 0
1254 | [7 empty] | 0
1255 | [7 empty] | 0
1256 | [7 empty] | 0
1257 | [7 empty] | 0
1258 | [7 empty] | 0
1259 | [7 empty] | 0
1260 | [7 empty] | 0
1261 | [7 empty] | 0
1262 | [7 empty] | 0
1263 | [7 empty] | 0
1264 | [7 empty] | 0
1265 | [7 empty] | 0
1266 | [7 empty] | 0
1267 | [7 empty] | 0
1268 | [7 empty] | 0
1269 | [7 empty] | 0
1270 | [7 empty] | 0
1271 | [7 empty] | 0
1272 | [7 empty] | 0
1273 | [7 empty] | 0
1274 | [7 empty] | 0
1275 | [7 empty] | 0
1276 | [7 empty] | 0
1277 | [7 empty] | 0
1278 | [7 empty] | 0
1279 | [7 empty] | 0
1280 | [7 empty] | 0
1281 | [7 empty] | 0
1282 | [7 empty] | 0
1283 | [7 empty] | 0
1284 | [7 empty] | 0
1285 | [7 empty] | 0
1286 | [7 empty] | 0
1287 | [7 empty] | 0
1288 | [7 empty] | 0
1289 | [7 empty] | 0
1290 | [7 empty] | 0
1291 | [7 empty] | 0
1292 | [7 empty] | 0
1293 | [7 empty] | 0
1294 | [7 empty] | 0
1295 | [7 empty] | 0
1296 | [7 empty] | 0
1297 | [7 empty] | 0
1298 | [7 empty] | 0
1299 | [7 empty] | 0
1300 | [7 empty] | 0
1301 | [7 empty] | 0
1302 | [7 empty] | 0
1303 | [7 empty] | 0
1304 | [7 empty] | 0
1305 | [7 empty] | 0
1306 | [7 empty] | 0
1307 | [7 empty] | 0
1308 | [7 empty] | 0
1309 | [7 empty] | 0
1310 | [7 empty] | 0
1311 | [7 empty] | 0
1312 | [7 empty] | 0
1313 | [7 empty] | 0
1314 | [7 empty] | 0
1315 | [7 empty] | 0
1316 | [7 empty] | 0
1317 | [7 empty] | 0
1318 | [7 empty] | 0
1319 | [7 empty] | 0
1320 | [7 empty] | 0
1321 | [7 empty] | 0
1322 | [7 empty] | 0
1323 | [7 empty] | 0
1324 | [7 empty] | 0
1325 | [7 empty] | 0
1326 | [7 empty] | 0
1327 | [7 empty] | 0
1328 | [7 empty] | 0
1329 | [7 empty] | 0
1330 | [7 empty] | 0
1331 | [7 empty] | 0
1332 | [7 empty] | 0
1333 | [7 empty] | 0
1334 | [7 empty] | 0
1335 | [7 empty] | 0
1336 | [7 empty] | 0
1337 | [7 empty] | 0
1338 | [7 empty] | 0
1339 | [7 empty] | 0
1340 | [7 empty] | 0
1341 | [7 empty] | 0
1342 | [7 empty] | 0
1343 | [7 empty] | 0
1344 | [7 empty] | 0
1345 | [7 empty] | 0
1346 | [7 empty] | 0
1347 | [7 empty] | 0
1348 | [7 empty] | 0
1349 | [7 empty] | 0
1350 | [7 empty] | 0
1351 | [7 empty] | 0
1352 | [7 empty] | 0
1353 | [7 empty] | 0
1354 | [7 empty] | 0
1355 | [7 empty] | 0
1356 | [7 empty] | 0
1357 | [7 empty] | 0
1358 | [7 empty] | 0
1359 | [7 empty] | 0
1360 | [7 empty] | 0
1361 | [7 empty] | 0
1362 | [7 empty] | 0
1363 | [7 empty] | 0
1364 | [7 empty] | 0
1365 | [7 empty] | 0
1366 | [7 empty] | 0
1367 | [7 empty] | 0
1368 | [7 empty] | 0
1369 | [7 empty] | 0
1370 | [7 empty] | 0
1371 | [7 empty] | 0
1372 | [7 empty] | 0
1373 | [7 empty] | 0
1374 | [7 empty] | 0
1375 | [7 empty] | 0
1376 | [7 empty] | 0
1377 | [7 empty] | 0
1378 | [7 empty] | 0
1379 | [7 empty] | 0
1380 | [7 empty] | 0
1381 | [7 empty] | 0
1382 | [7 empty] | 0
1383 | [7 empty] | 0
1384 | [7 empty] | 0
1385 | [7 empty] | 0
1386 | [7 empty] | 0
1387 | [7 empty] | 0
1388 | [7 empty] | 0
1389 | [7 empty] | 0
1390 | [7 empty] | 0
1391 | [7 empty] | 0
1392 | [7 empty] | 0
1393 | [7 empty] | 0
1394 | [7 empty] | 0
1395 | [7 empty] | 0
1396 | [7 empty] | 0
1397 | [7 empty] | 0
1398 | [7 empty] | 0
1399 | [7 empty] | 0
1400 | [7 empty] | 0
1401 | [7 empty] | 0
1402 | [7 empty] | 0
1403 | [7 empty] | 0
1404 | [7 empty] | 0
1405 | [7 empty] | 0
1406 | [7 empty] | 0
1407 | [7 empty] | 0
1408 | [7 empty] | 0
1409 | [7 empty] | 0
1410 | [7 empty] | 0
1411 | [7 empty] | 0
1412 | [7 empty] | 0
1413 | [7 empty] | 0
1414 | [7 empty] | 0
1415 | [7 empty] | 0
1416 | [7 empty] | 0
1417 | [7 empty] | 0
1418 | [7 empty] | 0
1419 | [7 empty] | 0
1420 | [7 empty] | 0
1421 | [7 empty] | 0
1422 | [7 empty] | 0
1423 | [7 empty] | 0
1424 | [7 empty] | 0
1425 | [7 empty] | 0
1426 | [7 empty] | 0
1427 | [7 empty] | 0
1428 | [7 empty] | 0
1429 | [7 empty] | 0
1430 | [7 empty] | 0
1431 | [7 empty] | 0
1432 | [7 empty] | 0
1433 | [7 empty] | 0
1434 | [7 empty] | 0
1435 | [7 empty] | 0
1436 | [7 empty] | 0
1437 | [7 empty] | 0
1438 | [7 empty] | 0
1439 | [7 empty] | 0
1440 | [7 empty] | 0
1441 | [7 empty] | 0
1442 | [7 empty] | 0
1443 | [7 empty] | 0
1444 | [7 empty] | 0
1445 | [7 empty] | 0
1446 | [7 empty] | 0
1447 | [7 empty] | 0
1448 | [7 empty] | 0
1449 | [7 empty] | 0
1450 | [7 empty] | 0
1451 | [7 empty] | 0
1452 | [7 empty] | 0
1453 | [7 empty] | 0
1454 | [7 empty] | 0
1455 | [7 empty] | 0
1456 | [7 empty] | 0
1457 | [7 empty] | 0
1458 | [7 empty] | 0
1459 | [7 empty] | 0
1460 | [7 empty] | 0
1461 | [7 empty] | 0
1462 | [7 empty] | 0
1463 | [7 empty] | 0
1464 | [7 empty] | 0
1465 | [7 empty] | 0
1466 | [7 empty] | 0
1467 | [7 empty] | 0
1468 | [7 empty] | 0
1469 | [7 empty] | 0
1470 | [7 empty] | 0
1471 | [7 empty] | 0
1472 | [7 empty] | 0
1473 | [7 empty] | 0
1474 | [7 empty] | 0
1475 | [7 empty] | 0
1476 | [7 empty] | 0
1477 | [7 empty] | 0
1478 | [7 empty] | 0
1479 | [7 empty] | 0
1480 | [7 empty] | 0
1481 | [7 empty] | 0
1482 | [7 empty] | 0
Note on F29: bram: Link API masih error (on cek pa Habil)
Note on F37: bram: Create Module Master Delivery template
Note on G44: bram: Sudah direvisi rate persenya lupa tapi nilai amounya sudah

## bc 1
BC(75% BC, 25% SAP)
| Project Start Date | 2026-03-26 |  |  |  | Display Week | 1 |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8
| Project Lead | Billy | [6 empty] | 2026-03-23 | [6 empty] | 2026-03-30 | [6 empty] | 2026-04-06 | [6 empty] | 2026-04-13 | [6 empty] | 2026-04-20 | [6 empty] | 2026-04-27 | [6 empty] | 2026-05-04 | [6 empty] | 2026-05-11
 | time axis 2026-03-23 to 2026-05-17
WBS | TASK | PIC | MEMO | START | END | DAYS | % DONE | WORK DAYS | time axis 2026-03-23 to 2026-05-17
1 | BC app development |  |  |  | - |  |  | -
1.1 | Menu Beacukai, Sub Menu Update Dok Keluar Market, Form Traceability Belum Ada Di MCS LJK [http://192.168.255.84/pzzl/index.php/Legal/updateKeluar2] | Baim | 015/SL-AAA/LJ1/0326 | 2026-03-26 | 2026-03-26 | 1 | 100% | 1
1.2 | Menu Beacukai, Sub Menu Update Dok Non-Keluar Market, Form Traceability Belum Ada Di MCS LJK[http://192.168.255.84/pzzl/index.php/Legal/updateKeluar] | Baim | 015/SL-AAA/LJ1/0326 | 2026-03-26 | 2026-03-26 | 1 | 100% | 1
1.3 | Menu Laporan Keluar/Masuk, Sub Menu Balance Lokal Belum Ada Di MCS LJK[http://192.168.255.84/pzzl/index.php/Legal/balancing\_local] | Baim | 015/SL-AAA/LJ1/0326 | 2026-03-27 | 2026-03-27 | 1 | 100% | 1
1.4 | Menu Print, Sub menu Packing List Dan Invoice Belum Ada Di MCS LJK [http://192.168.255.84/pzzl/index.php/Legal/packingListInvoice] | Baim | 015/SL-AAA/LJ1/0326 | 2026-03-28 | 2026-03-30 | 3 | 100% | 1
1.5 | Menu Mutasi, Sub menu Bahan Bakar Belum Ada Di IT INVENTORY LJK[http://192.168.255.84/leuwitex/beacukai/rMutBBM] | Baim | 015/SL-AAA/LJ1/0326 | 2026-03-30 | 2026-03-30 | 1 | 0% | 1
1.6 | 1a Menambah kolom : Asal Doc , No Daftar dan Tanggal daftar(/pzzl/index.php/Warehouse/laporanKeluar) | Baim | 142/ML-OFF/LJ1/1125 | 2026-03-31 | 2026-03-31 | 1 | 0% | 1
1.7 | 1b Menambah menu Edit untuk Pengisian Asal DOC, No Daftar dan Tanggal Daftar(/pzzl/index.php/Warehouse/laporanMasuk) | Baim | 142/ML-OFF/LJ1/1125 | 2026-04-01 | 2026-04-01 | 1 | 0% | 1
1.8 | 2 Belum tersedia untuk user LJK(/pzzl/index.php/MIT/dashboard) | Baim | 142/ML-OFF/LJ1/1125 | 2026-04-02 | 2026-04-02 | 1 | 0% | 1
1.9 | 3a penambahan kolom dengan nama QTY Keluar Tunggu Doc BC(/pzzl/index.php/Reporting/reportMR) | Baim | 142/ML-OFF/LJ1/1125 | 2026-04-03 | 2026-04-03 | 1 | 0% | 1
1.10 | 3b saldo buku belum berkurang jika doc bc belum terupdate(/pzzl/index.php/Reporting/reportMR) | Baim | 142/ML-OFF/LJ1/1125 | 2026-04-04 | 2026-04-04 | 1 | 0% | 0
1.11 | 4 Laporan mutasi yg muncul sesuai dengan user yang digunakan(/pzzl/index.php/Reporting/reportMR) | Baim | 142/ML-OFF/LJ1/1125 | 2026-04-05 | 2026-04-05 | 1 | 0% | 0
1 | Report |  |  |  | - |  |  | -
1.1 | REPORT - WM - MOVING HISTORY - GUDANG GREY | Billy, Baim |  | 2026-02-04 | 2026-02-10 | 7 | 0% | 5
1.2 | REPORT - WM - STOCK PER BARCODE | Baim |  | 2026-02-11 | 2026-02-17 | 7 | 0% | 5
1.3 | REPORT - WM - LAPORAN PERSEDIAAN GUDANG PACKING | Budi |  | 2026-02-11 | 2026-02-17 | 7 | 0% | 5
1.4 | REPORT - WM - LAPORAN GUDANG PACKING LEAD TIME | Baim |  | 2026-02-18 | 2026-02-24 | 7 | 0% | 5
1.5 | REPORT - WM - LIST KARTON PER KODE ORDER | Budi |  | 2026-02-18 | 2026-02-24 | 7 | 0% | 5
1.6 | REPORT - WM - MOVING HISTORY PER BARCODE | Baim |  | 2026-02-25 | 2026-03-03 | 7 | 0% | 5
1.7 | REPORT - WM - MOVING HISTORY PER LIST KARTON | Budi |  | 2026-02-25 | 2026-03-03 | 7 | 0% | 5
1.8 | REPORT - MM - STOCK KAIN GREY (GRADE) | Billy, Budi |  | 2026-02-04 | 2026-02-10 | 7 | 0% | 5
1.9 | REPORT - MM - STOCK LEADTIME | Baim |  | 2026-03-04 | 2026-03-10 | 7 | 0% | 5
1.10 | REPORT - MM - STOCK GREY LEAD TIME PER GRADE | Budi |  | 2026-03-04 | 2026-03-10 | 7 | 0% | 5
1.11 | REPORT - MM - STOCK BALANCE KAIN GREY | Budi |  | 2026-03-11 | 2026-03-17 | 7 | 0% | 5
1.12 | REPORT - MM - STOCK KAIN PASIF (ALL AREA) | Baim |  | 2026-03-11 | 2026-03-17 | 7 | 0% | 5
1.13 | REPORT - MM - STOCK KAIN GREY (LW 22) | Budi |  | 2026-03-18 | 2026-03-24 | 7 | 0% | 5
1.14 | REPORT - MM - REPORT RESERVASI | Budi |  | 2026-03-25 | 2026-03-31 | 7 | 0% | 5
1.15 | REPORT - MM - REPORT PEMARTAIAN | Budi |  | 2026-03-25 | 2026-03-31 | 7 | 0% | 5
1.16 | REPORT - MM - REPORT RESUME KODE PARTAI | Budi |  | 2026-04-01 | 2026-04-07 | 7 | 0% | 5
1.17 | REPORT - MM - BBK INTERN | Baim |  | 2026-04-01 | 2026-04-07 | 7 | 0% | 5
1.18 | REPORT - MM - Report Cancel Kain Masuk | Budi |  | 2026-04-08 | 2026-04-14 | 7 | 0% | 5
1.19 | REPORT - MM - Report Cancel Kain Keluar | Baim |  | 2026-04-08 | 2026-04-14 | 7 | 0% | 5
1.20 | REPORT - MM - List STK Intern dan Extern | Budi |  | 2026-04-15 | 2026-04-21 | 7 | 0% | 5
1.21 | REPORT - MM - Laporan Surat Jalan Sloc | Baim |  | 2026-04-15 | 2026-04-21 | 7 | 0% | 5
1.22 | REPORT - MM - Laporan Surat Jalan (P) | Budi |  | 2026-04-22 | 2026-04-28 | 7 | 0% | 5
1.23 | REPORT - WM - DASHBOARD LAYOUT PER BIN | Baim |  | 2026-04-22 | 2026-04-28 | 7 | 0% | 5
1.24 | REPORT - WM - MONITORING KAIN GREY | Budi |  | 2026-04-29 | 2026-05-05 | 7 | 0% | 5
1.25 | REPORT - CO - REPORT COSTING | Budi |  | 2026-04-29 | 2026-05-05 | 7 | 0% | 5
1.26 | REPORT - WM - DETAIL LIST KARTON PER RAK | Budi |  | 2026-05-06 | 2026-05-12 | 7 | 0% | 5
1.27 | REPORT - MM - STK Blank Gd. Packing | Budi |  | 2026-05-06 | 2026-05-12 | 7 | 0% | 5
2 | Interfaces |  |  |  | - |  |  | -
2.1 | INTERFACE BEA CUKAI | Billy, Budi |  | 2026-01-12 | 2026-01-16 | 5 | 0% | 5
2.2 | INTERFACE PRINT BARCODE | Billy, Baim, Budi |  | 2026-01-01 | 2026-01-10 | 10 | 0% | 6
2.3 | INTERFACE PRINT BARCODE BANYAK LIST KARTON | Billy, Baim |  | 2026-01-12 | 2026-01-16 | 5 | 0% | 5
3 | Forms |  |  |  | - |  |  | -
3.1 | Form Transfer Posting (ZSCMF001) | Billy, Budi |  | 2026-01-19 | 2026-01-22 | 4 | 0% | 4
3.2 | Form Purchase Order (ZSCMF002) | Billy, Baim |  | 2026-01-19 | 2026-01-22 | 4 | 0% | 4
3.3 | Form Good Receipt (ZSCMF003) | Baim |  | 2026-01-23 | 2026-01-28 | 6 | 0% | 4
3.4 | Form Good Issue (ZSCMF004) | Baim |  | 2026-01-29 | 2026-02-03 | 6 | 0% | 4
3.5 | Form Bukti Tanda Terima | Budi |  | 2026-01-23 | 2026-01-28 | 6 | 0% | 4
4 | Enhancement |  |  |  | - |  |  | -
4.1 | Custom field for qty in PCS at Report Stock | Billy, Budi |  | 2026-01-29 | 2026-02-03 | 6 | 0% | 4
Note on A7: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet.
Note on B7: Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on C7: Task Lead Enter the name of the Task Lead in this column.
Note on E7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on F7: End Date: The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on G7: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on H7: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on I7: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.
Note on B45: BC: $url = "https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_MATERIAL_STOCK_SRV/A_MatlStkInAcctMod"; $username = "LEUWITEX_US_SAP_COM_0947"; $password = "qyUUYn%4be7bl>m(VT/9nuW#3/342j~W9{C/88jL"; CREATE TABLE pz_material_stock ( id SERIAL PRIMARY KEY, -- optional, untuk unique identifier material VARCHAR(100) NOT NULL, plant VARCHAR(10) NOT NULL, storage_location VARCHAR(20), batch VARCHAR(50), inventory_stock_type VARCHAR(5), base_unit VARCHAR(10), warehouse_stock_qty NUMERIC(18,3) DEFAULT 0 );

## j
RICEF BY LEUWITEX ( update 17 Maret 2026 )
| Project Start Date | 2025-11-25 |  |  |  | Display Week | 1 |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8
| Project Lead | Billy | [6 empty] | 2025-11-24 | [6 empty] | 2025-12-01 | [6 empty] | 2025-12-08 | [6 empty] | 2025-12-15 | [6 empty] | 2025-12-22 | [6 empty] | 2025-12-29 | [6 empty] | 2026-01-05 | [6 empty] | 2026-01-12
 | time axis 2025-11-24 to 2026-01-18
WBS | TASK | PIC | NOTES | START | END | DAYS | % DONE | WORK DAYS | time axis 2025-11-24 to 2026-01-18
1 | SAP API development |  |  |  | - |  |  | -
1.1 | INSTALL ECLIPSE, ADOBE LIFECYCLE DI PC | Baim, Budi |  | 2025-11-26 | 2025-11-26 | 1 | 100% | 1
1.2 | BELAJAR KE SOLTIUS TENTANG SAP | Baim, Budi |  | 2025-11-27 | 2026-02-01 | 67 | 50% | 47
1.3 | INTEGRASI API SAP KE PRINT BARCODE INTERNAL | Baim, Budi |  | 2025-12-04 | 2025-12-10 | 7 | 100% | 5
1.4 | MAPPING IT INVENTORY | Baim |  | 2025-12-18 | 2025-12-23 | 6 | 100% | 4
1.5 | BELAJAR MENDAFTARKAN API SAP | Baim, Budi |  | 2025-12-30 | 2025-12-30 | 1 | 100% | 1
1.6 | MAPPING TABEL TAMBAHAN BEA CUKAI | Baim |  | 2025-12-30 | 2026-01-08 | 10 | 100% | 8
1.7 | SIT | Baim, Budi |  | 2026-01-06 | 2026-01-08 | 3 | 100% | 3
1.8 | INTEGRASI API SAP UNTUK BEA CUKAI | Baim, Budi, Jali, Star |  | 2026-01-09 | 2026-01-18 | 10 | 50% | 6
1.9 | BELAJAR MENGEDIT FORM SAP | Baim, Budi |  | 2026-01-08 | 2026-01-08 | 1 | 100% | 1
1.10 | KUT SAP BAGIAN MASTER DATA MM | Baim |  | 2026-01-15 | 2026-01-16 | 2 | 100% | 2
1.11 | KUT SAP BAGIAN MASTER DATA SD dan FICO | Budi |  | 2026-01-15 | 2026-01-16 | 2 | 100% | 2
1.12 | Modifikasi Form Invoice (Barang Bekas, Avfal, BS, Maklon, Masker) | Baim |  | 2026-01-10 | 2026-01-21 | 12 | 100% | 8
1.13 | Modifikasi Form Surat Jalan (Barang Bekas, Avfal, BS, Maklon, Masker) | Budi |  | 2026-01-10 | 2026-01-21 | 12 | 90% | 8
1.14 | Buat UI penarikan data dari API dan insert data Delivery | Baim |  | 2026-02-03 | 2026-02-04 | 2 | 100% | 2
1.15 | Buat UI penarikan data dari API dan insert data Material | Budi |  | 2026-02-03 | 2026-02-04 | 2 | 100% | 2
1.16 | Buat UI penarikan data dari API dan insert data Warehouse | Budi |  | 2026-02-05 | 2026-02-06 | 2 | 100% | 2
1.17 | Buat UI penarikan data dari API dan insert data Asset | Baim |  | 2026-02-05 | 2026-02-06 | 2 | 100% | 2
1.18 | Buat UI penarikan data dari API dan insert data Invoice | Budi |  | 2026-02-04 | 2026-02-05 | 2 | 100% | 2
1.19 | Buat UI penarikan data dari API dan insert data Supplier | Baim |  | 2026-02-05 | 2026-02-06 | 2 | 100% | 2
1.20 | Buat UI penarikan data dari API dan insert data Master Customer | Budi |  | 2026-02-07 | 2026-02-10 | 4 | 100% | 2
1.21 | Buat UI penarikan data dari API dan insert data PO | Baim |  | 2026-02-07 | 2026-02-10 | 4 | 100% | 2
1.22 | Buat UI penarikan data dari API dan insert data Material Document | Budi |  | 2026-02-11 | 2026-02-12 | 2 | 100% | 2
1.23 | Buat UI penarikan data dari API dan insert data BOM | Baim |  | 2026-02-11 | 2026-02-12 | 2 | 100% | 2
1.24 | UAT | Baim, Budi |  | 2026-02-12 | 2026-02-14 | 3 | 100% | 2
1.25 | BBK INTERN | Budi |  | 2026-02-15 | 2026-02-19 | 5 | 100% | 4
1.26 | LAPORAN SURAT JALAN (P) | Baim |  | 2026-02-15 | 2026-02-19 | 5 | 80% | 4
1.27 | DETAIL LIST KARTON PER RAK | Star |  | 2026-02-20 | 2026-02-23 | 4 | 100% | 2
1.28 | LAPORAN GUDANG PACKING LEAD TIME | Baim |  | 2026-02-20 | 2026-02-23 | 4 | 100% | 2
1.29 | MOVING HISTORY PER LIST KARTON | Star |  | 2026-02-24 | 2026-02-25 | 2 | 100% | 2
1.30 | DASHBOARD LAYOUT PER BIN | Budi |  | 2026-02-24 | 2026-02-25 | 2 | 0% | 2
1.31 | LAPORAN SURAT JALAN SLOC | Star, Baim |  | 2026-02-26 | 2026-02-27 | 2 | 80% | 2
1.32 | LIST KARTON PER KODE ORDER | Baim |  | 2026-02-26 | 2026-02-27 | 2 | 100% | 2
1.33 | LIST STK INTERN DAN EXTERN | Jali |  | 2026-02-28 | 2026-03-03 | 4 | 100% | 2
1.34 | MONITORING KAIN GREY | Budi |  | 2026-02-28 | 2026-03-03 | 4 | 0% | 2
1.35 | LAPORAN PERSEDIAAN GUDANG PACKING | Star |  | 2026-03-03 | 2026-03-05 | 3 | 100% | 3
1.36 | STOCK PER BARCODE | Jali |  | 2026-03-03 | 2026-03-05 | 3 | 100% | 3
1.37 | Buat UI penarikan data dari API dan insert data Reservasi | Jali |  | 2026-03-06 | 2026-03-07 | 2 | 100% | 1
1.38 | REPORT CANCEL KAIN KELUAR(TIDAK DIBUAT) | Budi |  | 2026-03-06 | 2026-03-09 | 4 | CANCEL | 2
1.39 | REPORT CANCEL KAIN MASUK(TIDAK DIBUAT) | Baim |  | 2026-03-06 | 2026-03-09 | 4 | CANCEL | 2
1.40 | REPORT COSTING ? | Budi |  | 2026-03-10 | 2026-03-11 | 2 | 0% | 2
1.41 | REPORT PEMARTAIAN | Budi |  | 2026-03-10 | 2026-03-11 | 2 | 0% | 2
1.42 | REPORT RESERVASI | Budi |  | 2026-03-12 | 2026-03-13 | 2 | 0% | 2
1.43 | REPORT RESUME KODE PARTAI | Budi |  | 2026-03-12 | 2026-03-13 | 2 | 0% | 2
1.44 | STK BLANK GD. PACKING | Budi |  | 2026-03-14 | 2026-03-17 | 4 | 100% | 2
1.45 | STOCK BALANCE KAIN GREY | Jali |  | 2026-03-14 | 2026-03-17 | 4 | 100% | 2
1.46 | STOCK GREY LEAD TIME PER GRADE | Budi |  | 2026-03-27 | 2026-03-30 | 4 | 100% | 2
1.47 | STOCK KAIN GREY (GRADE) | Jali |  | 2026-03-27 | 2026-03-30 | 4 | 100% | 2
1.48 | STOCK KAIN GREY (LW 22) | Budi |  | 2026-03-31 | 2026-04-01 | 2 | 100% | 2
1.49 | STOCK KAIN PASIF (ALL AREA) | Budi |  | 2026-03-31 | 2026-04-01 | 2 | 0% | 2
1.50 | STOCK LEADTIME | Jali |  | 2026-04-02 | 2026-04-03 | 2 | 100% | 2
1.51 | MOVING HISTORY PER LIST BARCODE | Star |  | 2026-04-02 | 2026-04-03 | 2 | 100% | 2
1.52 | MOVING HISTORY - GUDANG GREY | Budi |  | 2026-04-04 | 2026-04-07 | 4 | 0% | 2
1.53 | INTERFACE PRINT BARCODE BANYAK LIST KARTON | Baim |  | 2026-04-04 | 2026-04-07 | 4 | 0% | 2
1 | Report |  |  |  | - |  |  | -
1.1 | REPORT - WM - MOVING HISTORY - GUDANG GREY | Billy, Baim |  | 2026-02-04 | 2026-02-10 | 7 | 0% | 5
1.2 | REPORT - WM - STOCK PER BARCODE | Baim |  | 2026-02-11 | 2026-02-17 | 7 | 0% | 5
1.3 | REPORT - WM - LAPORAN PERSEDIAAN GUDANG PACKING | Budi |  | 2026-02-11 | 2026-02-17 | 7 | 0% | 5
1.4 | REPORT - WM - LAPORAN GUDANG PACKING LEAD TIME | Baim |  | 2026-02-18 | 2026-02-24 | 7 | 0% | 5
1.5 | REPORT - WM - LIST KARTON PER KODE ORDER | Budi |  | 2026-02-18 | 2026-02-24 | 7 | 0% | 5
1.6 | REPORT - WM - MOVING HISTORY PER BARCODE | Baim |  | 2026-02-25 | 2026-03-03 | 7 | 0% | 5
1.7 | REPORT - WM - MOVING HISTORY PER LIST KARTON | Budi |  | 2026-02-25 | 2026-03-03 | 7 | 0% | 5
1.8 | REPORT - MM - STOCK KAIN GREY (GRADE) | Billy, Budi |  | 2026-02-04 | 2026-02-10 | 7 | 0% | 5
1.9 | REPORT - MM - STOCK LEADTIME | Baim |  | 2026-03-04 | 2026-03-10 | 7 | 0% | 5
1.10 | REPORT - MM - STOCK GREY LEAD TIME PER GRADE | Budi |  | 2026-03-04 | 2026-03-10 | 7 | 0% | 5
1.11 | REPORT - MM - STOCK BALANCE KAIN GREY | Budi |  | 2026-03-11 | 2026-03-17 | 7 | 0% | 5
1.12 | REPORT - MM - STOCK KAIN PASIF (ALL AREA) | Baim |  | 2026-03-11 | 2026-03-17 | 7 | 0% | 5
1.13 | REPORT - MM - STOCK KAIN GREY (LW 22) | Budi |  | 2026-03-18 | 2026-03-24 | 7 | 0% | 5
1.14 | REPORT - MM - REPORT RESERVASI | Budi |  | 2026-03-25 | 2026-03-31 | 7 | 0% | 5
1.15 | REPORT - MM - REPORT PEMARTAIAN | Budi |  | 2026-03-25 | 2026-03-31 | 7 | 0% | 5
1.16 | REPORT - MM - REPORT RESUME KODE PARTAI | Budi |  | 2026-04-01 | 2026-04-07 | 7 | 0% | 5
1.17 | REPORT - MM - BBK INTERN | Baim |  | 2026-04-01 | 2026-04-07 | 7 | 0% | 5
1.18 | REPORT - MM - Report Cancel Kain Masuk | Budi |  | 2026-04-08 | 2026-04-14 | 7 | 0% | 5
1.19 | REPORT - MM - Report Cancel Kain Keluar | Baim |  | 2026-04-08 | 2026-04-14 | 7 | 0% | 5
1.20 | REPORT - MM - List STK Intern dan Extern | Budi |  | 2026-04-15 | 2026-04-21 | 7 | 0% | 5
1.21 | REPORT - MM - Laporan Surat Jalan Sloc | Baim |  | 2026-04-15 | 2026-04-21 | 7 | 0% | 5
1.22 | REPORT - MM - Laporan Surat Jalan (P) | Budi |  | 2026-04-22 | 2026-04-28 | 7 | 0% | 5
1.23 | REPORT - WM - DASHBOARD LAYOUT PER BIN | Baim |  | 2026-04-22 | 2026-04-28 | 7 | 0% | 5
1.24 | REPORT - WM - MONITORING KAIN GREY | Budi |  | 2026-04-29 | 2026-05-05 | 7 | 0% | 5
1.25 | REPORT - CO - REPORT COSTING | Budi |  | 2026-04-29 | 2026-05-05 | 7 | 0% | 5
1.26 | REPORT - WM - DETAIL LIST KARTON PER RAK | Budi |  | 2026-05-06 | 2026-05-12 | 7 | 0% | 5
1.27 | REPORT - MM - STK Blank Gd. Packing | Budi |  | 2026-05-06 | 2026-05-12 | 7 | 0% | 5
2 | Interfaces |  |  |  | - |  |  | -
2.1 | INTERFACE BEA CUKAI | Billy, Budi |  | 2026-01-12 | 2026-01-16 | 5 | 0% | 5
2.2 | INTERFACE PRINT BARCODE | Billy, Baim, Budi |  | 2026-01-01 | 2026-01-10 | 10 | 0% | 6
2.3 | INTERFACE PRINT BARCODE BANYAK LIST KARTON | Billy, Baim |  | 2026-01-12 | 2026-01-16 | 5 | 0% | 5
3 | Forms |  |  |  | - |  |  | -
3.1 | Form Transfer Posting (ZSCMF001) | Billy, Budi |  | 2026-01-19 | 2026-01-22 | 4 | 0% | 4
3.2 | Form Purchase Order (ZSCMF002) | Billy, Baim |  | 2026-01-19 | 2026-01-22 | 4 | 0% | 4
3.3 | Form Good Receipt (ZSCMF003) | Baim |  | 2026-01-23 | 2026-01-28 | 6 | 0% | 4
3.4 | Form Good Issue (ZSCMF004) | Baim |  | 2026-01-29 | 2026-02-03 | 6 | 0% | 4
3.5 | Form Bukti Tanda Terima | Budi |  | 2026-01-23 | 2026-01-28 | 6 | 0% | 4
4 | Enhancement |  |  |  | - |  |  | -
4.1 | Custom field for qty in PCS at Report Stock | Billy, Budi |  | 2026-01-29 | 2026-02-03 | 6 | 0% | 4
Note on A7: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet.
Note on B7: Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on C7: Task Lead Enter the name of the Task Lead in this column.
Note on E7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on F7: End Date: The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on G7: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on H7: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on I7: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.
Note on B23: BC: https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_PRODUCT_SRV//A_Product --> tabel pz_material https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_PRODUCT_SRV/A_ProductDescription --> tabel pz_material_description https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_PRODUCT_SRV/A_ProductPlant --> tabel pz_material_plant
Note on B24: $url = "https://my430621-api.s4hana.cloud.sap/sap/opu/odata4/sap/api_warehouse_order_task_2/srvd_a2x/sap/warehouseorder/0001/WarehouseTask"; $username = "LEUWITEX_US_SAP_COM_0353"; $password = "Leuwitexsapcloud@2025"; CREATE TABLE warehouse_task ( EWMWarehouse VARCHAR(20), WarehouseTask BIGINT, WarehouseTaskItem INT, WarehouseOrder BIGINT, WhseTaskCrtnUTCDateTime TIMESTAMP, WhseTaskLastChgUTCDateTime TIMESTAMP, WhseTaskConfUTCDateTime TIMESTAMP, ConfirmedByUser VARCHAR(50), WhseTaskPlannedClosingDateTime TIMESTAMP, WhseTaskGoodsReceiptDateTime TIMESTAMP, WarehouseTaskStatus CHAR(1), WarehouseProcessType VARCHAR(10), WarehouseProcessCategory INT, IsHandlingUnitWarehouseTask BOOLEAN, EWMHandlingUnitType VARCHAR(50), HomogeneousFullPalletPick VARCHAR(50), Product VARCHAR(50), Batch VARCHAR(20), BatchChangeIsNotAllowed BOOLEAN, CountryOfOrigin VARCHAR(50), ShelfLifeExpirationDate DATE, EWMStockType CHAR(1), EWMStockUsage VARCHAR(50), EWMStockOwner BIGINT, EntitledToDisposeParty BIGINT, WBSElementInternalID INT, WBSElementExternalID VARCHAR(50), SpecialStockIdfgSalesOrder VARCHAR(50), SpecialStockIdfgSalesOrderItem INT, ExecutingResource VARCHAR(50), WarehouseMovementsReason VARCHAR(50), ProductionOrder VARCHAR(50), EWMProductionSupplyArea VARCHAR(50), EWMDocumentCategory VARCHAR(10), EWMReferenceDocumentCategory VARCHAR(10), PDO VARCHAR(10), EWMWave INT, EWMWaveItem INT, EWMDelivery BIGINT, EWMDeliveryItem INT, PurchasingDocument BIGINT, PurchasingDocumentItem INT, SalesDocument VARCHAR(50), SalesDocumentItem INT, BaseUnit VARCHAR(10), EWMBaseUnitISOCode VARCHAR(10), AlternativeUnit VARCHAR(10), EWMAlternativeUnitISOCode VARCHAR(10), TargetQuantityInBaseUnit NUMERIC, TargetQuantityInAltvUnit NUMERIC, ActualQuantityInBaseUnit NUMERIC, ActualQuantityInAltvUnit NUMERIC, DifferenceQuantityInBaseUnit NUMERIC, DifferenceQuantityInAltvUnit NUMERIC, WhseTaskNetWeightUnitOfMeasure VARCHAR(10), WhseTaskNetWeight NUMERIC, WhseTaskNetVolumeUnitOfMeasure VARCHAR(10), WhseTaskNetVolume NUMERIC, SourceStorageType VARCHAR(10), SourceStorageSection VARCHAR(10), SourceStorageBin VARCHAR(20), SourceResource VARCHAR(50), DestinationStorageType VARCHAR(10), DestinationStorageSection VARCHAR(10), DestinationStorageBin VARCHAR(20), DestinationResource VARCHAR(50), ActivityArea VARCHAR(10), SourceHandlingUnit VARCHAR(50), DestinationHandlingUnit VARCHAR(50), WarehouseTaskExceptionCode VARCHAR(10), WhseTaskSortingSequenceValue INT, WarehouseOrderSequenceValue INT, WarehouseOrderActivityArea VARCHAR(10), WarehouseOrderCreationRule VARCHAR(10), WarehouseOrderQueue VARCHAR(50), WarehouseActivityType VARCHAR(10), EWMConsolidationGroup BIGINT, EWMWarehouseTaskPriority INT, CreatedByUser VARCHAR(50), EWMRoute VARCHAR(50), EWMWaveCategory VARCHAR(50), EWMCanceledWarehouseTask INT, SerialNumberRequiredLevel VARCHAR(10) );
Note on B25: BC: https://my430621-api.s4hana.cloud.sap/sap/opu/odata4/sap/api_fixedasset/srvd_a2x/sap/fixedasset/0001/FixedAsset Username : LEUWITEX_US_SAP_COM_0A93 Password : Leuwitexsapcloud@2025" tabel : pz_fixed_asset https://my430621-api.s4hana.cloud.sap/sap/opu/odata4/sap/api_fixedasset/srvd_a2x/sap/fixedasset/0001/FixedAssetLedger Username : LEUWITEX_US_SAP_COM_0A93 Password : Leuwitexsapcloud@2025" tabel : pz_fixed_asset_ledger
Note on B26: BC: https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BILLING_DOCUMENT_SRV/A_BillingDocument Comm User : LEUWITEX_US_SAP_COM_0120 password user comm: Leuwitexsapcloud@2025 tabel : pz_billing_document https://my430621-api.s4hana.cloud.sap/sap/opu/odata4/sap/api_billingdocument/srvd_a2x/sap/billingdocument/0001/BillingDocumentItem Comm User : LEUWITEX_US_SAP_COM_0120 password user comm: Leuwitexsapcloud@2025 tabel : pz_billing_document_item https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_SALES_ORDER_SRV/A_SalesOrder Comm User : LEUWITEX_US_SAP_COM_0109 password user comm: Leuwitexsapcloud@2025 tabel : pz_sales_order
Note on B27: https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BUSINESS_PARTNER/A_Supplier Username : LEUWITEX_US_SAP_COM_0008 SupplierFullName Bechtle AG Kriek street Password : \W+M)hw&kj]WHnSJ>UmhdB(f56N>\Zk9caxMY=5L CREATE TABLE pz_supplier ( supplier VARCHAR(20) PRIMARY KEY, supplier_full_name VARCHAR(100), created_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP, updated_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP ); https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BUSINESS_PARTNER/A_AddressEmailAddress Username : LEUWITEX_US_SAP_COM_0008 Password : \W+M)hw&kj]WHnSJ>UmhdB(f56N>\Zk9caxMY=5L CREATE TABLE pz_address_email_address ( email_address VARCHAR(100) NOT NULL, person VARCHAR(50), address_id VARCHAR(50), created_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP, updated_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP, PRIMARY KEY (email_address) ); https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BUSINESS_PARTNER/A_BusinessPartnerAddress Username : LEUWITEX_US_SAP_COM_0008 Password : \W+M)hw&kj]WHnSJ>UmhdB(f56N>\Zk9caxMY=5L CREATE TABLE pz_business_partner_address ( country VARCHAR(50), postal_code VARCHAR(20), region VARCHAR(100), district VARCHAR(100), business_partner VARCHAR(20), address_id VARCHAR(50), created_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP, updated_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP ); https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BUSINESS_PARTNER/A_AddressHomePageURL Username : LEUWITEX_US_SAP_COM_0008 Password : \W+M)hw&kj]WHnSJ>UmhdB(f56N>\Zk9caxMY=5L CREATE TABLE pz_address_home_page_url ( website_url VARCHAR(200) NOT NULL, address_id VARCHAR(50), -- Audit columns created_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP, updated_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP, PRIMARY KEY (website_url) ); https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BUSINESS_PARTNER/A_AddressPhoneNumber Username : LEUWITEX_US_SAP_COM_0008 Password : \W+M)hw&kj]WHnSJ>UmhdB(f56N>\Zk9caxMY=5L CREATE TABLE pz_address_phone_number ( phone_number VARCHAR(50) NOT NULL, address_id VARCHAR(50), created_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP, updated_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP ); https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BUSINESS_PARTNER/A_BuPaIdentification Username : LEUWITEX_US_SAP_COM_0008 Password : \W+M)hw&kj]WHnSJ>UmhdB(f56N>\Zk9caxMY=5L CREATE TABLE pz_bu_pa_identification ( npwp_vendor VARCHAR(30) NOT NULL, business_partner VARCHAR(20), created_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP, updated_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP ); https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BUSINESS_PARTNER/A_AddressFaxNumber Username : LEUWITEX_US_SAP_COM_0008 Password : \W+M)hw&kj]WHnSJ>UmhdB(f56N>\Zk9caxMY=5L CREATE TABLE pz_bu_address_fax_number ( fax_number VARCHAR(50) NOT NULL, address_id VARCHAR(50), created_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP, updated_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP );
Note on B28: https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BUSINESS_PARTNER/A_BusinessPartnerAddress UserName : LEUWITEX_US_SAP_COM_0008 Password : \W+M)hw&kj]WHnSJ>UmhdB(f56N>\Zk9caxMY=5L tabel : pz_business_partner_address https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BUSINESS_PARTNER/A_Customer UserName : LEUWITEX_US_SAP_COM_0008 Password : \W+M)hw&kj]WHnSJ>UmhdB(f56N>\Zk9caxMY=5L tabel : pz_customer https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BUSINESS_PARTNER/A_Customer('9200000010')/to_CustomerSalesArea UserName : LEUWITEX_US_SAP_COM_0008 Password : \W+M)hw&kj]WHnSJ>UmhdB(f56N>\Zk9caxMY=5L tabel : pz_customer_sales_area https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BUSINESS_PARTNER/A_BusinessPartnerTaxNumber UserName : LEUWITEX_US_SAP_COM_0008 Password : \W+M)hw&kj]WHnSJ>UmhdB(f56N>\Zk9caxMY=5L tabel : pz_business_partner_tax_number https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BUSINESS_PARTNER/A_CustSalesPartnerFunc UserName : LEUWITEX_US_SAP_COM_0008 Password : \W+M)hw&kj]WHnSJ>UmhdB(f56N>\Zk9caxMY=5L tabel : pz_cust_sales_partner_func
Note on B29: BC: https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BILL_OF_MATERIAL_SRV;v=0002/MaterialBOM Comm User : LEUWITEX_US_SAP_COM_0105 password user comm: Leuwitexsapcloud@2025 tabel : pz_material_bom https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BILL_OF_MATERIAL_SRV;v=0002/MaterialBOMItem Comm User : LEUWITEX_US_SAP_COM_0105 password user comm: Leuwitexsapcloud@2025 tabel : pz_material_bom_item
Note on B30: https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_MATERIAL_DOCUMENT_SRV/A_MaterialDocumentHeader Username : LEUWITEX_US_SAP_COM_0108 Password : Leuwitexsapcloud@2025 table pz_material_document_header https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_MATERIAL_DOCUMENT_SRV//A_MaterialDocumentItem Username : LEUWITEX_US_SAP_COM_0108 Password : Leuwitexsapcloud@2025 table pz_material_document_item
Note on B31: BC: https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BILL_OF_MATERIAL_SRV;v=0002/MaterialBOM Comm User : LEUWITEX_US_SAP_COM_0105 password user comm: Leuwitexsapcloud@2025 tabel : pz_material_bom https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BILL_OF_MATERIAL_SRV;v=0002/MaterialBOMItem Comm User : LEUWITEX_US_SAP_COM_0105 password user comm: Leuwitexsapcloud@2025 tabel : pz_material_bom_item
Note on B32: BC: https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BILL_OF_MATERIAL_SRV;v=0002/MaterialBOM Comm User : LEUWITEX_US_SAP_COM_0105 password user comm: Leuwitexsapcloud@2025 tabel : pz_material_bom https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BILL_OF_MATERIAL_SRV;v=0002/MaterialBOMItem Comm User : LEUWITEX_US_SAP_COM_0105 password user comm: Leuwitexsapcloud@2025 tabel : pz_material_bom_item
Note on B45: BC: $url = "https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_MATERIAL_STOCK_SRV/A_MatlStkInAcctMod"; $username = "LEUWITEX_US_SAP_COM_0947"; $password = "qyUUYn%4be7bl>m(VT/9nuW#3/342j~W9{C/88jL"; CREATE TABLE pz_material_stock ( id SERIAL PRIMARY KEY, -- optional, untuk unique identifier material VARCHAR(100) NOT NULL, plant VARCHAR(10) NOT NULL, storage_location VARCHAR(20), batch VARCHAR(50), inventory_stock_type VARCHAR(5), base_unit VARCHAR(10), warehouse_stock_qty NUMERIC(18,3) DEFAULT 0 );

## i
RICEF BY LEUWITEX ( update 3 Maret 2026 )
| Project Start Date | 2025-11-25 |  |  |  | Display Week | 1 |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8
| Project Lead | Billy | [6 empty] | 2025-11-24 | [6 empty] | 2025-12-01 | [6 empty] | 2025-12-08 | [6 empty] | 2025-12-15 | [6 empty] | 2025-12-22 | [6 empty] | 2025-12-29 | [6 empty] | 2026-01-05 | [6 empty] | 2026-01-12
 | time axis 2025-11-24 to 2026-01-18
WBS | TASK | PIC | NOTES | START | END | DAYS | % DONE | WORK DAYS | time axis 2025-11-24 to 2026-01-18
1 | SAP API development |  |  |  | - |  |  | -
1.1 | INSTALL ECLIPSE, ADOBE LIFECYCLE DI PC | Baim, Budi |  | 2025-11-26 | 2025-11-26 | 1 | 100% | 1
1.2 | BELAJAR KE SOLTIUS TENTANG SAP | Baim, Budi |  | 2025-11-27 | 2026-02-01 | 67 | 40% | 47
1.3 | INTEGRASI API SAP KE PRINT BARCODE INTERNAL | Baim, Budi |  | 2025-12-04 | 2025-12-10 | 7 | 100% | 5
1.4 | MAPPING IT INVENTORY | Baim |  | 2025-12-18 | 2025-12-23 | 6 | 100% | 4
1.5 | BELAJAR MENDAFTARKAN API SAP | Baim, Budi |  | 2025-12-30 | 2025-12-30 | 1 | 100% | 1
1.6 | MAPPING TABEL TAMBAHAN BEA CUKAI | Baim |  | 2025-12-30 | 2026-01-08 | 10 | 100% | 8
1.7 | SIT | Baim, Budi |  | 2026-01-06 | 2026-01-08 | 3 | 100% | 3
1.8 | INTEGRASI API SAP UNTUK BEA CUKAI | Baim, Budi, Jali, Star |  | 2026-01-09 | 2026-01-18 | 10 | 50% | 6
1.9 | BELAJAR MENGEDIT FORM SAP | Baim, Budi |  | 2026-01-08 | 2026-01-08 | 1 | 100% | 1
1.10 | KUT SAP BAGIAN MASTER DATA MM | Baim |  | 2026-01-15 | 2026-01-16 | 2 | 100% | 2
1.11 | KUT SAP BAGIAN MASTER DATA SD dan FICO | Budi |  | 2026-01-15 | 2026-01-16 | 2 | 100% | 2
1.12 | Modifikasi Form Invoice (Barang Bekas, Avfal, BS, Maklon, Masker) | Baim |  | 2026-01-10 | 2026-01-21 | 12 | 100% | 8
1.13 | Modifikasi Form Surat Jalan (Barang Bekas, Avfal, BS, Maklon, Masker) | Budi |  | 2026-01-10 | 2026-01-21 | 12 | 90% | 8
1.14 | Buat UI penarikan data dari API dan insert data Delivery | Baim | Sudah Tenant | 2026-02-03 | 2026-02-04 | 2 | 100% | 2
1.15 | Buat UI penarikan data dari API dan insert data Material | Budi |  | 2026-02-03 | 2026-02-04 | 2 | 100% | 2
1.16 | Buat UI penarikan data dari API dan insert data Warehouse | Budi |  | 2026-02-05 | 2026-02-06 | 2 | 100% | 2
1.17 | Buat UI penarikan data dari API dan insert data Asset | Baim | Sudah Tenant | 2026-02-05 | 2026-02-06 | 2 | 100% | 2
1.18 | Buat UI penarikan data dari API dan insert data Invoice | Budi |  | 2026-02-04 | 2026-02-05 | 2 | 100% | 2
1.19 | Buat UI penarikan data dari API dan insert data Supplier | Baim |  | 2026-02-05 | 2026-02-06 | 2 | 100% | 2
1.20 | Buat UI penarikan data dari API dan insert data Master Customer | Budi |  | 2026-02-07 | 2026-02-10 | 4 | 100% | 2
1.21 | Buat UI penarikan data dari API dan insert data PO | Baim | Sudah Tenant | 2026-02-07 | 2026-02-10 | 4 | 100% | 2
1.22 | Buat UI penarikan data dari API dan insert data Material Document | Budi |  | 2026-02-11 | 2026-02-12 | 2 | 100% | 2
1.23 | Buat UI penarikan data dari API dan insert data BOM | Baim | Sudah Tenant | 2026-02-11 | 2026-02-12 | 2 | 100% | 2
1.24 | UAT | Baim, Budi |  | 2026-02-12 | 2026-02-14 | 3 | 100% | 2
1.25 | BBK INTERN | Budi |  | 2026-02-15 | 2026-02-19 | 5 | 0% | 4
1.26 | LAPORAN SURAT JALAN (P) | Baim |  | 2026-02-15 | 2026-02-19 | 5 | 80% | 4
1.27 | DETAIL LIST KARTON PER RAK | Star |  | 2026-02-20 | 2026-02-23 | 4 | 0% | 2
1.28 | LAPORAN GUDANG PACKING LEAD TIME | Baim |  | 2026-02-20 | 2026-02-23 | 4 | 50% | 2
1.29 | MOVING HISTORY PER LIST KARTON | Star |  | 2026-02-24 | 2026-02-25 | 2 | 0% | 2
1.30 | DASHBOARD LAYOUT PER BIN | Jali |  | 2026-02-24 | 2026-02-25 | 2 | 0% | 2
1.31 | LAPORAN SURAT JALAN SLOC | Baim | Baim | 2026-02-26 | 2026-02-27 | 2 | 0% | 2
1.32 | LIST KARTON PER KODE ORDER | Baim |  | 2026-02-26 | 2026-02-27 | 2 | 50% | 2
1.33 | LIST STK INTERN DAN EXTERN | Jali |  | 2026-02-28 | 2026-03-03 | 4 | 100% | 2
1.34 | MONITORING KAIN GREY | Jali |  | 2026-02-28 | 2026-03-03 | 4 | 0% | 2
1.35 | LAPORAN PERSEDIAAN GUDANG PACKING | Star |  | 2026-03-03 | 2026-03-05 | 3 | 0% | 3
1.36 | STOCK PER BARCODE | Jali |  | 2026-03-03 | 2026-03-05 | 3 | 0% | 3
1.37 | Buat UI penarikan data dari API dan insert data Reservasi | Jali |  | 2026-03-06 | 2026-03-07 | 2 | 0% | 1
1.38 | REPORT CANCEL KAIN KELUAR | Budi |  | 2026-03-06 | 2026-03-09 | 4 | 0% | 2
1.39 | REPORT CANCEL KAIN MASUK | Baim |  | 2026-03-06 | 2026-03-09 | 4 | 0% | 2
1.40 | REPORT COSTING ? | Budi |  | 2026-03-10 | 2026-03-11 | 2 | 0% | 2
1.41 | REPORT PEMARTAIAN | Jali |  | 2026-03-10 | 2026-03-11 | 2 | 0% | 2
1.42 | REPORT RESERVASI | Budi |  | 2026-03-12 | 2026-03-13 | 2 | 0% | 2
1.43 | REPORT RESUME KODE PARTAI | Jali |  | 2026-03-12 | 2026-03-13 | 2 | 0% | 2
1.44 | STK BLANK GD. PACKING | Budi |  | 2026-03-14 | 2026-03-17 | 4 | 0% | 2
1.45 | STOCK BALANCE KAIN GREY | Jali |  | 2026-03-14 | 2026-03-17 | 4 | 0% | 2
1.46 | STOCK GREY LEAD TIME PER GRADE | Budi |  | 2026-03-27 | 2026-03-30 | 4 | 0% | 2
1.47 | STOCK KAIN GREY (GRADE) | Jali |  | 2026-03-27 | 2026-03-30 | 4 | 0% | 2
1.48 | STOCK KAIN GREY (LW 22) | Budi |  | 2026-03-31 | 2026-04-01 | 2 | 0% | 2
1.49 | STOCK KAIN PASIF (ALL AREA) | Jali |  | 2026-03-31 | 2026-04-01 | 2 | 0% | 2
1.50 | STOCK LEADTIME | Jali |  | 2026-04-02 | 2026-04-03 | 2 | 0% | 2
1.51 | MOVING HISTORY PER LIST BARCODE | Star |  | 2026-04-02 | 2026-04-03 | 2 | 0% | 2
1.52 | MOVING HISTORY - GUDANG GREY | Budi |  | 2026-04-04 | 2026-04-07 | 4 | 0% | 2
1 | Report |  |  |  | - |  |  | -
1.1 | REPORT - WM - MOVING HISTORY - GUDANG GREY | Billy, Baim |  | 2026-02-04 | 2026-02-10 | 7 | 0% | 5
1.2 | REPORT - WM - STOCK PER BARCODE | Baim |  | 2026-02-11 | 2026-02-17 | 7 | 0% | 5
1.3 | REPORT - WM - LAPORAN PERSEDIAAN GUDANG PACKING | Budi |  | 2026-02-11 | 2026-02-17 | 7 | 0% | 5
1.4 | REPORT - WM - LAPORAN GUDANG PACKING LEAD TIME | Baim |  | 2026-02-18 | 2026-02-24 | 7 | 0% | 5
1.5 | REPORT - WM - LIST KARTON PER KODE ORDER | Budi |  | 2026-02-18 | 2026-02-24 | 7 | 0% | 5
1.6 | REPORT - WM - MOVING HISTORY PER BARCODE | Baim |  | 2026-02-25 | 2026-03-03 | 7 | 0% | 5
1.7 | REPORT - WM - MOVING HISTORY PER LIST KARTON | Budi |  | 2026-02-25 | 2026-03-03 | 7 | 0% | 5
1.8 | REPORT - MM - STOCK KAIN GREY (GRADE) | Billy, Budi |  | 2026-02-04 | 2026-02-10 | 7 | 0% | 5
1.9 | REPORT - MM - STOCK LEADTIME | Baim |  | 2026-03-04 | 2026-03-10 | 7 | 0% | 5
1.10 | REPORT - MM - STOCK GREY LEAD TIME PER GRADE | Budi |  | 2026-03-04 | 2026-03-10 | 7 | 0% | 5
1.11 | REPORT - MM - STOCK BALANCE KAIN GREY | Budi |  | 2026-03-11 | 2026-03-17 | 7 | 0% | 5
1.12 | REPORT - MM - STOCK KAIN PASIF (ALL AREA) | Baim |  | 2026-03-11 | 2026-03-17 | 7 | 0% | 5
1.13 | REPORT - MM - STOCK KAIN GREY (LW 22) | Budi |  | 2026-03-18 | 2026-03-24 | 7 | 0% | 5
1.14 | REPORT - MM - REPORT RESERVASI | Budi |  | 2026-03-25 | 2026-03-31 | 7 | 0% | 5
1.15 | REPORT - MM - REPORT PEMARTAIAN | Budi |  | 2026-03-25 | 2026-03-31 | 7 | 0% | 5
1.16 | REPORT - MM - REPORT RESUME KODE PARTAI | Budi |  | 2026-04-01 | 2026-04-07 | 7 | 0% | 5
1.17 | REPORT - MM - BBK INTERN | Baim |  | 2026-04-01 | 2026-04-07 | 7 | 0% | 5
1.18 | REPORT - MM - Report Cancel Kain Masuk | Budi |  | 2026-04-08 | 2026-04-14 | 7 | 0% | 5
1.19 | REPORT - MM - Report Cancel Kain Keluar | Baim |  | 2026-04-08 | 2026-04-14 | 7 | 0% | 5
1.20 | REPORT - MM - List STK Intern dan Extern | Budi |  | 2026-04-15 | 2026-04-21 | 7 | 0% | 5
1.21 | REPORT - MM - Laporan Surat Jalan Sloc | Baim |  | 2026-04-15 | 2026-04-21 | 7 | 0% | 5
1.22 | REPORT - MM - Laporan Surat Jalan (P) | Budi |  | 2026-04-22 | 2026-04-28 | 7 | 0% | 5
1.23 | REPORT - WM - DASHBOARD LAYOUT PER BIN | Baim |  | 2026-04-22 | 2026-04-28 | 7 | 0% | 5
1.24 | REPORT - WM - MONITORING KAIN GREY | Budi |  | 2026-04-29 | 2026-05-05 | 7 | 0% | 5
1.25 | REPORT - CO - REPORT COSTING | Budi |  | 2026-04-29 | 2026-05-05 | 7 | 0% | 5
1.26 | REPORT - WM - DETAIL LIST KARTON PER RAK | Budi |  | 2026-05-06 | 2026-05-12 | 7 | 0% | 5
1.27 | REPORT - MM - STK Blank Gd. Packing | Budi |  | 2026-05-06 | 2026-05-12 | 7 | 0% | 5
2 | Interfaces |  |  |  | - |  |  | -
2.1 | INTERFACE BEA CUKAI | Billy, Budi |  | 2026-01-12 | 2026-01-16 | 5 | 0% | 5
2.2 | INTERFACE PRINT BARCODE | Billy, Baim, Budi |  | 2026-01-01 | 2026-01-10 | 10 | 0% | 6
2.3 | INTERFACE PRINT BARCODE BANYAK LIST KARTON | Billy, Baim |  | 2026-01-12 | 2026-01-16 | 5 | 0% | 5
3 | Forms |  |  |  | - |  |  | -
3.1 | Form Transfer Posting (ZSCMF001) | Billy, Budi |  | 2026-01-19 | 2026-01-22 | 4 | 0% | 4
3.2 | Form Purchase Order (ZSCMF002) | Billy, Baim |  | 2026-01-19 | 2026-01-22 | 4 | 0% | 4
3.3 | Form Good Receipt (ZSCMF003) | Baim |  | 2026-01-23 | 2026-01-28 | 6 | 0% | 4
3.4 | Form Good Issue (ZSCMF004) | Baim |  | 2026-01-29 | 2026-02-03 | 6 | 0% | 4
3.5 | Form Bukti Tanda Terima | Budi |  | 2026-01-23 | 2026-01-28 | 6 | 0% | 4
4 | Enhancement |  |  |  | - |  |  | -
4.1 | Custom field for qty in PCS at Report Stock | Billy, Budi |  | 2026-01-29 | 2026-02-03 | 6 | 0% | 4
Note on A7: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet.
Note on B7: Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on C7: Task Lead Enter the name of the Task Lead in this column.
Note on E7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on F7: End Date: The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on G7: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on H7: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on I7: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.
Note on B23: BC: https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_PRODUCT_SRV//A_Product --> tabel pz_material https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_PRODUCT_SRV/A_ProductDescription --> tabel pz_material_description https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_PRODUCT_SRV/A_ProductPlant --> tabel pz_material_plant
Note on B24: $url = "https://my430621-api.s4hana.cloud.sap/sap/opu/odata4/sap/api_warehouse_order_task_2/srvd_a2x/sap/warehouseorder/0001/WarehouseTask"; $username = "LEUWITEX_US_SAP_COM_0353"; $password = "Leuwitexsapcloud@2025"; CREATE TABLE warehouse_task ( EWMWarehouse VARCHAR(20), WarehouseTask BIGINT, WarehouseTaskItem INT, WarehouseOrder BIGINT, WhseTaskCrtnUTCDateTime TIMESTAMP, WhseTaskLastChgUTCDateTime TIMESTAMP, WhseTaskConfUTCDateTime TIMESTAMP, ConfirmedByUser VARCHAR(50), WhseTaskPlannedClosingDateTime TIMESTAMP, WhseTaskGoodsReceiptDateTime TIMESTAMP, WarehouseTaskStatus CHAR(1), WarehouseProcessType VARCHAR(10), WarehouseProcessCategory INT, IsHandlingUnitWarehouseTask BOOLEAN, EWMHandlingUnitType VARCHAR(50), HomogeneousFullPalletPick VARCHAR(50), Product VARCHAR(50), Batch VARCHAR(20), BatchChangeIsNotAllowed BOOLEAN, CountryOfOrigin VARCHAR(50), ShelfLifeExpirationDate DATE, EWMStockType CHAR(1), EWMStockUsage VARCHAR(50), EWMStockOwner BIGINT, EntitledToDisposeParty BIGINT, WBSElementInternalID INT, WBSElementExternalID VARCHAR(50), SpecialStockIdfgSalesOrder VARCHAR(50), SpecialStockIdfgSalesOrderItem INT, ExecutingResource VARCHAR(50), WarehouseMovementsReason VARCHAR(50), ProductionOrder VARCHAR(50), EWMProductionSupplyArea VARCHAR(50), EWMDocumentCategory VARCHAR(10), EWMReferenceDocumentCategory VARCHAR(10), PDO VARCHAR(10), EWMWave INT, EWMWaveItem INT, EWMDelivery BIGINT, EWMDeliveryItem INT, PurchasingDocument BIGINT, PurchasingDocumentItem INT, SalesDocument VARCHAR(50), SalesDocumentItem INT, BaseUnit VARCHAR(10), EWMBaseUnitISOCode VARCHAR(10), AlternativeUnit VARCHAR(10), EWMAlternativeUnitISOCode VARCHAR(10), TargetQuantityInBaseUnit NUMERIC, TargetQuantityInAltvUnit NUMERIC, ActualQuantityInBaseUnit NUMERIC, ActualQuantityInAltvUnit NUMERIC, DifferenceQuantityInBaseUnit NUMERIC, DifferenceQuantityInAltvUnit NUMERIC, WhseTaskNetWeightUnitOfMeasure VARCHAR(10), WhseTaskNetWeight NUMERIC, WhseTaskNetVolumeUnitOfMeasure VARCHAR(10), WhseTaskNetVolume NUMERIC, SourceStorageType VARCHAR(10), SourceStorageSection VARCHAR(10), SourceStorageBin VARCHAR(20), SourceResource VARCHAR(50), DestinationStorageType VARCHAR(10), DestinationStorageSection VARCHAR(10), DestinationStorageBin VARCHAR(20), DestinationResource VARCHAR(50), ActivityArea VARCHAR(10), SourceHandlingUnit VARCHAR(50), DestinationHandlingUnit VARCHAR(50), WarehouseTaskExceptionCode VARCHAR(10), WhseTaskSortingSequenceValue INT, WarehouseOrderSequenceValue INT, WarehouseOrderActivityArea VARCHAR(10), WarehouseOrderCreationRule VARCHAR(10), WarehouseOrderQueue VARCHAR(50), WarehouseActivityType VARCHAR(10), EWMConsolidationGroup BIGINT, EWMWarehouseTaskPriority INT, CreatedByUser VARCHAR(50), EWMRoute VARCHAR(50), EWMWaveCategory VARCHAR(50), EWMCanceledWarehouseTask INT, SerialNumberRequiredLevel VARCHAR(10) );
Note on B25: BC: https://my430621-api.s4hana.cloud.sap/sap/opu/odata4/sap/api_fixedasset/srvd_a2x/sap/fixedasset/0001/FixedAsset Username : LEUWITEX_US_SAP_COM_0A93 Password : Leuwitexsapcloud@2025" tabel : pz_fixed_asset https://my430621-api.s4hana.cloud.sap/sap/opu/odata4/sap/api_fixedasset/srvd_a2x/sap/fixedasset/0001/FixedAssetLedger Username : LEUWITEX_US_SAP_COM_0A93 Password : Leuwitexsapcloud@2025" tabel : pz_fixed_asset_ledger
Note on B26: BC: https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BILLING_DOCUMENT_SRV/A_BillingDocument Comm User : LEUWITEX_US_SAP_COM_0120 password user comm: Leuwitexsapcloud@2025 tabel : pz_billing_document https://my430621-api.s4hana.cloud.sap/sap/opu/odata4/sap/api_billingdocument/srvd_a2x/sap/billingdocument/0001/BillingDocumentItem Comm User : LEUWITEX_US_SAP_COM_0120 password user comm: Leuwitexsapcloud@2025 tabel : pz_billing_document_item https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_SALES_ORDER_SRV/A_SalesOrder Comm User : LEUWITEX_US_SAP_COM_0109 password user comm: Leuwitexsapcloud@2025 tabel : pz_sales_order
Note on B27: https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BUSINESS_PARTNER/A_Supplier Username : LEUWITEX_US_SAP_COM_0008 SupplierFullName Bechtle AG Kriek street Password : \W+M)hw&kj]WHnSJ>UmhdB(f56N>\Zk9caxMY=5L CREATE TABLE pz_supplier ( supplier VARCHAR(20) PRIMARY KEY, supplier_full_name VARCHAR(100), created_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP, updated_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP ); https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BUSINESS_PARTNER/A_AddressEmailAddress Username : LEUWITEX_US_SAP_COM_0008 Password : \W+M)hw&kj]WHnSJ>UmhdB(f56N>\Zk9caxMY=5L CREATE TABLE pz_address_email_address ( email_address VARCHAR(100) NOT NULL, person VARCHAR(50), address_id VARCHAR(50), created_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP, updated_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP, PRIMARY KEY (email_address) ); https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BUSINESS_PARTNER/A_BusinessPartnerAddress Username : LEUWITEX_US_SAP_COM_0008 Password : \W+M)hw&kj]WHnSJ>UmhdB(f56N>\Zk9caxMY=5L CREATE TABLE pz_business_partner_address ( country VARCHAR(50), postal_code VARCHAR(20), region VARCHAR(100), district VARCHAR(100), business_partner VARCHAR(20), address_id VARCHAR(50), created_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP, updated_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP ); https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BUSINESS_PARTNER/A_AddressHomePageURL Username : LEUWITEX_US_SAP_COM_0008 Password : \W+M)hw&kj]WHnSJ>UmhdB(f56N>\Zk9caxMY=5L CREATE TABLE pz_address_home_page_url ( website_url VARCHAR(200) NOT NULL, address_id VARCHAR(50), -- Audit columns created_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP, updated_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP, PRIMARY KEY (website_url) ); https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BUSINESS_PARTNER/A_AddressPhoneNumber Username : LEUWITEX_US_SAP_COM_0008 Password : \W+M)hw&kj]WHnSJ>UmhdB(f56N>\Zk9caxMY=5L CREATE TABLE pz_address_phone_number ( phone_number VARCHAR(50) NOT NULL, address_id VARCHAR(50), created_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP, updated_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP ); https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BUSINESS_PARTNER/A_BuPaIdentification Username : LEUWITEX_US_SAP_COM_0008 Password : \W+M)hw&kj]WHnSJ>UmhdB(f56N>\Zk9caxMY=5L CREATE TABLE pz_bu_pa_identification ( npwp_vendor VARCHAR(30) NOT NULL, business_partner VARCHAR(20), created_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP, updated_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP ); https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BUSINESS_PARTNER/A_AddressFaxNumber Username : LEUWITEX_US_SAP_COM_0008 Password : \W+M)hw&kj]WHnSJ>UmhdB(f56N>\Zk9caxMY=5L CREATE TABLE pz_bu_address_fax_number ( fax_number VARCHAR(50) NOT NULL, address_id VARCHAR(50), created_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP, updated_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP );
Note on B28: https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BUSINESS_PARTNER/A_BusinessPartnerAddress UserName : LEUWITEX_US_SAP_COM_0008 Password : \W+M)hw&kj]WHnSJ>UmhdB(f56N>\Zk9caxMY=5L tabel : pz_business_partner_address https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BUSINESS_PARTNER/A_Customer UserName : LEUWITEX_US_SAP_COM_0008 Password : \W+M)hw&kj]WHnSJ>UmhdB(f56N>\Zk9caxMY=5L tabel : pz_customer https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BUSINESS_PARTNER/A_Customer('9200000010')/to_CustomerSalesArea UserName : LEUWITEX_US_SAP_COM_0008 Password : \W+M)hw&kj]WHnSJ>UmhdB(f56N>\Zk9caxMY=5L tabel : pz_customer_sales_area https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BUSINESS_PARTNER/A_BusinessPartnerTaxNumber UserName : LEUWITEX_US_SAP_COM_0008 Password : \W+M)hw&kj]WHnSJ>UmhdB(f56N>\Zk9caxMY=5L tabel : pz_business_partner_tax_number https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BUSINESS_PARTNER/A_CustSalesPartnerFunc UserName : LEUWITEX_US_SAP_COM_0008 Password : \W+M)hw&kj]WHnSJ>UmhdB(f56N>\Zk9caxMY=5L tabel : pz_cust_sales_partner_func
Note on B29: BC: https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BILL_OF_MATERIAL_SRV;v=0002/MaterialBOM Comm User : LEUWITEX_US_SAP_COM_0105 password user comm: Leuwitexsapcloud@2025 tabel : pz_material_bom https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BILL_OF_MATERIAL_SRV;v=0002/MaterialBOMItem Comm User : LEUWITEX_US_SAP_COM_0105 password user comm: Leuwitexsapcloud@2025 tabel : pz_material_bom_item
Note on B30: https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_MATERIAL_DOCUMENT_SRV/A_MaterialDocumentHeader Username : LEUWITEX_US_SAP_COM_0108 Password : Leuwitexsapcloud@2025 table pz_material_document_header https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_MATERIAL_DOCUMENT_SRV//A_MaterialDocumentItem Username : LEUWITEX_US_SAP_COM_0108 Password : Leuwitexsapcloud@2025 table pz_material_document_item
Note on B31: BC: https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BILL_OF_MATERIAL_SRV;v=0002/MaterialBOM Comm User : LEUWITEX_US_SAP_COM_0105 password user comm: Leuwitexsapcloud@2025 tabel : pz_material_bom https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BILL_OF_MATERIAL_SRV;v=0002/MaterialBOMItem Comm User : LEUWITEX_US_SAP_COM_0105 password user comm: Leuwitexsapcloud@2025 tabel : pz_material_bom_item
Note on B32: BC: https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BILL_OF_MATERIAL_SRV;v=0002/MaterialBOM Comm User : LEUWITEX_US_SAP_COM_0105 password user comm: Leuwitexsapcloud@2025 tabel : pz_material_bom https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BILL_OF_MATERIAL_SRV;v=0002/MaterialBOMItem Comm User : LEUWITEX_US_SAP_COM_0105 password user comm: Leuwitexsapcloud@2025 tabel : pz_material_bom_item
Note on B45: BC: $url = "https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_MATERIAL_STOCK_SRV/A_MatlStkInAcctMod"; $username = "LEUWITEX_US_SAP_COM_0947"; $password = "qyUUYn%4be7bl>m(VT/9nuW#3/342j~W9{C/88jL"; CREATE TABLE pz_material_stock ( id SERIAL PRIMARY KEY, -- optional, untuk unique identifier material VARCHAR(100) NOT NULL, plant VARCHAR(10) NOT NULL, storage_location VARCHAR(20), batch VARCHAR(50), inventory_stock_type VARCHAR(5), base_unit VARCHAR(10), warehouse_stock_qty NUMERIC(18,3) DEFAULT 0 );

## h
RICEF BY LEUWITEX ( update 2 Maret 2026 )
| Project Start Date | 2025-11-25 |  |  |  | Display Week | 1 |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8
| Project Lead | Billy | [6 empty] | 2025-11-24 | [6 empty] | 2025-12-01 | [6 empty] | 2025-12-08 | [6 empty] | 2025-12-15 | [6 empty] | 2025-12-22 | [6 empty] | 2025-12-29 | [6 empty] | 2026-01-05 | [6 empty] | 2026-01-12
 | time axis 2025-11-24 to 2026-01-18
WBS | TASK | PIC | NOTES | START | END | DAYS | % DONE | WORK DAYS | time axis 2025-11-24 to 2026-01-18
1 | SAP API development |  |  |  | - |  |  | -
1.1 | INSTALL ECLIPSE, ADOBE LIFECYCLE DI PC | Baim, Budi |  | 2025-11-26 | 2025-11-26 | 1 | 100% | 1
1.2 | BELAJAR KE SOLTIUS TENTANG SAP | Baim, Budi |  | 2025-11-27 | 2026-02-01 | 67 | 40% | 47
1.3 | INTEGRASI API SAP KE PRINT BARCODE INTERNAL | Baim, Budi |  | 2025-12-04 | 2025-12-10 | 7 | 100% | 5
1.4 | MAPPING IT INVENTORY | Baim |  | 2025-12-18 | 2025-12-23 | 6 | 100% | 4
1.5 | BELAJAR MENDAFTARKAN API SAP | Baim, Budi |  | 2025-12-30 | 2025-12-30 | 1 | 100% | 1
1.6 | MAPPING TABEL TAMBAHAN BEA CUKAI | Baim |  | 2025-12-30 | 2026-01-08 | 10 | 100% | 8
1.7 | SIT | Baim, Budi |  | 2026-01-06 | 2026-01-08 | 3 | 100% | 3
1.8 | INTEGRASI API SAP UNTUK BEA CUKAI | Baim |  | 2026-01-09 | 2026-01-18 | 10 | 50% | 6
1.9 | BELAJAR MENGEDIT FORM SAP | Baim, Budi |  | 2026-01-08 | 2026-01-08 | 1 | 100% | 1
1.10 | KUT SAP BAGIAN MASTER DATA MM | Baim |  | 2026-01-15 | 2026-01-16 | 2 | 100% | 2
1.11 | KUT SAP BAGIAN MASTER DATA SD dan FICO | Budi |  | 2026-01-15 | 2026-01-16 | 2 | 100% | 2
1.12 | Modifikasi Form Invoice (Barang Bekas, Avfal, BS, Maklon, Masker) | Baim |  | 2026-01-10 | 2026-01-21 | 12 | 90% | 8
1.13 | Modifikasi Form Surat Jalan (Barang Bekas, Avfal, BS, Maklon, Masker) | Budi |  | 2026-01-10 | 2026-01-21 | 12 | 75% | 8
1.14 | Buat UI penarikan data dari API dan insert data Delivery | Baim |  | 2026-02-03 | 2026-02-04 | 2 | 100% | 2
1.15 | Buat UI penarikan data dari API dan insert data Material | Budi |  | 2026-02-03 | 2026-02-04 | 2 | 100% | 2
1.16 | Buat UI penarikan data dari API dan insert data Warehouse | Budi |  | 2026-02-05 | 2026-02-06 | 2 | 100% | 2
1.17 | Buat UI penarikan data dari API dan insert data Asset | Baim |  | 2026-02-05 | 2026-02-06 | 2 | 100% | 2
1.18 | Buat UI penarikan data dari API dan insert data Invoice | Budi |  | 2026-02-04 | 2026-02-05 | 2 | 100% | 2
1.19 | Buat UI penarikan data dari API dan insert data Supplier | Baim |  | 2026-02-05 | 2026-02-06 | 2 | 100% | 2
1.20 | Buat UI penarikan data dari API dan insert data Master Customer | Budi |  | 2026-02-07 | 2026-02-10 | 4 | 100% | 2
1.21 | Buat UI penarikan data dari API dan insert data PO | Baim |  | 2026-02-07 | 2026-02-10 | 4 | 100% | 2
1.22 | Buat UI penarikan data dari API dan insert data Material Document | Budi |  | 2026-02-11 | 2026-02-12 | 2 | 100% | 2
1.23 | Buat UI penarikan data dari API dan insert data BOM | Baim |  | 2026-02-11 | 2026-02-12 | 2 | 100% | 2
1.24 | UAT | Baim, Budi |  | 2026-02-12 | 2026-02-14 | 3 | 100% | 2
1.25 | BBK INTERN | Budi |  | 2026-02-15 | 2026-02-19 | 5 | 0% | 4
1.26 | LAPORAN SURAT JALAN (P) | Baim |  | 2026-02-15 | 2026-02-19 | 5 | 80% | 4
1.27 | DETAIL LIST KARTON PER RAK | Budi |  | 2026-02-20 | 2026-02-23 | 4 | 0% | 2
1.28 | LAPORAN GUDANG PACKING LEAD TIME | Baim/Star |  | 2026-02-20 | 2026-02-23 | 4 | 0% | 2
1.29 | LAPORAN PERSEDIAAN GUDANG PACKING | Budi/Star |  | 2026-02-24 | 2026-02-25 | 2 | 0% | 2
1.30 | DASHBOARD LAYOUT PER BIN | Baim |  | 2026-02-24 | 2026-02-25 | 2 | 0% | 2
1.31 | FORM BC - PO | Jali |  | 2026-02-26 | 2026-03-02 | 5 | 0% | 3
1.32 | LAPORAN SURAT JALAN SLOC | Budi |  | 2026-02-26 | 2026-02-27 | 2 | 0% | 2
1.33 | LIST KARTON PER KODE ORDER | Baim/Star |  | 2026-02-26 | 2026-02-27 | 2 | 0% | 2
1.34 | FORM BC - GRS | Jali |  | 2026-03-03 | 2026-03-04 | 2 | 0% | 2
1.35 | LIST STK INTERN DAN EXTERN | Budi |  | 2026-02-28 | 2026-03-03 | 4 | 0% | 2
1.36 | MONITORING KAIN GREY | Baim |  | 2026-02-28 | 2026-03-03 | 4 | 0% | 2
1.37 | FORM BC - BPB | Jali |  | 2026-03-05 | 2026-03-06 | 2 | 0% | 2
1.38 | MOVING HISTORY PER LIST KARTON | Budi/Star |  | 2026-03-04 | 2026-03-05 | 2 | 0% | 2
1.39 | MOVING HISTORY PER LIST BARCODE | Baim |  | 2026-03-04 | 2026-03-05 | 2 | 0% | 2
1.40 | REPORT CANCEL KAIN KELUAR | Budi |  | 2026-03-06 | 2026-03-09 | 4 | 0% | 2
1.41 | REPORT CANCEL KAIN MASUK | Baim |  | 2026-03-06 | 2026-03-09 | 4 | 0% | 2
1.42 | FORM BC - SJ | Jali |  | 2026-03-07 | 2026-03-10 | 4 | 0% | 2
1.43 | REPORT COSTING | Budi |  | 2026-03-10 | 2026-03-11 | 2 | 0% | 2
1.44 | REPORT PEMARTAIAN | Baim |  | 2026-03-10 | 2026-03-11 | 2 | 0% | 2
1.45 | FORM BC - INVOICE | Jali |  | 2026-03-11 | 2026-03-12 | 2 | 0% | 2
1.46 | REPORT RESERVASI | Budi |  | 2026-03-12 | 2026-03-13 | 2 | 0% | 2
1.47 | REPORT RESUME KODE PARTAI | Baim |  | 2026-03-12 | 2026-03-13 | 2 | 0% | 2
1.48 | FORM BC - STOCK GUDANG | Jali |  | 2026-03-13 | 2026-03-16 | 4 | 0% | 2
1.49 | STK BLANK GD. PACKING | Budi |  | 2026-03-14 | 2026-03-17 | 4 | 0% | 2
1.50 | STOCK BALANCE KAIN GREY | Baim |  | 2026-03-14 | 2026-03-17 | 4 | 0% | 2
1.51 | FORM BC - WIP | Jali |  | 2026-03-17 | 2026-03-19 | 3 | 0% | 3
1.52 | FORM BC - MASTER MATERIAL | Jali |  | 2026-03-18 | 2026-03-19 | 2 | 0% | 2
1.53 | STOCK GREY LEAD TIME PER GRADE | Budi |  | 2026-03-18 | 2026-03-19 | 2 | 0% | 2
1.54 | STOCK KAIN GREY (GRADE) | Baim |  | 2026-03-18 | 2026-03-19 | 2 | 0% | 2
1.55 | FORM BC - MASTER MATERIAL | Jali |  | 2026-03-28 | 2026-03-31 | 4 | 0% | 2
1.56 | STOCK KAIN GREY (LW 22) | Budi |  | 2026-03-28 | 2026-03-31 | 4 | 0% | 2
1.57 | STOCK KAIN PASIF (ALL AREA) | Baim |  | 2026-03-28 | 2026-03-31 | 4 | 0% | 2
1.58 | FORM BC - MASTER VENDOR | Jali |  | 2026-04-01 | 2026-04-04 | 4 | 0% | 3
1.59 | STOCK LEADTIME | Budi |  | 2026-04-01 | 2026-04-02 | 2 | 0% | 2
1.60 | STOCK PER BARCODE | Baim/Jali |  | 2026-04-01 | 2026-04-02 | 2 | 0% | 2
1.61 | FORM BC - UPDATE DOK EXPORT | Jali |  | 2026-04-05 | 2026-04-08 | 4 | 0% | 3
1.62 | MOVING HISTORY - GUDANG GREY | Budi |  | 2026-04-03 | 2026-04-06 | 4 | 0% | 2
1.63 | FORM BC - UPDATE DOK KELUAR MARKET | Jali |  | 2026-04-03 | 2026-04-06 | 4 | 0% | 2
1.64 | FORM BC - UPDATE DOK KELUAR NON MARKET | Jali |  | 2026-04-09 | 2026-04-12 | 4 | 0% | 2
1.65 | FORM BC - UPDATE DOK MASUK BPB | Jali |  | 2026-04-07 | 2026-04-10 | 4 | 0% | 4
1.66 | FORM BC - UPDATE DOK MASUK GRS | Jali |  | 2026-04-07 | 2026-04-10 | 4 | 0% | 4
1 | Report |  |  |  | - |  |  | -
1.1 | REPORT - WM - MOVING HISTORY - GUDANG GREY | Billy, Baim |  | 2026-02-04 | 2026-02-10 | 7 | 0% | 5
1.2 | REPORT - WM - STOCK PER BARCODE | Baim |  | 2026-02-11 | 2026-02-17 | 7 | 0% | 5
1.3 | REPORT - WM - LAPORAN PERSEDIAAN GUDANG PACKING | Budi |  | 2026-02-11 | 2026-02-17 | 7 | 0% | 5
1.4 | REPORT - WM - LAPORAN GUDANG PACKING LEAD TIME | Baim |  | 2026-02-18 | 2026-02-24 | 7 | 0% | 5
1.5 | REPORT - WM - LIST KARTON PER KODE ORDER | Budi |  | 2026-02-18 | 2026-02-24 | 7 | 0% | 5
1.6 | REPORT - WM - MOVING HISTORY PER BARCODE | Baim |  | 2026-02-25 | 2026-03-03 | 7 | 0% | 5
1.7 | REPORT - WM - MOVING HISTORY PER LIST KARTON | Budi |  | 2026-02-25 | 2026-03-03 | 7 | 0% | 5
1.8 | REPORT - MM - STOCK KAIN GREY (GRADE) | Billy, Budi |  | 2026-02-04 | 2026-02-10 | 7 | 0% | 5
1.9 | REPORT - MM - STOCK LEADTIME | Baim |  | 2026-03-04 | 2026-03-10 | 7 | 0% | 5
1.10 | REPORT - MM - STOCK GREY LEAD TIME PER GRADE | Budi |  | 2026-03-04 | 2026-03-10 | 7 | 0% | 5
1.11 | REPORT - MM - STOCK BALANCE KAIN GREY | Budi |  | 2026-03-11 | 2026-03-17 | 7 | 0% | 5
1.12 | REPORT - MM - STOCK KAIN PASIF (ALL AREA) | Baim |  | 2026-03-11 | 2026-03-17 | 7 | 0% | 5
1.13 | REPORT - MM - STOCK KAIN GREY (LW 22) | Budi |  | 2026-03-18 | 2026-03-24 | 7 | 0% | 5
1.14 | REPORT - MM - REPORT RESERVASI | Budi |  | 2026-03-25 | 2026-03-31 | 7 | 0% | 5
1.15 | REPORT - MM - REPORT PEMARTAIAN | Budi |  | 2026-03-25 | 2026-03-31 | 7 | 0% | 5
1.16 | REPORT - MM - REPORT RESUME KODE PARTAI | Budi |  | 2026-04-01 | 2026-04-07 | 7 | 0% | 5
1.17 | REPORT - MM - BBK INTERN | Baim |  | 2026-04-01 | 2026-04-07 | 7 | 0% | 5
1.18 | REPORT - MM - Report Cancel Kain Masuk | Budi |  | 2026-04-08 | 2026-04-14 | 7 | 0% | 5
1.19 | REPORT - MM - Report Cancel Kain Keluar | Baim |  | 2026-04-08 | 2026-04-14 | 7 | 0% | 5
1.20 | REPORT - MM - List STK Intern dan Extern | Budi |  | 2026-04-15 | 2026-04-21 | 7 | 0% | 5
1.21 | REPORT - MM - Laporan Surat Jalan Sloc | Baim |  | 2026-04-15 | 2026-04-21 | 7 | 0% | 5
1.22 | REPORT - MM - Laporan Surat Jalan (P) | Budi |  | 2026-04-22 | 2026-04-28 | 7 | 0% | 5
1.23 | REPORT - WM - DASHBOARD LAYOUT PER BIN | Baim |  | 2026-04-22 | 2026-04-28 | 7 | 0% | 5
1.24 | REPORT - WM - MONITORING KAIN GREY | Budi |  | 2026-04-29 | 2026-05-05 | 7 | 0% | 5
1.25 | REPORT - CO - REPORT COSTING | Budi |  | 2026-04-29 | 2026-05-05 | 7 | 0% | 5
1.26 | REPORT - WM - DETAIL LIST KARTON PER RAK | Budi |  | 2026-05-06 | 2026-05-12 | 7 | 0% | 5
1.27 | REPORT - MM - STK Blank Gd. Packing | Budi |  | 2026-05-06 | 2026-05-12 | 7 | 0% | 5
2 | Interfaces |  |  |  | - |  |  | -
2.1 | INTERFACE BEA CUKAI | Billy, Budi |  | 2026-01-12 | 2026-01-16 | 5 | 0% | 5
2.2 | INTERFACE PRINT BARCODE | Billy, Baim, Budi |  | 2026-01-01 | 2026-01-10 | 10 | 0% | 6
2.3 | INTERFACE PRINT BARCODE BANYAK LIST KARTON | Billy, Baim |  | 2026-01-12 | 2026-01-16 | 5 | 0% | 5
3 | Forms |  |  |  | - |  |  | -
3.1 | Form Transfer Posting (ZSCMF001) | Billy, Budi |  | 2026-01-19 | 2026-01-22 | 4 | 0% | 4
3.2 | Form Purchase Order (ZSCMF002) | Billy, Baim |  | 2026-01-19 | 2026-01-22 | 4 | 0% | 4
3.3 | Form Good Receipt (ZSCMF003) | Baim |  | 2026-01-23 | 2026-01-28 | 6 | 0% | 4
3.4 | Form Good Issue (ZSCMF004) | Baim |  | 2026-01-29 | 2026-02-03 | 6 | 0% | 4
3.5 | Form Bukti Tanda Terima | Budi |  | 2026-01-23 | 2026-01-28 | 6 | 0% | 4
4 | Enhancement |  |  |  | - |  |  | -
4.1 | Custom field for qty in PCS at Report Stock | Billy, Budi |  | 2026-01-29 | 2026-02-03 | 6 | 0% | 4
Note on A7: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet.
Note on B7: Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on C7: Task Lead Enter the name of the Task Lead in this column.
Note on E7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on F7: End Date: The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on G7: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on H7: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on I7: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.
Note on B23: BC: https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_PRODUCT_SRV//A_Product --> tabel pz_material https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_PRODUCT_SRV/A_ProductDescription --> tabel pz_material_description https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_PRODUCT_SRV/A_ProductPlant --> tabel pz_material_plant
Note on B24: $url = "https://my430621-api.s4hana.cloud.sap/sap/opu/odata4/sap/api_warehouse_order_task_2/srvd_a2x/sap/warehouseorder/0001/WarehouseTask"; $username = "LEUWITEX_US_SAP_COM_0353"; $password = "Leuwitexsapcloud@2025"; CREATE TABLE warehouse_task ( EWMWarehouse VARCHAR(20), WarehouseTask BIGINT, WarehouseTaskItem INT, WarehouseOrder BIGINT, WhseTaskCrtnUTCDateTime TIMESTAMP, WhseTaskLastChgUTCDateTime TIMESTAMP, WhseTaskConfUTCDateTime TIMESTAMP, ConfirmedByUser VARCHAR(50), WhseTaskPlannedClosingDateTime TIMESTAMP, WhseTaskGoodsReceiptDateTime TIMESTAMP, WarehouseTaskStatus CHAR(1), WarehouseProcessType VARCHAR(10), WarehouseProcessCategory INT, IsHandlingUnitWarehouseTask BOOLEAN, EWMHandlingUnitType VARCHAR(50), HomogeneousFullPalletPick VARCHAR(50), Product VARCHAR(50), Batch VARCHAR(20), BatchChangeIsNotAllowed BOOLEAN, CountryOfOrigin VARCHAR(50), ShelfLifeExpirationDate DATE, EWMStockType CHAR(1), EWMStockUsage VARCHAR(50), EWMStockOwner BIGINT, EntitledToDisposeParty BIGINT, WBSElementInternalID INT, WBSElementExternalID VARCHAR(50), SpecialStockIdfgSalesOrder VARCHAR(50), SpecialStockIdfgSalesOrderItem INT, ExecutingResource VARCHAR(50), WarehouseMovementsReason VARCHAR(50), ProductionOrder VARCHAR(50), EWMProductionSupplyArea VARCHAR(50), EWMDocumentCategory VARCHAR(10), EWMReferenceDocumentCategory VARCHAR(10), PDO VARCHAR(10), EWMWave INT, EWMWaveItem INT, EWMDelivery BIGINT, EWMDeliveryItem INT, PurchasingDocument BIGINT, PurchasingDocumentItem INT, SalesDocument VARCHAR(50), SalesDocumentItem INT, BaseUnit VARCHAR(10), EWMBaseUnitISOCode VARCHAR(10), AlternativeUnit VARCHAR(10), EWMAlternativeUnitISOCode VARCHAR(10), TargetQuantityInBaseUnit NUMERIC, TargetQuantityInAltvUnit NUMERIC, ActualQuantityInBaseUnit NUMERIC, ActualQuantityInAltvUnit NUMERIC, DifferenceQuantityInBaseUnit NUMERIC, DifferenceQuantityInAltvUnit NUMERIC, WhseTaskNetWeightUnitOfMeasure VARCHAR(10), WhseTaskNetWeight NUMERIC, WhseTaskNetVolumeUnitOfMeasure VARCHAR(10), WhseTaskNetVolume NUMERIC, SourceStorageType VARCHAR(10), SourceStorageSection VARCHAR(10), SourceStorageBin VARCHAR(20), SourceResource VARCHAR(50), DestinationStorageType VARCHAR(10), DestinationStorageSection VARCHAR(10), DestinationStorageBin VARCHAR(20), DestinationResource VARCHAR(50), ActivityArea VARCHAR(10), SourceHandlingUnit VARCHAR(50), DestinationHandlingUnit VARCHAR(50), WarehouseTaskExceptionCode VARCHAR(10), WhseTaskSortingSequenceValue INT, WarehouseOrderSequenceValue INT, WarehouseOrderActivityArea VARCHAR(10), WarehouseOrderCreationRule VARCHAR(10), WarehouseOrderQueue VARCHAR(50), WarehouseActivityType VARCHAR(10), EWMConsolidationGroup BIGINT, EWMWarehouseTaskPriority INT, CreatedByUser VARCHAR(50), EWMRoute VARCHAR(50), EWMWaveCategory VARCHAR(50), EWMCanceledWarehouseTask INT, SerialNumberRequiredLevel VARCHAR(10) );
Note on B25: BC: https://my430621-api.s4hana.cloud.sap/sap/opu/odata4/sap/api_fixedasset/srvd_a2x/sap/fixedasset/0001/FixedAsset Username : LEUWITEX_US_SAP_COM_0A93 Password : Leuwitexsapcloud@2025" tabel : pz_fixed_asset https://my430621-api.s4hana.cloud.sap/sap/opu/odata4/sap/api_fixedasset/srvd_a2x/sap/fixedasset/0001/FixedAssetLedger Username : LEUWITEX_US_SAP_COM_0A93 Password : Leuwitexsapcloud@2025" tabel : pz_fixed_asset_ledger
Note on B26: BC: https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BILLING_DOCUMENT_SRV/A_BillingDocument Comm User : LEUWITEX_US_SAP_COM_0120 password user comm: Leuwitexsapcloud@2025 tabel : pz_billing_document https://my430621-api.s4hana.cloud.sap/sap/opu/odata4/sap/api_billingdocument/srvd_a2x/sap/billingdocument/0001/BillingDocumentItem Comm User : LEUWITEX_US_SAP_COM_0120 password user comm: Leuwitexsapcloud@2025 tabel : pz_billing_document_item https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_SALES_ORDER_SRV/A_SalesOrder Comm User : LEUWITEX_US_SAP_COM_0109 password user comm: Leuwitexsapcloud@2025 tabel : pz_sales_order
Note on B27: https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BUSINESS_PARTNER/A_Supplier Username : LEUWITEX_US_SAP_COM_0008 SupplierFullName Bechtle AG Kriek street Password : \W+M)hw&kj]WHnSJ>UmhdB(f56N>\Zk9caxMY=5L CREATE TABLE pz_supplier ( supplier VARCHAR(20) PRIMARY KEY, supplier_full_name VARCHAR(100), created_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP, updated_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP ); https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BUSINESS_PARTNER/A_AddressEmailAddress Username : LEUWITEX_US_SAP_COM_0008 Password : \W+M)hw&kj]WHnSJ>UmhdB(f56N>\Zk9caxMY=5L CREATE TABLE pz_address_email_address ( email_address VARCHAR(100) NOT NULL, person VARCHAR(50), address_id VARCHAR(50), created_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP, updated_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP, PRIMARY KEY (email_address) ); https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BUSINESS_PARTNER/A_BusinessPartnerAddress Username : LEUWITEX_US_SAP_COM_0008 Password : \W+M)hw&kj]WHnSJ>UmhdB(f56N>\Zk9caxMY=5L CREATE TABLE pz_business_partner_address ( country VARCHAR(50), postal_code VARCHAR(20), region VARCHAR(100), district VARCHAR(100), business_partner VARCHAR(20), address_id VARCHAR(50), created_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP, updated_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP ); https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BUSINESS_PARTNER/A_AddressHomePageURL Username : LEUWITEX_US_SAP_COM_0008 Password : \W+M)hw&kj]WHnSJ>UmhdB(f56N>\Zk9caxMY=5L CREATE TABLE pz_address_home_page_url ( website_url VARCHAR(200) NOT NULL, address_id VARCHAR(50), -- Audit columns created_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP, updated_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP, PRIMARY KEY (website_url) ); https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BUSINESS_PARTNER/A_AddressPhoneNumber Username : LEUWITEX_US_SAP_COM_0008 Password : \W+M)hw&kj]WHnSJ>UmhdB(f56N>\Zk9caxMY=5L CREATE TABLE pz_address_phone_number ( phone_number VARCHAR(50) NOT NULL, address_id VARCHAR(50), created_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP, updated_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP ); https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BUSINESS_PARTNER/A_BuPaIdentification Username : LEUWITEX_US_SAP_COM_0008 Password : \W+M)hw&kj]WHnSJ>UmhdB(f56N>\Zk9caxMY=5L CREATE TABLE pz_bu_pa_identification ( npwp_vendor VARCHAR(30) NOT NULL, business_partner VARCHAR(20), created_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP, updated_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP ); https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BUSINESS_PARTNER/A_AddressFaxNumber Username : LEUWITEX_US_SAP_COM_0008 Password : \W+M)hw&kj]WHnSJ>UmhdB(f56N>\Zk9caxMY=5L CREATE TABLE pz_bu_address_fax_number ( fax_number VARCHAR(50) NOT NULL, address_id VARCHAR(50), created_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP, updated_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP );
Note on B28: https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BUSINESS_PARTNER/A_BusinessPartnerAddress UserName : LEUWITEX_US_SAP_COM_0008 Password : \W+M)hw&kj]WHnSJ>UmhdB(f56N>\Zk9caxMY=5L tabel : pz_business_partner_address https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BUSINESS_PARTNER/A_Customer UserName : LEUWITEX_US_SAP_COM_0008 Password : \W+M)hw&kj]WHnSJ>UmhdB(f56N>\Zk9caxMY=5L tabel : pz_customer https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BUSINESS_PARTNER/A_Customer('9200000010')/to_CustomerSalesArea UserName : LEUWITEX_US_SAP_COM_0008 Password : \W+M)hw&kj]WHnSJ>UmhdB(f56N>\Zk9caxMY=5L tabel : pz_customer_sales_area https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BUSINESS_PARTNER/A_BusinessPartnerTaxNumber UserName : LEUWITEX_US_SAP_COM_0008 Password : \W+M)hw&kj]WHnSJ>UmhdB(f56N>\Zk9caxMY=5L tabel : pz_business_partner_tax_number https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BUSINESS_PARTNER/A_CustSalesPartnerFunc UserName : LEUWITEX_US_SAP_COM_0008 Password : \W+M)hw&kj]WHnSJ>UmhdB(f56N>\Zk9caxMY=5L tabel : pz_cust_sales_partner_func
Note on B29: BC: https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BILL_OF_MATERIAL_SRV;v=0002/MaterialBOM Comm User : LEUWITEX_US_SAP_COM_0105 password user comm: Leuwitexsapcloud@2025 tabel : pz_material_bom https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BILL_OF_MATERIAL_SRV;v=0002/MaterialBOMItem Comm User : LEUWITEX_US_SAP_COM_0105 password user comm: Leuwitexsapcloud@2025 tabel : pz_material_bom_item
Note on B30: https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_MATERIAL_DOCUMENT_SRV/A_MaterialDocumentHeader Username : LEUWITEX_US_SAP_COM_0108 Password : Leuwitexsapcloud@2025 table pz_material_document_header https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_MATERIAL_DOCUMENT_SRV//A_MaterialDocumentItem Username : LEUWITEX_US_SAP_COM_0108 Password : Leuwitexsapcloud@2025 table pz_material_document_item
Note on B31: BC: https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BILL_OF_MATERIAL_SRV;v=0002/MaterialBOM Comm User : LEUWITEX_US_SAP_COM_0105 password user comm: Leuwitexsapcloud@2025 tabel : pz_material_bom https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BILL_OF_MATERIAL_SRV;v=0002/MaterialBOMItem Comm User : LEUWITEX_US_SAP_COM_0105 password user comm: Leuwitexsapcloud@2025 tabel : pz_material_bom_item
Note on B32: BC: https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BILL_OF_MATERIAL_SRV;v=0002/MaterialBOM Comm User : LEUWITEX_US_SAP_COM_0105 password user comm: Leuwitexsapcloud@2025 tabel : pz_material_bom https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BILL_OF_MATERIAL_SRV;v=0002/MaterialBOMItem Comm User : LEUWITEX_US_SAP_COM_0105 password user comm: Leuwitexsapcloud@2025 tabel : pz_material_bom_item

## g
RICEF BY LEUWITEX ( update 2 Maret 2026 )
| Project Start Date | 2025-11-25 |  |  |  | Display Week | 1 |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8
| Project Lead | Billy | [6 empty] | 2025-11-24 | [6 empty] | 2025-12-01 | [6 empty] | 2025-12-08 | [6 empty] | 2025-12-15 | [6 empty] | 2025-12-22 | [6 empty] | 2025-12-29 | [6 empty] | 2026-01-05 | [6 empty] | 2026-01-12
 | time axis 2025-11-24 to 2026-01-18
WBS | TASK | PIC | NOTES | START | END | DAYS | % DONE | WORK DAYS | time axis 2025-11-24 to 2026-01-18
1 | SAP API development |  |  |  | - |  |  | -
1.1 | INSTALL ECLIPSE, ADOBE LIFECYCLE DI PC | Baim, Budi |  | 2025-11-26 | 2025-11-26 | 1 | 100% | 1
1.2 | BELAJAR KE SOLTIUS TENTANG SAP | Baim, Budi |  | 2025-11-27 | 2026-02-01 | 67 | 40% | 47
1.3 | INTEGRASI API SAP KE PRINT BARCODE INTERNAL | Baim, Budi |  | 2025-12-04 | 2025-12-10 | 7 | 100% | 5
1.4 | MAPPING IT INVENTORY | Baim |  | 2025-12-18 | 2025-12-23 | 6 | 100% | 4
1.5 | BELAJAR MENDAFTARKAN API SAP | Baim, Budi |  | 2025-12-30 | 2025-12-30 | 1 | 100% | 1
1.6 | MAPPING TABEL TAMBAHAN BEA CUKAI | Baim |  | 2025-12-30 | 2026-01-08 | 10 | 100% | 8
1.7 | SIT | Baim, Budi |  | 2026-01-06 | 2026-01-08 | 3 | 100% | 3
1.8 | INTEGRASI API SAP UNTUK BEA CUKAI | Baim |  | 2026-01-09 | 2026-01-18 | 10 | 50% | 6
1.9 | BELAJAR MENGEDIT FORM SAP | Baim, Budi |  | 2026-01-08 | 2026-01-08 | 1 | 100% | 1
1.10 | KUT SAP BAGIAN MASTER DATA MM | Baim |  | 2026-01-15 | 2026-01-16 | 2 | 100% | 2
1.11 | KUT SAP BAGIAN MASTER DATA SD dan FICO | Budi |  | 2026-01-15 | 2026-01-16 | 2 | 100% | 2
1.12 | Modifikasi Form Invoice (Barang Bekas, Avfal, BS, Maklon, Masker) | Baim |  | 2026-01-10 | 2026-01-21 | 12 | 90% | 8
1.13 | Modifikasi Form Surat Jalan (Barang Bekas, Avfal, BS, Maklon, Masker) | Budi |  | 2026-01-10 | 2026-01-21 | 12 | 75% | 8
1.14 | Buat UI penarikan data dari API dan insert data Delivery | Baim |  | 2026-02-03 | 2026-02-04 | 2 | 100% | 2
1.15 | Buat UI penarikan data dari API dan insert data Material | Budi |  | 2026-02-03 | 2026-02-04 | 2 | 100% | 2
1.16 | Buat UI penarikan data dari API dan insert data Warehouse | Budi |  | 2026-02-05 | 2026-02-06 | 2 | 100% | 2
1.17 | Buat UI penarikan data dari API dan insert data Asset | Baim |  | 2026-02-05 | 2026-02-06 | 2 | 100% | 2
1.18 | Buat UI penarikan data dari API dan insert data Invoice | Budi |  | 2026-02-04 | 2026-02-05 | 2 | 100% | 2
1.19 | Buat UI penarikan data dari API dan insert data Supplier | Baim |  | 2026-02-05 | 2026-02-06 | 2 | 100% | 2
1.20 | Buat UI penarikan data dari API dan insert data Master Customer | Budi |  | 2026-02-07 | 2026-02-10 | 4 | 100% | 2
1.21 | Buat UI penarikan data dari API dan insert data PO | Baim |  | 2026-02-07 | 2026-02-10 | 4 | 100% | 2
1.22 | Buat UI penarikan data dari API dan insert data Material Document | Budi |  | 2026-02-11 | 2026-02-12 | 2 | 100% | 2
1.23 | Buat UI penarikan data dari API dan insert data BOM | Baim |  | 2026-02-11 | 2026-02-12 | 2 | 100% | 2
1.24 | UAT | Baim, Budi |  | 2026-02-12 | 2026-02-14 | 3 | 100% | 2
1.25 | BBK INTERN | Budi |  | 2026-02-15 | 2026-02-19 | 5 | 0% | 4
1.26 | LAPORAN SURAT JALAN (P) | Baim |  | 2026-02-15 | 2026-02-19 | 5 | 80% | 4
1.27 | DETAIL LIST KARTON PER RAK | Budi |  | 2026-02-20 | 2026-02-23 | 4 | 0% | 2
1.28 | LAPORAN GUDANG PACKING LEAD TIME | Baim |  | 2026-02-20 | 2026-02-23 | 4 | 50% | 2
1.29 | MOVING HISTORY PER LIST KARTON | Budi |  | 2026-02-24 | 2026-02-25 | 2 | 0% | 2
1.30 | DASHBOARD LAYOUT PER BIN | Baim |  | 2026-02-24 | 2026-02-25 | 2 | 0% | 2
1.31 | LAPORAN SURAT JALAN SLOC | Budi |  | 2026-02-26 | 2026-02-27 | 2 | 0% | 2
1.32 | LIST KARTON PER KODE ORDER | Baim |  | 2026-02-26 | 2026-02-27 | 2 | 50% | 2
1.33 | LIST STK INTERN DAN EXTERN | Budi |  | 2026-02-28 | 2026-03-03 | 4 | 0% | 2
1.34 | MONITORING KAIN GREY | Baim |  | 2026-02-28 | 2026-03-03 | 4 | 0% | 2
1.35 | LAPORAN PERSEDIAAN GUDANG PACKING | Star |  | 2026-03-03 | 2026-03-05 | 3 | 0% | 3
1.36 | STOCK PER BARCODE | Jali |  | 2026-03-03 | 2026-03-05 | 3 | 0% | 3
1.37 | REPORT CANCEL KAIN KELUAR | Budi |  | 2026-03-06 | 2026-03-09 | 4 | 0% | 2
1.38 | REPORT CANCEL KAIN MASUK | Baim |  | 2026-03-06 | 2026-03-09 | 4 | 0% | 2
1.39 | REPORT COSTING | Budi |  | 2026-03-10 | 2026-03-11 | 2 | 0% | 2
1.40 | REPORT PEMARTAIAN | Baim |  | 2026-03-10 | 2026-03-11 | 2 | 0% | 2
1.41 | REPORT RESERVASI | Budi |  | 2026-03-12 | 2026-03-13 | 2 | 0% | 2
1.42 | REPORT RESUME KODE PARTAI | Baim |  | 2026-03-12 | 2026-03-13 | 2 | 0% | 2
1.43 | STK BLANK GD. PACKING | Budi |  | 2026-03-14 | 2026-03-17 | 4 | 0% | 2
1.44 | STOCK BALANCE KAIN GREY | Baim |  | 2026-03-14 | 2026-03-17 | 4 | 0% | 2
1.45 | STOCK GREY LEAD TIME PER GRADE | Budi |  | 2026-03-18 | 2026-03-19 | 2 | 0% | 2
1.46 | STOCK KAIN GREY (GRADE) | Baim |  | 2026-03-18 | 2026-03-19 | 2 | 0% | 2
1.47 | STOCK KAIN GREY (LW 22) | Budi |  | 2026-03-28 | 2026-03-31 | 4 | 0% | 2
1.48 | STOCK KAIN PASIF (ALL AREA) | Baim |  | 2026-03-28 | 2026-03-31 | 4 | 0% | 2
1.49 | STOCK LEADTIME | Budi |  | 2026-04-01 | 2026-04-02 | 2 | 0% | 2
1.50 | MOVING HISTORY PER LIST BARCODE | Baim |  | 2026-04-01 | 2026-04-02 | 2 | 0% | 2
1.51 | MOVING HISTORY - GUDANG GREY | Budi |  | 2026-04-03 | 2026-04-06 | 4 | 0% | 2
1 | Report |  |  |  | - |  |  | -
1.1 | REPORT - WM - MOVING HISTORY - GUDANG GREY | Billy, Baim |  | 2026-02-04 | 2026-02-10 | 7 | 0% | 5
1.2 | REPORT - WM - STOCK PER BARCODE | Baim |  | 2026-02-11 | 2026-02-17 | 7 | 0% | 5
1.3 | REPORT - WM - LAPORAN PERSEDIAAN GUDANG PACKING | Budi |  | 2026-02-11 | 2026-02-17 | 7 | 0% | 5
1.4 | REPORT - WM - LAPORAN GUDANG PACKING LEAD TIME | Baim |  | 2026-02-18 | 2026-02-24 | 7 | 0% | 5
1.5 | REPORT - WM - LIST KARTON PER KODE ORDER | Budi |  | 2026-02-18 | 2026-02-24 | 7 | 0% | 5
1.6 | REPORT - WM - MOVING HISTORY PER BARCODE | Baim |  | 2026-02-25 | 2026-03-03 | 7 | 0% | 5
1.7 | REPORT - WM - MOVING HISTORY PER LIST KARTON | Budi |  | 2026-02-25 | 2026-03-03 | 7 | 0% | 5
1.8 | REPORT - MM - STOCK KAIN GREY (GRADE) | Billy, Budi |  | 2026-02-04 | 2026-02-10 | 7 | 0% | 5
1.9 | REPORT - MM - STOCK LEADTIME | Baim |  | 2026-03-04 | 2026-03-10 | 7 | 0% | 5
1.10 | REPORT - MM - STOCK GREY LEAD TIME PER GRADE | Budi |  | 2026-03-04 | 2026-03-10 | 7 | 0% | 5
1.11 | REPORT - MM - STOCK BALANCE KAIN GREY | Budi |  | 2026-03-11 | 2026-03-17 | 7 | 0% | 5
1.12 | REPORT - MM - STOCK KAIN PASIF (ALL AREA) | Baim |  | 2026-03-11 | 2026-03-17 | 7 | 0% | 5
1.13 | REPORT - MM - STOCK KAIN GREY (LW 22) | Budi |  | 2026-03-18 | 2026-03-24 | 7 | 0% | 5
1.14 | REPORT - MM - REPORT RESERVASI | Budi |  | 2026-03-25 | 2026-03-31 | 7 | 0% | 5
1.15 | REPORT - MM - REPORT PEMARTAIAN | Budi |  | 2026-03-25 | 2026-03-31 | 7 | 0% | 5
1.16 | REPORT - MM - REPORT RESUME KODE PARTAI | Budi |  | 2026-04-01 | 2026-04-07 | 7 | 0% | 5
1.17 | REPORT - MM - BBK INTERN | Baim |  | 2026-04-01 | 2026-04-07 | 7 | 0% | 5
1.18 | REPORT - MM - Report Cancel Kain Masuk | Budi |  | 2026-04-08 | 2026-04-14 | 7 | 0% | 5
1.19 | REPORT - MM - Report Cancel Kain Keluar | Baim |  | 2026-04-08 | 2026-04-14 | 7 | 0% | 5
1.20 | REPORT - MM - List STK Intern dan Extern | Budi |  | 2026-04-15 | 2026-04-21 | 7 | 0% | 5
1.21 | REPORT - MM - Laporan Surat Jalan Sloc | Baim |  | 2026-04-15 | 2026-04-21 | 7 | 0% | 5
1.22 | REPORT - MM - Laporan Surat Jalan (P) | Budi |  | 2026-04-22 | 2026-04-28 | 7 | 0% | 5
1.23 | REPORT - WM - DASHBOARD LAYOUT PER BIN | Baim |  | 2026-04-22 | 2026-04-28 | 7 | 0% | 5
1.24 | REPORT - WM - MONITORING KAIN GREY | Budi |  | 2026-04-29 | 2026-05-05 | 7 | 0% | 5
1.25 | REPORT - CO - REPORT COSTING | Budi |  | 2026-04-29 | 2026-05-05 | 7 | 0% | 5
1.26 | REPORT - WM - DETAIL LIST KARTON PER RAK | Budi |  | 2026-05-06 | 2026-05-12 | 7 | 0% | 5
1.27 | REPORT - MM - STK Blank Gd. Packing | Budi |  | 2026-05-06 | 2026-05-12 | 7 | 0% | 5
2 | Interfaces |  |  |  | - |  |  | -
2.1 | INTERFACE BEA CUKAI | Billy, Budi |  | 2026-01-12 | 2026-01-16 | 5 | 0% | 5
2.2 | INTERFACE PRINT BARCODE | Billy, Baim, Budi |  | 2026-01-01 | 2026-01-10 | 10 | 0% | 6
2.3 | INTERFACE PRINT BARCODE BANYAK LIST KARTON | Billy, Baim |  | 2026-01-12 | 2026-01-16 | 5 | 0% | 5
3 | Forms |  |  |  | - |  |  | -
3.1 | Form Transfer Posting (ZSCMF001) | Billy, Budi |  | 2026-01-19 | 2026-01-22 | 4 | 0% | 4
3.2 | Form Purchase Order (ZSCMF002) | Billy, Baim |  | 2026-01-19 | 2026-01-22 | 4 | 0% | 4
3.3 | Form Good Receipt (ZSCMF003) | Baim |  | 2026-01-23 | 2026-01-28 | 6 | 0% | 4
3.4 | Form Good Issue (ZSCMF004) | Baim |  | 2026-01-29 | 2026-02-03 | 6 | 0% | 4
3.5 | Form Bukti Tanda Terima | Budi |  | 2026-01-23 | 2026-01-28 | 6 | 0% | 4
4 | Enhancement |  |  |  | - |  |  | -
4.1 | Custom field for qty in PCS at Report Stock | Billy, Budi |  | 2026-01-29 | 2026-02-03 | 6 | 0% | 4
Note on A7: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet.
Note on B7: Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on C7: Task Lead Enter the name of the Task Lead in this column.
Note on E7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on F7: End Date: The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on G7: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on H7: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on I7: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.
Note on B23: BC: https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_PRODUCT_SRV//A_Product --> tabel pz_material https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_PRODUCT_SRV/A_ProductDescription --> tabel pz_material_description https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_PRODUCT_SRV/A_ProductPlant --> tabel pz_material_plant
Note on B24: $url = "https://my430621-api.s4hana.cloud.sap/sap/opu/odata4/sap/api_warehouse_order_task_2/srvd_a2x/sap/warehouseorder/0001/WarehouseTask"; $username = "LEUWITEX_US_SAP_COM_0353"; $password = "Leuwitexsapcloud@2025"; CREATE TABLE warehouse_task ( EWMWarehouse VARCHAR(20), WarehouseTask BIGINT, WarehouseTaskItem INT, WarehouseOrder BIGINT, WhseTaskCrtnUTCDateTime TIMESTAMP, WhseTaskLastChgUTCDateTime TIMESTAMP, WhseTaskConfUTCDateTime TIMESTAMP, ConfirmedByUser VARCHAR(50), WhseTaskPlannedClosingDateTime TIMESTAMP, WhseTaskGoodsReceiptDateTime TIMESTAMP, WarehouseTaskStatus CHAR(1), WarehouseProcessType VARCHAR(10), WarehouseProcessCategory INT, IsHandlingUnitWarehouseTask BOOLEAN, EWMHandlingUnitType VARCHAR(50), HomogeneousFullPalletPick VARCHAR(50), Product VARCHAR(50), Batch VARCHAR(20), BatchChangeIsNotAllowed BOOLEAN, CountryOfOrigin VARCHAR(50), ShelfLifeExpirationDate DATE, EWMStockType CHAR(1), EWMStockUsage VARCHAR(50), EWMStockOwner BIGINT, EntitledToDisposeParty BIGINT, WBSElementInternalID INT, WBSElementExternalID VARCHAR(50), SpecialStockIdfgSalesOrder VARCHAR(50), SpecialStockIdfgSalesOrderItem INT, ExecutingResource VARCHAR(50), WarehouseMovementsReason VARCHAR(50), ProductionOrder VARCHAR(50), EWMProductionSupplyArea VARCHAR(50), EWMDocumentCategory VARCHAR(10), EWMReferenceDocumentCategory VARCHAR(10), PDO VARCHAR(10), EWMWave INT, EWMWaveItem INT, EWMDelivery BIGINT, EWMDeliveryItem INT, PurchasingDocument BIGINT, PurchasingDocumentItem INT, SalesDocument VARCHAR(50), SalesDocumentItem INT, BaseUnit VARCHAR(10), EWMBaseUnitISOCode VARCHAR(10), AlternativeUnit VARCHAR(10), EWMAlternativeUnitISOCode VARCHAR(10), TargetQuantityInBaseUnit NUMERIC, TargetQuantityInAltvUnit NUMERIC, ActualQuantityInBaseUnit NUMERIC, ActualQuantityInAltvUnit NUMERIC, DifferenceQuantityInBaseUnit NUMERIC, DifferenceQuantityInAltvUnit NUMERIC, WhseTaskNetWeightUnitOfMeasure VARCHAR(10), WhseTaskNetWeight NUMERIC, WhseTaskNetVolumeUnitOfMeasure VARCHAR(10), WhseTaskNetVolume NUMERIC, SourceStorageType VARCHAR(10), SourceStorageSection VARCHAR(10), SourceStorageBin VARCHAR(20), SourceResource VARCHAR(50), DestinationStorageType VARCHAR(10), DestinationStorageSection VARCHAR(10), DestinationStorageBin VARCHAR(20), DestinationResource VARCHAR(50), ActivityArea VARCHAR(10), SourceHandlingUnit VARCHAR(50), DestinationHandlingUnit VARCHAR(50), WarehouseTaskExceptionCode VARCHAR(10), WhseTaskSortingSequenceValue INT, WarehouseOrderSequenceValue INT, WarehouseOrderActivityArea VARCHAR(10), WarehouseOrderCreationRule VARCHAR(10), WarehouseOrderQueue VARCHAR(50), WarehouseActivityType VARCHAR(10), EWMConsolidationGroup BIGINT, EWMWarehouseTaskPriority INT, CreatedByUser VARCHAR(50), EWMRoute VARCHAR(50), EWMWaveCategory VARCHAR(50), EWMCanceledWarehouseTask INT, SerialNumberRequiredLevel VARCHAR(10) );
Note on B25: BC: https://my430621-api.s4hana.cloud.sap/sap/opu/odata4/sap/api_fixedasset/srvd_a2x/sap/fixedasset/0001/FixedAsset Username : LEUWITEX_US_SAP_COM_0A93 Password : Leuwitexsapcloud@2025" tabel : pz_fixed_asset https://my430621-api.s4hana.cloud.sap/sap/opu/odata4/sap/api_fixedasset/srvd_a2x/sap/fixedasset/0001/FixedAssetLedger Username : LEUWITEX_US_SAP_COM_0A93 Password : Leuwitexsapcloud@2025" tabel : pz_fixed_asset_ledger
Note on B26: BC: https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BILLING_DOCUMENT_SRV/A_BillingDocument Comm User : LEUWITEX_US_SAP_COM_0120 password user comm: Leuwitexsapcloud@2025 tabel : pz_billing_document https://my430621-api.s4hana.cloud.sap/sap/opu/odata4/sap/api_billingdocument/srvd_a2x/sap/billingdocument/0001/BillingDocumentItem Comm User : LEUWITEX_US_SAP_COM_0120 password user comm: Leuwitexsapcloud@2025 tabel : pz_billing_document_item https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_SALES_ORDER_SRV/A_SalesOrder Comm User : LEUWITEX_US_SAP_COM_0109 password user comm: Leuwitexsapcloud@2025 tabel : pz_sales_order
Note on B27: https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BUSINESS_PARTNER/A_Supplier Username : LEUWITEX_US_SAP_COM_0008 SupplierFullName Bechtle AG Kriek street Password : \W+M)hw&kj]WHnSJ>UmhdB(f56N>\Zk9caxMY=5L CREATE TABLE pz_supplier ( supplier VARCHAR(20) PRIMARY KEY, supplier_full_name VARCHAR(100), created_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP, updated_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP ); https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BUSINESS_PARTNER/A_AddressEmailAddress Username : LEUWITEX_US_SAP_COM_0008 Password : \W+M)hw&kj]WHnSJ>UmhdB(f56N>\Zk9caxMY=5L CREATE TABLE pz_address_email_address ( email_address VARCHAR(100) NOT NULL, person VARCHAR(50), address_id VARCHAR(50), created_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP, updated_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP, PRIMARY KEY (email_address) ); https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BUSINESS_PARTNER/A_BusinessPartnerAddress Username : LEUWITEX_US_SAP_COM_0008 Password : \W+M)hw&kj]WHnSJ>UmhdB(f56N>\Zk9caxMY=5L CREATE TABLE pz_business_partner_address ( country VARCHAR(50), postal_code VARCHAR(20), region VARCHAR(100), district VARCHAR(100), business_partner VARCHAR(20), address_id VARCHAR(50), created_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP, updated_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP ); https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BUSINESS_PARTNER/A_AddressHomePageURL Username : LEUWITEX_US_SAP_COM_0008 Password : \W+M)hw&kj]WHnSJ>UmhdB(f56N>\Zk9caxMY=5L CREATE TABLE pz_address_home_page_url ( website_url VARCHAR(200) NOT NULL, address_id VARCHAR(50), -- Audit columns created_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP, updated_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP, PRIMARY KEY (website_url) ); https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BUSINESS_PARTNER/A_AddressPhoneNumber Username : LEUWITEX_US_SAP_COM_0008 Password : \W+M)hw&kj]WHnSJ>UmhdB(f56N>\Zk9caxMY=5L CREATE TABLE pz_address_phone_number ( phone_number VARCHAR(50) NOT NULL, address_id VARCHAR(50), created_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP, updated_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP ); https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BUSINESS_PARTNER/A_BuPaIdentification Username : LEUWITEX_US_SAP_COM_0008 Password : \W+M)hw&kj]WHnSJ>UmhdB(f56N>\Zk9caxMY=5L CREATE TABLE pz_bu_pa_identification ( npwp_vendor VARCHAR(30) NOT NULL, business_partner VARCHAR(20), created_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP, updated_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP ); https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BUSINESS_PARTNER/A_AddressFaxNumber Username : LEUWITEX_US_SAP_COM_0008 Password : \W+M)hw&kj]WHnSJ>UmhdB(f56N>\Zk9caxMY=5L CREATE TABLE pz_bu_address_fax_number ( fax_number VARCHAR(50) NOT NULL, address_id VARCHAR(50), created_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP, updated_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP );
Note on B28: https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BUSINESS_PARTNER/A_BusinessPartnerAddress UserName : LEUWITEX_US_SAP_COM_0008 Password : \W+M)hw&kj]WHnSJ>UmhdB(f56N>\Zk9caxMY=5L tabel : pz_business_partner_address https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BUSINESS_PARTNER/A_Customer UserName : LEUWITEX_US_SAP_COM_0008 Password : \W+M)hw&kj]WHnSJ>UmhdB(f56N>\Zk9caxMY=5L tabel : pz_customer https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BUSINESS_PARTNER/A_Customer('9200000010')/to_CustomerSalesArea UserName : LEUWITEX_US_SAP_COM_0008 Password : \W+M)hw&kj]WHnSJ>UmhdB(f56N>\Zk9caxMY=5L tabel : pz_customer_sales_area https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BUSINESS_PARTNER/A_BusinessPartnerTaxNumber UserName : LEUWITEX_US_SAP_COM_0008 Password : \W+M)hw&kj]WHnSJ>UmhdB(f56N>\Zk9caxMY=5L tabel : pz_business_partner_tax_number https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BUSINESS_PARTNER/A_CustSalesPartnerFunc UserName : LEUWITEX_US_SAP_COM_0008 Password : \W+M)hw&kj]WHnSJ>UmhdB(f56N>\Zk9caxMY=5L tabel : pz_cust_sales_partner_func
Note on B29: BC: https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BILL_OF_MATERIAL_SRV;v=0002/MaterialBOM Comm User : LEUWITEX_US_SAP_COM_0105 password user comm: Leuwitexsapcloud@2025 tabel : pz_material_bom https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BILL_OF_MATERIAL_SRV;v=0002/MaterialBOMItem Comm User : LEUWITEX_US_SAP_COM_0105 password user comm: Leuwitexsapcloud@2025 tabel : pz_material_bom_item
Note on B30: https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_MATERIAL_DOCUMENT_SRV/A_MaterialDocumentHeader Username : LEUWITEX_US_SAP_COM_0108 Password : Leuwitexsapcloud@2025 table pz_material_document_header https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_MATERIAL_DOCUMENT_SRV//A_MaterialDocumentItem Username : LEUWITEX_US_SAP_COM_0108 Password : Leuwitexsapcloud@2025 table pz_material_document_item
Note on B31: BC: https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BILL_OF_MATERIAL_SRV;v=0002/MaterialBOM Comm User : LEUWITEX_US_SAP_COM_0105 password user comm: Leuwitexsapcloud@2025 tabel : pz_material_bom https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BILL_OF_MATERIAL_SRV;v=0002/MaterialBOMItem Comm User : LEUWITEX_US_SAP_COM_0105 password user comm: Leuwitexsapcloud@2025 tabel : pz_material_bom_item
Note on B32: BC: https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BILL_OF_MATERIAL_SRV;v=0002/MaterialBOM Comm User : LEUWITEX_US_SAP_COM_0105 password user comm: Leuwitexsapcloud@2025 tabel : pz_material_bom https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BILL_OF_MATERIAL_SRV;v=0002/MaterialBOMItem Comm User : LEUWITEX_US_SAP_COM_0105 password user comm: Leuwitexsapcloud@2025 tabel : pz_material_bom_item

## f
RICEF BY LEUWITEX ( update 20 February 2026 )
| Project Start Date | 2025-11-25 |  |  |  | Display Week | 1 |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8
| Project Lead | Billy | [6 empty] | 2025-11-24 | [6 empty] | 2025-12-01 | [6 empty] | 2025-12-08 | [6 empty] | 2025-12-15 | [6 empty] | 2025-12-22 | [6 empty] | 2025-12-29 | [6 empty] | 2026-01-05 | [6 empty] | 2026-01-12
 | time axis 2025-11-24 to 2026-01-18
WBS | TASK | PIC | NOTES | START | END | DAYS | % DONE | WORK DAYS | time axis 2025-11-24 to 2026-01-18
1 | SAP API development |  |  |  | - |  |  | -
1.1 | INSTALL ECLIPSE, ADOBE LIFECYCLE DI PC | Baim, Budi |  | 2025-11-26 | 2025-11-26 | 1 | 100% | 1 | 2025-11-24: INSTALL ECLIPSE, ADOBE LIFECYCLE DI PC; 2025-11-25: TRUE
1.2 | BELAJAR KE SOLTIUS TENTANG SAP | Baim, Budi |  | 2025-11-27 | 2026-02-01 | 67 | 40% | 47 | 2025-11-24: BELAJAR KE SOLTIUS TENTANG SAP; 2025-11-25: TRUE
1.3 | INTEGRASI API SAP KE PRINT BARCODE INTERNAL | Baim, Budi |  | 2025-12-04 | 2025-12-10 | 7 | 100% | 5 | 2025-11-24: INTEGRASI API SAP KE PRINT BARCODE INTERNAL; 2025-11-25: TRUE
1.4 | MAPPING IT INVENTORY | Baim |  | 2025-12-18 | 2025-12-23 | 6 | 100% | 4 | 2025-11-24: MAPPING IT INVENTORY; 2025-11-25: TRUE
1.5 | BELAJAR MENDAFTARKAN API SAP | Baim, Budi |  | 2025-12-30 | 2025-12-30 | 1 | 100% | 1 | 2025-11-24: BELAJAR MENDAFTARKAN API SAP; 2025-11-25: TRUE
1.6 | MAPPING TABEL TAMBAHAN BEA CUKAI | Baim |  | 2025-12-30 | 2026-01-08 | 10 | 100% | 8 | 2025-11-24: MAPPING TABEL TAMBAHAN BEA CUKAI; 2025-11-25: TRUE
1.7 | SIT | Baim, Budi |  | 2026-01-06 | 2026-01-08 | 3 | 100% | 3 | 2025-11-24: SIT; 2025-11-25: TRUE
1.8 | INTEGRASI API SAP UNTUK BEA CUKAI | Baim |  | 2026-01-09 | 2026-01-18 | 10 | 0% | 6 | 2025-11-24: INTEGRASI API SAP UNTUK BEA CUKAI; 2025-11-25: TRUE
1.9 | BELAJAR MENGEDIT FORM SAP | Baim, Budi |  | 2026-01-08 | 2026-01-08 | 1 | 100% | 1 | 2025-11-24: BELAJAR MENGEDIT FORM SAP; 2025-11-25: TRUE
1.10 | KUT SAP BAGIAN MASTER DATA MM | Baim |  | 2026-01-15 | 2026-01-16 | 2 | 100% | 2 | 2025-11-24: KUT SAP BAGIAN MASTER DATA MM; 2025-11-25: TRUE
1.11 | KUT SAP BAGIAN MASTER DATA SD dan FICO | Budi |  | 2026-01-15 | 2026-01-16 | 2 | 100% | 2 | 2025-11-24: KUT SAP BAGIAN MASTER DATA SD dan FICO; 2025-11-25: TRUE
1.12 | Modifikasi Form Invoice (Barang Bekas, Avfal, BS, Maklon, Masker) | Baim |  | 2026-01-10 | 2026-01-21 | 12 | 90% | 8 | 2025-11-24: Modifikasi Form Invoice (Barang Bekas, Avfal, BS, Maklon, Masker); 2025-11-25: TRUE
1.13 | Modifikasi Form Surat Jalan (Barang Bekas, Avfal, BS, Maklon, Masker) | Budi |  | 2026-01-10 | 2026-01-21 | 12 | 75% | 8 | 2025-11-24: Modifikasi Form Surat Jalan (Barang Bekas, Avfal, BS, Maklon, Masker); 2025-11-25: TRUE
1.14 | Buat UI penarikan data dari API dan insert data Delivery | Baim |  | 2026-02-03 | 2026-02-04 | 2 | 100% | 2 | 2025-11-24: Buat UI penarikan data dari API dan insert data Delivery; 2025-11-25: TRUE
1.15 | Buat UI penarikan data dari API dan insert data Material | Budi |  | 2026-02-03 | 2026-02-04 | 2 | 100% | 2 | 2025-11-24: Buat UI penarikan data dari API dan insert data Material; 2025-11-25: TRUE
1.16 | Buat UI penarikan data dari API dan insert data Warehouse | Budi |  | 2026-02-05 | 2026-02-06 | 2 | 0% | 2 | 2025-11-24: Buat UI penarikan data dari API dan insert data Business User; 2025-11-25: FALSE
1.17 | Buat UI penarikan data dari API dan insert data Asset | Baim |  | 2026-02-05 | 2026-02-06 | 2 | 100% | 2 | 2025-11-24: Buat UI penarikan data dari API dan insert data Asset; 2025-11-25: TRUE
1.18 | Buat UI penarikan data dari API dan insert data Invoice | Budi |  | 2026-02-04 | 2026-02-05 | 2 | 100% | 2 | 2025-11-24: Buat UI penarikan data dari API dan insert data Invoice; 2025-11-25: TRUE
1.19 | Buat UI penarikan data dari API dan insert data Supplier | Baim |  | 2026-02-05 | 2026-02-06 | 2 | 100% | 2 | 2025-11-24: Buat UI penarikan data dari API dan insert data Delivery; 2025-11-25: FALSE
1.20 | Buat UI penarikan data dari API dan insert data Master Customer | Budi |  | 2026-02-07 | 2026-02-08 | 2 | 100% | 0 | 2025-11-24: Buat UI penarikan data dari API dan insert data Master Customer; 2025-11-25: TRUE
1.21 | Buat UI penarikan data dari API dan insert data PO | Baim |  | 2026-02-07 | 2026-02-08 | 2 | 100% | 0 | 2025-11-24: Buat UI penarikan data dari API dan insert data BOM; 2025-11-25: FALSE
1.22 | Buat UI penarikan data dari API dan insert data Material Document | Budi |  | 2026-02-09 | 2026-02-10 | 2 | 100% | 2 | 2025-11-24: Buat UI penarikan data dari API dan insert data Material Document; 2025-11-25: TRUE
1.23 | Buat UI penarikan data dari API dan insert data BOM | Baim |  | 2026-02-09 | 2026-02-10 | 2 | 100% | 2 | 2025-11-24: Buat UI penarikan data dari API dan insert data PO; 2025-11-25: FALSE
1.24 | UAT | Baim, Budi |  | 2026-02-11 | 2026-02-13 | 3 | 100% | 3 | 2025-11-24: Buat UI penarikan data dari API dan insert data Supplier; 2025-11-25: FALSE
1.25 | BBK INTERN | Budi |  | 2026-02-14 | 2026-02-18 | 5 | 0% | 3 | 2025-11-24: BBK INTERN; 2025-11-25: TRUE
1.26 | LAPORAN SURAT JALAN (P) | Baim |  | 2026-02-14 | 2026-02-18 | 5 | 100% | 3 | 2025-11-24: DASHBOARD LAYOUT PER BIN; 2025-11-25: FALSE
1.27 | DETAIL LIST KARTON PER RAK | Budi |  | 2026-02-19 | 2026-02-22 | 4 | 0% | 2 | 2025-11-24: DETAIL LIST KARTON PER RAK; 2025-11-25: TRUE
1.28 | LAPORAN GUDANG PACKING LEAD TIME | Baim |  | 2026-02-19 | 2026-02-22 | 4 | 50% | 2 | 2025-11-24: LAPORAN GUDANG PACKING LEAD TIME; 2025-11-25: TRUE
1.29 | LAPORAN PERSEDIAAN GUDANG PACKING | Budi |  | 2026-02-23 | 2026-02-24 | 2 | 0% | 2 | 2025-11-24: LAPORAN PERSEDIAAN GUDANG PACKING; 2025-11-25: TRUE
1.30 | DASHBOARD LAYOUT PER BIN | Baim |  | 2026-02-23 | 2026-02-24 | 2 | 0% | 2 | 2025-11-24: LAPORAN SURAT JALAN (P); 2025-11-25: FALSE
1.31 | LAPORAN SURAT JALAN SLOC | Budi |  | 2026-02-25 | 2026-02-26 | 2 | 0% | 2 | 2025-11-24: LAPORAN SURAT JALAN SLOC; 2025-11-25: TRUE
1.32 | LIST KARTON PER KODE ORDER | Baim |  | 2026-02-25 | 2026-02-26 | 2 | 50% | 2 | 2025-11-24: LIST KARTON PER KODE ORDER; 2025-11-25: TRUE
1.33 | LIST STK INTERN DAN EXTERN | Budi |  | 2026-02-27 | 2026-03-02 | 4 | 0% | 2 | 2025-11-24: LIST STK INTERN DAN EXTERN; 2025-11-25: TRUE
1.34 | MONITORING KAIN GREY | Baim |  | 2026-02-27 | 2026-03-02 | 4 | 0% | 2 | 2025-11-24: MONITORING KAIN GREY; 2025-11-25: TRUE
1.35 | MOVING HISTORY PER LIST KARTON | Budi |  | 2026-03-03 | 2026-03-04 | 2 | 0% | 2 | 2025-11-24: MOVING HISTORY PER LIST KARTON; 2025-11-25: TRUE
1.36 | MOVING HISTORY PER LIST BARCODE | Baim |  | 2026-03-03 | 2026-03-04 | 2 | 0% | 2 | 2025-11-24: MOVING HISTORY PER LIST BARCODE; 2025-11-25: TRUE
1.37 | REPORT CANCEL KAIN KELUAR | Budi |  | 2026-03-05 | 2026-03-06 | 2 | 0% | 2 | 2025-11-24: REPORT CANCEL KAIN KELUAR; 2025-11-25: TRUE
1.38 | REPORT CANCEL KAIN MASUK | Baim |  | 2026-03-05 | 2026-03-06 | 2 | 0% | 2 | 2025-11-24: REPORT CANCEL KAIN MASUK; 2025-11-25: TRUE
1.39 | REPORT COSTING | Budi |  | 2026-03-07 | 2026-03-10 | 4 | 0% | 2 | 2025-11-24: REPORT COSTING; 2025-11-25: TRUE
1.40 | REPORT PEMARTAIAN | Baim |  | 2026-03-07 | 2026-03-10 | 4 | 0% | 2 | 2025-11-24: REPORT PEMARTAIAN; 2025-11-25: TRUE
1.41 | REPORT RESERVASI | Budi |  | 2026-03-11 | 2026-03-12 | 2 | 0% | 2 | 2025-11-24: REPORT RESERVASI; 2025-11-25: TRUE
1.42 | REPORT RESUME KODE PARTAI | Baim |  | 2026-03-11 | 2026-03-12 | 2 | 0% | 2 | 2025-11-24: REPORT RESUME KODE PARTAI; 2025-11-25: TRUE
1.43 | STK BLANK GD. PACKING | Budi |  | 2026-03-13 | 2026-03-16 | 4 | 0% | 2 | 2025-11-24: STK BLANK GD. PACKING; 2025-11-25: TRUE
1.44 | STOCK BALANCE KAIN GREY | Baim |  | 2026-03-13 | 2026-03-16 | 4 | 0% | 2 | 2025-11-24: STOCK BALANCE KAIN GREY; 2025-11-25: TRUE
1.45 | STOCK GREY LEAD TIME PER GRADE | Budi |  | 2026-03-17 | 2026-03-18 | 2 | 0% | 2 | 2025-11-24: STOCK GREY LEAD TIME PER GRADE; 2025-11-25: TRUE
1.46 | STOCK KAIN GREY (GRADE) | Baim |  | 2026-03-17 | 2026-03-18 | 2 | 0% | 2 | 2025-11-24: STOCK KAIN GREY (GRADE); 2025-11-25: TRUE
1.47 | STOCK KAIN GREY (LW 22) | Budi |  | 2026-03-27 | 2026-03-28 | 2 | 0% | 1 | 2025-11-24: STOCK KAIN GREY (LW 22); 2025-11-25: TRUE
1.48 | STOCK KAIN PASIF (ALL AREA) | Baim |  | 2026-03-27 | 2026-03-28 | 2 | 0% | 1 | 2025-11-24: STOCK KAIN PASIF (ALL AREA); 2025-11-25: TRUE
1.49 | STOCK LEADTIME | Budi |  | 2026-03-29 | 2026-04-01 | 4 | 0% | 3 | 2025-11-24: STOCK LEADTIME; 2025-11-25: TRUE
1.50 | STOCK PER BARCODE | Baim |  | 2026-03-29 | 2026-04-01 | 4 | 0% | 3 | 2025-11-24: STOCK PER BARCODE; 2025-11-25: TRUE
1.51 | MOVING HISTORY - GUDANG GREY | Budi |  | 2026-04-02 | 2026-04-03 | 2 | 0% | 2 | 2025-11-24: #N/A; 2025-11-25: #N/A
1 | Report |  |  |  | - |  |  | -
1.1 | REPORT - WM - MOVING HISTORY - GUDANG GREY | Billy, Baim |  | 2026-02-04 | 2026-02-10 | 7 | 0% | 5
1.2 | REPORT - WM - STOCK PER BARCODE | Baim |  | 2026-02-11 | 2026-02-17 | 7 | 0% | 5
1.3 | REPORT - WM - LAPORAN PERSEDIAAN GUDANG PACKING | Budi |  | 2026-02-11 | 2026-02-17 | 7 | 0% | 5
1.4 | REPORT - WM - LAPORAN GUDANG PACKING LEAD TIME | Baim |  | 2026-02-18 | 2026-02-24 | 7 | 0% | 5
1.5 | REPORT - WM - LIST KARTON PER KODE ORDER | Budi |  | 2026-02-18 | 2026-02-24 | 7 | 0% | 5
1.6 | REPORT - WM - MOVING HISTORY PER BARCODE | Baim |  | 2026-02-25 | 2026-03-03 | 7 | 0% | 5
1.7 | REPORT - WM - MOVING HISTORY PER LIST KARTON | Budi |  | 2026-02-25 | 2026-03-03 | 7 | 0% | 5
1.8 | REPORT - MM - STOCK KAIN GREY (GRADE) | Billy, Budi |  | 2026-02-04 | 2026-02-10 | 7 | 0% | 5
1.9 | REPORT - MM - STOCK LEADTIME | Baim |  | 2026-03-04 | 2026-03-10 | 7 | 0% | 5
1.10 | REPORT - MM - STOCK GREY LEAD TIME PER GRADE | Budi |  | 2026-03-04 | 2026-03-10 | 7 | 0% | 5
1.11 | REPORT - MM - STOCK BALANCE KAIN GREY | Budi |  | 2026-03-11 | 2026-03-17 | 7 | 0% | 5
1.12 | REPORT - MM - STOCK KAIN PASIF (ALL AREA) | Baim |  | 2026-03-11 | 2026-03-17 | 7 | 0% | 5
1.13 | REPORT - MM - STOCK KAIN GREY (LW 22) | Budi |  | 2026-03-18 | 2026-03-24 | 7 | 0% | 5
1.14 | REPORT - MM - REPORT RESERVASI | Budi |  | 2026-03-25 | 2026-03-31 | 7 | 0% | 5
1.15 | REPORT - MM - REPORT PEMARTAIAN | Budi |  | 2026-03-25 | 2026-03-31 | 7 | 0% | 5
1.16 | REPORT - MM - REPORT RESUME KODE PARTAI | Budi |  | 2026-04-01 | 2026-04-07 | 7 | 0% | 5
1.17 | REPORT - MM - BBK INTERN | Baim |  | 2026-04-01 | 2026-04-07 | 7 | 0% | 5
1.18 | REPORT - MM - Report Cancel Kain Masuk | Budi |  | 2026-04-08 | 2026-04-14 | 7 | 0% | 5
1.19 | REPORT - MM - Report Cancel Kain Keluar | Baim |  | 2026-04-08 | 2026-04-14 | 7 | 0% | 5
1.20 | REPORT - MM - List STK Intern dan Extern | Budi |  | 2026-04-15 | 2026-04-21 | 7 | 0% | 5
1.21 | REPORT - MM - Laporan Surat Jalan Sloc | Baim |  | 2026-04-15 | 2026-04-21 | 7 | 0% | 5
1.22 | REPORT - MM - Laporan Surat Jalan (P) | Budi |  | 2026-04-22 | 2026-04-28 | 7 | 0% | 5
1.23 | REPORT - WM - DASHBOARD LAYOUT PER BIN | Baim |  | 2026-04-22 | 2026-04-28 | 7 | 0% | 5
1.24 | REPORT - WM - MONITORING KAIN GREY | Budi |  | 2026-04-29 | 2026-05-05 | 7 | 0% | 5
1.25 | REPORT - CO - REPORT COSTING | Budi |  | 2026-04-29 | 2026-05-05 | 7 | 0% | 5
1.26 | REPORT - WM - DETAIL LIST KARTON PER RAK | Budi |  | 2026-05-06 | 2026-05-12 | 7 | 0% | 5
1.27 | REPORT - MM - STK Blank Gd. Packing | Budi |  | 2026-05-06 | 2026-05-12 | 7 | 0% | 5
2 | Interfaces |  |  |  | - |  |  | -
2.1 | INTERFACE BEA CUKAI | Billy, Budi |  | 2026-01-12 | 2026-01-16 | 5 | 0% | 5
2.2 | INTERFACE PRINT BARCODE | Billy, Baim, Budi |  | 2026-01-01 | 2026-01-10 | 10 | 0% | 6
2.3 | INTERFACE PRINT BARCODE BANYAK LIST KARTON | Billy, Baim |  | 2026-01-12 | 2026-01-16 | 5 | 0% | 5
3 | Forms |  |  |  | - |  |  | -
3.1 | Form Transfer Posting (ZSCMF001) | Billy, Budi |  | 2026-01-19 | 2026-01-22 | 4 | 0% | 4
3.2 | Form Purchase Order (ZSCMF002) | Billy, Baim |  | 2026-01-19 | 2026-01-22 | 4 | 0% | 4
3.3 | Form Good Receipt (ZSCMF003) | Baim |  | 2026-01-23 | 2026-01-28 | 6 | 0% | 4
3.4 | Form Good Issue (ZSCMF004) | Baim |  | 2026-01-29 | 2026-02-03 | 6 | 0% | 4
3.5 | Form Bukti Tanda Terima | Budi |  | 2026-01-23 | 2026-01-28 | 6 | 0% | 4
4 | Enhancement |  |  |  | - |  |  | -
4.1 | Custom field for qty in PCS at Report Stock | Billy, Budi |  | 2026-01-29 | 2026-02-03 | 6 | 0% | 4
Note on A7: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet.
Note on B7: Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on C7: Task Lead Enter the name of the Task Lead in this column.
Note on E7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on F7: End Date: The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on G7: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on H7: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on I7: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.
Note on B23: BC: https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_PRODUCT_SRV//A_Product --> tabel pz_material https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_PRODUCT_SRV/A_ProductDescription --> tabel pz_material_description https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_PRODUCT_SRV/A_ProductPlant --> tabel pz_material_plant
Note on B24: $url = "https://my430621-api.s4hana.cloud.sap/sap/opu/odata4/sap/api_warehouse_order_task_2/srvd_a2x/sap/warehouseorder/0001/WarehouseTask"; $username = "LEUWITEX_US_SAP_COM_0353"; $password = "Leuwitexsapcloud@2025"; CREATE TABLE warehouse_task ( EWMWarehouse VARCHAR(20), WarehouseTask BIGINT, WarehouseTaskItem INT, WarehouseOrder BIGINT, WhseTaskCrtnUTCDateTime TIMESTAMP, WhseTaskLastChgUTCDateTime TIMESTAMP, WhseTaskConfUTCDateTime TIMESTAMP, ConfirmedByUser VARCHAR(50), WhseTaskPlannedClosingDateTime TIMESTAMP, WhseTaskGoodsReceiptDateTime TIMESTAMP, WarehouseTaskStatus CHAR(1), WarehouseProcessType VARCHAR(10), WarehouseProcessCategory INT, IsHandlingUnitWarehouseTask BOOLEAN, EWMHandlingUnitType VARCHAR(50), HomogeneousFullPalletPick VARCHAR(50), Product VARCHAR(50), Batch VARCHAR(20), BatchChangeIsNotAllowed BOOLEAN, CountryOfOrigin VARCHAR(50), ShelfLifeExpirationDate DATE, EWMStockType CHAR(1), EWMStockUsage VARCHAR(50), EWMStockOwner BIGINT, EntitledToDisposeParty BIGINT, WBSElementInternalID INT, WBSElementExternalID VARCHAR(50), SpecialStockIdfgSalesOrder VARCHAR(50), SpecialStockIdfgSalesOrderItem INT, ExecutingResource VARCHAR(50), WarehouseMovementsReason VARCHAR(50), ProductionOrder VARCHAR(50), EWMProductionSupplyArea VARCHAR(50), EWMDocumentCategory VARCHAR(10), EWMReferenceDocumentCategory VARCHAR(10), PDO VARCHAR(10), EWMWave INT, EWMWaveItem INT, EWMDelivery BIGINT, EWMDeliveryItem INT, PurchasingDocument BIGINT, PurchasingDocumentItem INT, SalesDocument VARCHAR(50), SalesDocumentItem INT, BaseUnit VARCHAR(10), EWMBaseUnitISOCode VARCHAR(10), AlternativeUnit VARCHAR(10), EWMAlternativeUnitISOCode VARCHAR(10), TargetQuantityInBaseUnit NUMERIC, TargetQuantityInAltvUnit NUMERIC, ActualQuantityInBaseUnit NUMERIC, ActualQuantityInAltvUnit NUMERIC, DifferenceQuantityInBaseUnit NUMERIC, DifferenceQuantityInAltvUnit NUMERIC, WhseTaskNetWeightUnitOfMeasure VARCHAR(10), WhseTaskNetWeight NUMERIC, WhseTaskNetVolumeUnitOfMeasure VARCHAR(10), WhseTaskNetVolume NUMERIC, SourceStorageType VARCHAR(10), SourceStorageSection VARCHAR(10), SourceStorageBin VARCHAR(20), SourceResource VARCHAR(50), DestinationStorageType VARCHAR(10), DestinationStorageSection VARCHAR(10), DestinationStorageBin VARCHAR(20), DestinationResource VARCHAR(50), ActivityArea VARCHAR(10), SourceHandlingUnit VARCHAR(50), DestinationHandlingUnit VARCHAR(50), WarehouseTaskExceptionCode VARCHAR(10), WhseTaskSortingSequenceValue INT, WarehouseOrderSequenceValue INT, WarehouseOrderActivityArea VARCHAR(10), WarehouseOrderCreationRule VARCHAR(10), WarehouseOrderQueue VARCHAR(50), WarehouseActivityType VARCHAR(10), EWMConsolidationGroup BIGINT, EWMWarehouseTaskPriority INT, CreatedByUser VARCHAR(50), EWMRoute VARCHAR(50), EWMWaveCategory VARCHAR(50), EWMCanceledWarehouseTask INT, SerialNumberRequiredLevel VARCHAR(10) );
Note on B25: BC: https://my430621-api.s4hana.cloud.sap/sap/opu/odata4/sap/api_fixedasset/srvd_a2x/sap/fixedasset/0001/FixedAsset Username : LEUWITEX_US_SAP_COM_0A93 Password : Leuwitexsapcloud@2025" tabel : pz_fixed_asset https://my430621-api.s4hana.cloud.sap/sap/opu/odata4/sap/api_fixedasset/srvd_a2x/sap/fixedasset/0001/FixedAssetLedger Username : LEUWITEX_US_SAP_COM_0A93 Password : Leuwitexsapcloud@2025" tabel : pz_fixed_asset_ledger
Note on B26: BC: https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BILLING_DOCUMENT_SRV/A_BillingDocument Comm User : LEUWITEX_US_SAP_COM_0120 password user comm: Leuwitexsapcloud@2025 tabel : pz_billing_document https://my430621-api.s4hana.cloud.sap/sap/opu/odata4/sap/api_billingdocument/srvd_a2x/sap/billingdocument/0001/BillingDocumentItem Comm User : LEUWITEX_US_SAP_COM_0120 password user comm: Leuwitexsapcloud@2025 tabel : pz_billing_document_item https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_SALES_ORDER_SRV/A_SalesOrder Comm User : LEUWITEX_US_SAP_COM_0109 password user comm: Leuwitexsapcloud@2025 tabel : pz_sales_order
Note on B27: https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BUSINESS_PARTNER/A_Supplier Username : LEUWITEX_US_SAP_COM_0008 SupplierFullName Bechtle AG Kriek street Password : \W+M)hw&kj]WHnSJ>UmhdB(f56N>\Zk9caxMY=5L CREATE TABLE pz_supplier ( supplier VARCHAR(20) PRIMARY KEY, supplier_full_name VARCHAR(100), created_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP, updated_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP ); https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BUSINESS_PARTNER/A_AddressEmailAddress Username : LEUWITEX_US_SAP_COM_0008 Password : \W+M)hw&kj]WHnSJ>UmhdB(f56N>\Zk9caxMY=5L CREATE TABLE pz_address_email_address ( email_address VARCHAR(100) NOT NULL, person VARCHAR(50), address_id VARCHAR(50), created_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP, updated_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP, PRIMARY KEY (email_address) ); https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BUSINESS_PARTNER/A_BusinessPartnerAddress Username : LEUWITEX_US_SAP_COM_0008 Password : \W+M)hw&kj]WHnSJ>UmhdB(f56N>\Zk9caxMY=5L CREATE TABLE pz_business_partner_address ( country VARCHAR(50), postal_code VARCHAR(20), region VARCHAR(100), district VARCHAR(100), business_partner VARCHAR(20), address_id VARCHAR(50), created_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP, updated_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP ); https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BUSINESS_PARTNER/A_AddressHomePageURL Username : LEUWITEX_US_SAP_COM_0008 Password : \W+M)hw&kj]WHnSJ>UmhdB(f56N>\Zk9caxMY=5L CREATE TABLE pz_address_home_page_url ( website_url VARCHAR(200) NOT NULL, address_id VARCHAR(50), -- Audit columns created_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP, updated_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP, PRIMARY KEY (website_url) ); https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BUSINESS_PARTNER/A_AddressPhoneNumber Username : LEUWITEX_US_SAP_COM_0008 Password : \W+M)hw&kj]WHnSJ>UmhdB(f56N>\Zk9caxMY=5L CREATE TABLE pz_address_phone_number ( phone_number VARCHAR(50) NOT NULL, address_id VARCHAR(50), created_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP, updated_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP ); https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BUSINESS_PARTNER/A_BuPaIdentification Username : LEUWITEX_US_SAP_COM_0008 Password : \W+M)hw&kj]WHnSJ>UmhdB(f56N>\Zk9caxMY=5L CREATE TABLE pz_bu_pa_identification ( npwp_vendor VARCHAR(30) NOT NULL, business_partner VARCHAR(20), created_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP, updated_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP ); https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BUSINESS_PARTNER/A_AddressFaxNumber Username : LEUWITEX_US_SAP_COM_0008 Password : \W+M)hw&kj]WHnSJ>UmhdB(f56N>\Zk9caxMY=5L CREATE TABLE pz_bu_address_fax_number ( fax_number VARCHAR(50) NOT NULL, address_id VARCHAR(50), created_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP, updated_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP );
Note on B28: https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BUSINESS_PARTNER/A_BusinessPartnerAddress UserName : LEUWITEX_US_SAP_COM_0008 Password : \W+M)hw&kj]WHnSJ>UmhdB(f56N>\Zk9caxMY=5L tabel : pz_business_partner_address https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BUSINESS_PARTNER/A_Customer UserName : LEUWITEX_US_SAP_COM_0008 Password : \W+M)hw&kj]WHnSJ>UmhdB(f56N>\Zk9caxMY=5L tabel : pz_customer https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BUSINESS_PARTNER/A_Customer('9200000010')/to_CustomerSalesArea UserName : LEUWITEX_US_SAP_COM_0008 Password : \W+M)hw&kj]WHnSJ>UmhdB(f56N>\Zk9caxMY=5L tabel : pz_customer_sales_area https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BUSINESS_PARTNER/A_BusinessPartnerTaxNumber UserName : LEUWITEX_US_SAP_COM_0008 Password : \W+M)hw&kj]WHnSJ>UmhdB(f56N>\Zk9caxMY=5L tabel : pz_business_partner_tax_number https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BUSINESS_PARTNER/A_CustSalesPartnerFunc UserName : LEUWITEX_US_SAP_COM_0008 Password : \W+M)hw&kj]WHnSJ>UmhdB(f56N>\Zk9caxMY=5L tabel : pz_cust_sales_partner_func
Note on B29: BC: https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BILL_OF_MATERIAL_SRV;v=0002/MaterialBOM Comm User : LEUWITEX_US_SAP_COM_0105 password user comm: Leuwitexsapcloud@2025 tabel : pz_material_bom https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BILL_OF_MATERIAL_SRV;v=0002/MaterialBOMItem Comm User : LEUWITEX_US_SAP_COM_0105 password user comm: Leuwitexsapcloud@2025 tabel : pz_material_bom_item
Note on B30: https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_MATERIAL_DOCUMENT_SRV/A_MaterialDocumentHeader Username : LEUWITEX_US_SAP_COM_0108 Password : Leuwitexsapcloud@2025 table pz_material_document_header https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_MATERIAL_DOCUMENT_SRV//A_MaterialDocumentItem Username : LEUWITEX_US_SAP_COM_0108 Password : Leuwitexsapcloud@2025 table pz_material_document_item
Note on B31: BC: https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BILL_OF_MATERIAL_SRV;v=0002/MaterialBOM Comm User : LEUWITEX_US_SAP_COM_0105 password user comm: Leuwitexsapcloud@2025 tabel : pz_material_bom https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BILL_OF_MATERIAL_SRV;v=0002/MaterialBOMItem Comm User : LEUWITEX_US_SAP_COM_0105 password user comm: Leuwitexsapcloud@2025 tabel : pz_material_bom_item
Note on B32: BC: https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BILL_OF_MATERIAL_SRV;v=0002/MaterialBOM Comm User : LEUWITEX_US_SAP_COM_0105 password user comm: Leuwitexsapcloud@2025 tabel : pz_material_bom https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BILL_OF_MATERIAL_SRV;v=0002/MaterialBOMItem Comm User : LEUWITEX_US_SAP_COM_0105 password user comm: Leuwitexsapcloud@2025 tabel : pz_material_bom_item

## e
RICEF BY LEUWITEX ( update 3 February 2026 )
| Project Start Date | 2025-11-25 |  |  |  | Display Week | 1 |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8
| Project Lead | Billy | [6 empty] | 2025-11-24 | [6 empty] | 2025-12-01 | [6 empty] | 2025-12-08 | [6 empty] | 2025-12-15 | [6 empty] | 2025-12-22 | [6 empty] | 2025-12-29 | [6 empty] | 2026-01-05 | [6 empty] | 2026-01-12
 | time axis 2025-11-24 to 2026-01-18
WBS | TASK | PIC | PREDECESSOR | START | END | DAYS | % DONE | WORK DAYS | time axis 2025-11-24 to 2026-01-18
1 | SAP API development |  |  |  | - |  |  | -
1.1 | INSTALL ECLIPSE, ADOBE LIFECYCLE DI PC | Baim, Budi |  | 2025-11-26 | 2025-11-26 | 1 | 100% | 1
1.2 | BELAJAR KE SOLTIUS TENTANG SAP | Baim, Budi |  | 2025-11-27 | 2026-02-01 | 67 | 40% | 47
1.3 | INTEGRASI API SAP KE PRINT BARCODE INTERNAL | Baim, Budi |  | 2025-12-04 | 2025-12-10 | 7 | 100% | 5
1.4 | MAPPING IT INVENTORY | Baim |  | 2025-12-18 | 2025-12-23 | 6 | 100% | 4
1.5 | BELAJAR MENDAFTARKAN API SAP | Baim, Budi |  | 2025-12-30 | 2025-12-30 | 1 | 100% | 1
1.6 | MAPPING TABEL TAMBAHAN BEA CUKAI | Baim |  | 2025-12-30 | 2026-01-08 | 10 | 100% | 8
1.7 | SIT | Baim, Budi |  | 2026-01-06 | 2026-01-08 | 3 | 100% | 3
1.8 | INTEGRASI API SAP UNTUK BEA CUKAI | Baim |  | 2026-01-09 | 2026-01-18 | 10 | 0% | 6
1.9 | BELAJAR MENGEDIT FORM SAP | Baim, Budi |  | 2026-01-08 | 2026-01-08 | 1 | 100% | 1
1.10 | KUT SAP BAGIAN MASTER DATA MM | Baim |  | 2026-01-15 | 2026-01-16 | 2 | 100% | 2
1.11 | KUT SAP BAGIAN MASTER DATA SD dan FICO | Budi |  | 2026-01-15 | 2026-01-16 | 2 | 100% | 2
1.12 | Modifikasi Form Invoice (Barang Bekas, Avfal, BS, Maklon, Masker) | Baim |  | 2026-01-10 | 2026-01-21 | 12 | 90% | 8
1.13 | Modifikasi Form Surat Jalan (Barang Bekas, Avfal, BS, Maklon, Masker) | Budi |  | 2026-01-10 | 2026-01-21 | 12 | 75% | 8
1.14 | Buat UI penarikan data dari API dan insert data Delivery | Baim |  | 2026-02-03 | 2026-02-04 | 2 | 100% | 2
1.15 | Buat UI penarikan data dari API dan insert data Material | Budi |  | 2026-02-03 | 2026-02-04 | 2 | 0% | 2
1.16 | Buat UI penarikan data dari API dan insert data Business User | Budi |  | 2026-02-05 | 2026-02-06 | 2 | 0% | 2
1.17 | Buat UI penarikan data dari API dan insert data Asset | Baim |  | 2026-02-05 | 2026-02-06 | 2 | 100% | 2
1.18 | Buat UI penarikan data dari API dan insert data Invoice | Budi |  | 2026-02-04 | 2026-02-05 | 2 | 0% | 2
1.19 | Buat UI penarikan data dari API dan insert data Delivery | Baim |  | 2026-02-05 | 2026-02-06 | 2 | 100% | 2
1.20 | Buat UI penarikan data dari API dan insert data Master Customer | Budi |  | 2026-02-07 | 2026-02-08 | 2 | 0% | 0
1.21 | Buat UI penarikan data dari API dan insert data BOM | Baim |  | 2026-02-07 | 2026-02-08 | 2 | 100% | 0
1.22 | Buat UI penarikan data dari API dan insert data Material Document | Budi |  | 2026-02-07 | 2026-02-08 | 2 | 0% | 0
1.23 | Buat UI penarikan data dari API dan insert data PO | Baim |  | 2026-02-07 | 2026-02-08 | 2 | 100% | 0
1.24 | Buat UI penarikan data dari API dan insert data Supplier | Baim |  | 2026-02-04 | 2026-02-05 | 2 | 100% | 2
1.25 | BBK INTERN | Budi |  | 2026-02-09 | 2026-02-10 | 2 | 0% | 2
1.26 | DASHBOARD LAYOUT PER BIN | Baim |  | 2026-02-09 | 2026-02-10 | 2 | 0% | 2
1.27 | DETAIL LIST KARTON PER RAK | Budi |  | 2026-02-11 | 2026-02-12 | 2 | 0% | 2
1.28 | LAPORAN GUDANG PACKING LEAD TIME | Baim |  | 2026-02-11 | 2026-02-12 | 2 | 0% | 2
1.29 | LAPORAN PERSEDIAAN GUDANG PACKING | Budi |  | 2026-02-13 | 2026-02-14 | 2 | 0% | 1
1.30 | LAPORAN SURAT JALAN (P) | Baim |  | 2026-02-13 | 2026-02-14 | 2 | 0% | 1
1.31 | LAPORAN SURAT JALAN SLOC | Budi |  | 2026-02-15 | 2026-02-16 | 2 | 0% | 1
1.32 | LIST KARTON PER KODE ORDER | Baim |  | 2026-02-15 | 2026-02-16 | 2 | 0% | 1
1.33 | LIST STK INTERN DAN EXTERN | Budi |  | 2026-02-17 | 2026-02-18 | 2 | 0% | 2
1.34 | MONITORING KAIN GREY | Baim |  | 2026-02-17 | 2026-02-18 | 2 | 0% | 2
1.35 | MOVING HISTORY PER LIST KARTON | Budi |  | 2026-02-19 | 2026-02-20 | 2 | 0% | 2
1.36 | MOVING HISTORY PER LIST BARCODE | Baim |  | 2026-02-19 | 2026-02-20 | 2 | 0% | 2
1.37 | REPORT CANCEL KAIN KELUAR | Budi |  | 2026-02-21 | 2026-02-22 | 2 | 0% | 0
1.38 | REPORT CANCEL KAIN MASUK | Baim |  | 2026-02-21 | 2026-02-22 | 2 | 0% | 0
1.39 | REPORT COSTING | Budi |  | 2026-02-23 | 2026-02-24 | 2 | 0% | 2
1.40 | REPORT PEMARTAIAN | Baim |  | 2026-02-23 | 2026-02-24 | 2 | 0% | 2
1.41 | REPORT RESERVASI | Budi |  | 2026-02-25 | 2026-02-26 | 2 | 0% | 2
1.42 | REPORT RESUME KODE PARTAI | Baim |  | 2026-02-25 | 2026-02-26 | 2 | 0% | 2
1.43 | STK BLANK GD. PACKING | Budi |  | 2026-02-27 | 2026-02-28 | 2 | 0% | 1
1.44 | STOCK BALANCE KAIN GREY | Baim |  | 2026-02-27 | 2026-02-28 | 2 | 0% | 1
1.45 | STOCK GREY LEAD TIME PER GRADE | Budi |  | 2026-03-01 | 2026-03-02 | 2 | 0% | 1
1.46 | STOCK KAIN GREY (GRADE) | Baim |  | 2026-03-01 | 2026-03-02 | 2 | 0% | 1
1.47 | STOCK KAIN GREY (LW 22) | Budi |  | 2026-03-03 | 2026-03-04 | 2 | 0% | 2
1.48 | STOCK KAIN PASIF (ALL AREA) | Baim |  | 2026-03-03 | 2026-03-04 | 2 | 0% | 2
1.49 | STOCK LEADTIME | Budi |  | 2026-03-05 | 2026-03-06 | 2 | 0% | 2
1.50 | STOCK PER BARCODE | Baim |  | 2026-03-05 | 2026-03-06 | 2 | 0% | 2
1.51 | MOVING HISTORY - GUDANG GREY | Budi |  | 2026-03-07 | 2026-03-08 | 2 | 0% | 0
1 | Report |  |  |  | - |  |  | -
1.1 | REPORT - WM - MOVING HISTORY - GUDANG GREY | Billy, Baim |  | 2026-02-04 | 2026-02-10 | 7 | 0% | 5
1.2 | REPORT - WM - STOCK PER BARCODE | Baim |  | 2026-02-11 | 2026-02-17 | 7 | 0% | 5
1.3 | REPORT - WM - LAPORAN PERSEDIAAN GUDANG PACKING | Budi |  | 2026-02-11 | 2026-02-17 | 7 | 0% | 5
1.4 | REPORT - WM - LAPORAN GUDANG PACKING LEAD TIME | Baim |  | 2026-02-18 | 2026-02-24 | 7 | 0% | 5
1.5 | REPORT - WM - LIST KARTON PER KODE ORDER | Budi |  | 2026-02-18 | 2026-02-24 | 7 | 0% | 5
1.6 | REPORT - WM - MOVING HISTORY PER BARCODE | Baim |  | 2026-02-25 | 2026-03-03 | 7 | 0% | 5
1.7 | REPORT - WM - MOVING HISTORY PER LIST KARTON | Budi |  | 2026-02-25 | 2026-03-03 | 7 | 0% | 5
1.8 | REPORT - MM - STOCK KAIN GREY (GRADE) | Billy, Budi |  | 2026-02-04 | 2026-02-10 | 7 | 0% | 5
1.9 | REPORT - MM - STOCK LEADTIME | Baim |  | 2026-03-04 | 2026-03-10 | 7 | 0% | 5
1.10 | REPORT - MM - STOCK GREY LEAD TIME PER GRADE | Budi |  | 2026-03-04 | 2026-03-10 | 7 | 0% | 5
1.11 | REPORT - MM - STOCK BALANCE KAIN GREY | Budi |  | 2026-03-11 | 2026-03-17 | 7 | 0% | 5
1.12 | REPORT - MM - STOCK KAIN PASIF (ALL AREA) | Baim |  | 2026-03-11 | 2026-03-17 | 7 | 0% | 5
1.13 | REPORT - MM - STOCK KAIN GREY (LW 22) | Budi |  | 2026-03-18 | 2026-03-24 | 7 | 0% | 5
1.14 | REPORT - MM - REPORT RESERVASI | Budi |  | 2026-03-25 | 2026-03-31 | 7 | 0% | 5
1.15 | REPORT - MM - REPORT PEMARTAIAN | Budi |  | 2026-03-25 | 2026-03-31 | 7 | 0% | 5
1.16 | REPORT - MM - REPORT RESUME KODE PARTAI | Budi |  | 2026-04-01 | 2026-04-07 | 7 | 0% | 5
1.17 | REPORT - MM - BBK INTERN | Baim |  | 2026-04-01 | 2026-04-07 | 7 | 0% | 5
1.18 | REPORT - MM - Report Cancel Kain Masuk | Budi |  | 2026-04-08 | 2026-04-14 | 7 | 0% | 5
1.19 | REPORT - MM - Report Cancel Kain Keluar | Baim |  | 2026-04-08 | 2026-04-14 | 7 | 0% | 5
1.20 | REPORT - MM - List STK Intern dan Extern | Budi |  | 2026-04-15 | 2026-04-21 | 7 | 0% | 5
1.21 | REPORT - MM - Laporan Surat Jalan Sloc | Baim |  | 2026-04-15 | 2026-04-21 | 7 | 0% | 5
1.22 | REPORT - MM - Laporan Surat Jalan (P) | Budi |  | 2026-04-22 | 2026-04-28 | 7 | 0% | 5
1.23 | REPORT - WM - DASHBOARD LAYOUT PER BIN | Baim |  | 2026-04-22 | 2026-04-28 | 7 | 0% | 5
1.24 | REPORT - WM - MONITORING KAIN GREY | Budi |  | 2026-04-29 | 2026-05-05 | 7 | 0% | 5
1.25 | REPORT - CO - REPORT COSTING | Budi |  | 2026-04-29 | 2026-05-05 | 7 | 0% | 5
1.26 | REPORT - WM - DETAIL LIST KARTON PER RAK | Budi |  | 2026-05-06 | 2026-05-12 | 7 | 0% | 5
1.27 | REPORT - MM - STK Blank Gd. Packing | Budi |  | 2026-05-06 | 2026-05-12 | 7 | 0% | 5
2 | Interfaces |  |  |  | - |  |  | -
2.1 | INTERFACE BEA CUKAI | Billy, Budi |  | 2026-01-12 | 2026-01-16 | 5 | 0% | 5
2.2 | INTERFACE PRINT BARCODE | Billy, Baim, Budi |  | 2026-01-01 | 2026-01-10 | 10 | 0% | 6
2.3 | INTERFACE PRINT BARCODE BANYAK LIST KARTON | Billy, Baim |  | 2026-01-12 | 2026-01-16 | 5 | 0% | 5
3 | Forms |  |  |  | - |  |  | -
3.1 | Form Transfer Posting (ZSCMF001) | Billy, Budi |  | 2026-01-19 | 2026-01-22 | 4 | 0% | 4
3.2 | Form Purchase Order (ZSCMF002) | Billy, Baim |  | 2026-01-19 | 2026-01-22 | 4 | 0% | 4
3.3 | Form Good Receipt (ZSCMF003) | Baim |  | 2026-01-23 | 2026-01-28 | 6 | 0% | 4
3.4 | Form Good Issue (ZSCMF004) | Baim |  | 2026-01-29 | 2026-02-03 | 6 | 0% | 4
3.5 | Form Bukti Tanda Terima | Budi |  | 2026-01-23 | 2026-01-28 | 6 | 0% | 4
4 | Enhancement |  |  |  | - |  |  | -
4.1 | Custom field for qty in PCS at Report Stock | Billy, Budi |  | 2026-01-29 | 2026-02-03 | 6 | 0% | 4
Note on A7: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet.
Note on B7: Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on C7: Task Lead Enter the name of the Task Lead in this column.
Note on D7: Predecessor Tasks: You can use this column to enter the WBS of a predecessor for reference. The PRO version uses formulas to automatically calculate the Start Date based on the Predecessor.
Note on E7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on F7: End Date: The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on G7: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on H7: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on I7: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.
Note on B23: BC: https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_PRODUCT_SRV//A_Product --> tabel pz_material https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_PRODUCT_SRV/A_ProductDescription --> tabel pz_material_description https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_PRODUCT_SRV/A_ProductPlant --> tabel pz_material_plant
Note on B32: https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BUSINESS_PARTNER/A_Supplier Username : LEUWITEX_US_SAP_COM_0008 SupplierFullName Bechtle AG Kriek street Password : \W+M)hw&kj]WHnSJ>UmhdB(f56N>\Zk9caxMY=5L CREATE TABLE pz_supplier ( supplier VARCHAR(20) PRIMARY KEY, supplier_full_name VARCHAR(100), created_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP, updated_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP ); https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BUSINESS_PARTNER/A_AddressEmailAddress Username : LEUWITEX_US_SAP_COM_0008 Password : \W+M)hw&kj]WHnSJ>UmhdB(f56N>\Zk9caxMY=5L CREATE TABLE pz_address_email_address ( email_address VARCHAR(100) NOT NULL, person VARCHAR(50), address_id VARCHAR(50), created_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP, updated_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP, PRIMARY KEY (email_address) ); https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BUSINESS_PARTNER/A_BusinessPartnerAddress Username : LEUWITEX_US_SAP_COM_0008 Password : \W+M)hw&kj]WHnSJ>UmhdB(f56N>\Zk9caxMY=5L CREATE TABLE pz_business_partner_address ( country VARCHAR(50), postal_code VARCHAR(20), region VARCHAR(100), district VARCHAR(100), business_partner VARCHAR(20), address_id VARCHAR(50), created_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP, updated_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP ); https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BUSINESS_PARTNER/A_AddressHomePageURL Username : LEUWITEX_US_SAP_COM_0008 Password : \W+M)hw&kj]WHnSJ>UmhdB(f56N>\Zk9caxMY=5L CREATE TABLE pz_address_home_page_url ( website_url VARCHAR(200) NOT NULL, address_id VARCHAR(50), -- Audit columns created_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP, updated_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP, PRIMARY KEY (website_url) ); https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BUSINESS_PARTNER/A_AddressPhoneNumber Username : LEUWITEX_US_SAP_COM_0008 Password : \W+M)hw&kj]WHnSJ>UmhdB(f56N>\Zk9caxMY=5L CREATE TABLE pz_address_phone_number ( phone_number VARCHAR(50) NOT NULL, address_id VARCHAR(50), created_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP, updated_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP ); https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BUSINESS_PARTNER/A_BuPaIdentification Username : LEUWITEX_US_SAP_COM_0008 Password : \W+M)hw&kj]WHnSJ>UmhdB(f56N>\Zk9caxMY=5L CREATE TABLE pz_bu_pa_identification ( npwp_vendor VARCHAR(30) NOT NULL, business_partner VARCHAR(20), created_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP, updated_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP ); https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_BUSINESS_PARTNER/A_AddressFaxNumber Username : LEUWITEX_US_SAP_COM_0008 Password : \W+M)hw&kj]WHnSJ>UmhdB(f56N>\Zk9caxMY=5L CREATE TABLE pz_bu_address_fax_number ( fax_number VARCHAR(50) NOT NULL, address_id VARCHAR(50), created_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP, updated_at TIMESTAMP DEFAULT CURRENT_TIMESTAMP );

## d
RICEF BY LEUWITEX ( update 31 January 2026 )
| Project Start Date | 2025-11-25 |  |  |  | Display Week | 1 |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8
| Project Lead | Billy | [6 empty] | 2025-11-24 | [6 empty] | 2025-12-01 | [6 empty] | 2025-12-08 | [6 empty] | 2025-12-15 | [6 empty] | 2025-12-22 | [6 empty] | 2025-12-29 | [6 empty] | 2026-01-05 | [6 empty] | 2026-01-12
 | time axis 2025-11-24 to 2026-01-18
WBS | TASK | PIC | PREDECESSOR | START | END | DAYS | % DONE | WORK DAYS | time axis 2025-11-24 to 2026-01-18
1 | SAP API development |  |  |  | - |  |  | -
1.1 | INSTALL ECLIPSE, ADOBE LIFECYCLE DI PC | Baim, Budi |  | 2025-11-26 | 2025-11-26 | 1 | 100% | 1
1.2 | BELAJAR KE SOLTIUS TENTANG SAP | Baim, Budi |  | 2025-11-27 | 2026-02-01 | 67 | 40% | 47
1.3 | INTEGRASI API SAP KE PRINT BARCODE INTERNAL | Baim, Budi |  | 2025-12-04 | 2025-12-10 | 7 | 100% | 5
1.4 | MAPPING IT INVENTORY | Baim |  | 2025-12-18 | 2025-12-23 | 6 | 100% | 4
1.5 | BELAJAR MENDAFTARKAN API SAP | Baim, Budi |  | 2025-12-30 | 2025-12-30 | 1 | 100% | 1
1.6 | MAPPING TABEL TAMBAHAN BEA CUKAI | Baim |  | 2025-12-30 | 2026-01-08 | 10 | 100% | 8
1.7 | SIT | Baim, Budi |  | 2026-01-06 | 2026-01-08 | 3 | 100% | 3
1.8 | INTEGRASI API SAP UNTUK BEA CUKAI | Baim |  | 2026-01-09 | 2026-01-18 | 10 | 0% | 6
1.9 | BELAJAR MENGEDIT FORM SAP | Baim, Budi |  | 2026-01-08 | 2026-01-08 | 1 | 100% | 1
1.10 | KUT SAP BAGIAN MASTER DATA MM | Baim |  | 2026-01-15 | 2026-01-16 | 2 | 100% | 2
1.11 | KUT SAP BAGIAN MASTER DATA SD dan FICO | Budi |  | 2026-01-15 | 2026-01-16 | 2 | 100% | 2
1.12 | Modifikasi Form Invoice (Barang Bekas, Avfal, BS, Maklon, Masker) | Baim |  | 2026-01-10 | 2026-01-21 | 12 | 90% | 8
1.13 | Modifikasi Form Surat Jalan (Barang Bekas, Avfal, BS, Maklon, Masker) | Budi |  | 2026-01-10 | 2026-01-21 | 12 | 75% | 8
1.14 | Buat UI penarikan data dari API dan insert data Master Supplier | Baim |  | 2026-02-03 | 2026-02-04 | 2 | 100% | 2
1.15 | Buat UI penarikan data dari API dan insert data Material | Budi |  | 2026-02-03 | 2026-02-04 | 2 | 0% | 2
1.16 | Buat UI penarikan data dari API dan insert data Business User | Budi |  | 2026-02-05 | 2026-02-06 | 2 | 0% | 2
1.17 | Buat UI penarikan data dari API dan insert data Asset | Baim |  | 2026-02-05 | 2026-02-06 | 2 | 0% | 2
1.18 | Buat UI penarikan data dari API dan insert data Invoice | Budi |  | 2026-02-04 | 2026-02-05 | 2 | 0% | 2
1.19 | Buat UI penarikan data dari API dan insert data Delivery | Baim |  | 2026-02-05 | 2026-02-06 | 2 | 100% | 2
1.20 | Buat UI penarikan data dari API dan insert data Master Customer | Budi |  | 2026-02-07 | 2026-02-08 | 2 | 0% | 0
1.21 | Buat UI penarikan data dari API dan insert data BOM | Baim |  | 2026-02-07 | 2026-02-08 | 2 | 0% | 0
1.22 | Buat UI penarikan data dari API dan insert data Material Document | Budi |  | 2026-02-07 | 2026-02-08 | 2 | 0% | 0
1.23 | Buat UI penarikan data dari API dan insert data PO | Baim |  | 2026-02-07 | 2026-02-08 | 2 | 100% | 0
1.24 | BBK INTERN | Budi |  | 2026-02-09 | 2026-02-10 | 2 | 0% | 2
1.25 | DASHBOARD LAYOUT PER BIN | Baim |  | 2026-02-09 | 2026-02-10 | 2 | 0% | 2
1.26 | DETAIL LIST KARTON PER RAK | Budi |  | 2026-02-11 | 2026-02-12 | 2 | 0% | 2
1.27 | LAPORAN GUDANG PACKING LEAD TIME | Baim |  | 2026-02-11 | 2026-02-12 | 2 | 0% | 2
1.28 | LAPORAN PERSEDIAAN GUDANG PACKING | Budi |  | 2026-02-13 | 2026-02-14 | 2 | 0% | 1
1.29 | LAPORAN SURAT JALAN (P) | Baim |  | 2026-02-13 | 2026-02-14 | 2 | 0% | 1
1.30 | LAPORAN SURAT JALAN SLOC | Budi |  | 2026-02-15 | 2026-02-16 | 2 | 0% | 1
1.31 | LIST KARTON PER KODE ORDER | Baim |  | 2026-02-15 | 2026-02-16 | 2 | 0% | 1
1.32 | LIST STK INTERN DAN EXTERN | Budi |  | 2026-02-17 | 2026-02-18 | 2 | 0% | 2
1.33 | MONITORING KAIN GREY | Baim |  | 2026-02-17 | 2026-02-18 | 2 | 0% | 2
1.34 | MOVING HISTORY PER LIST KARTON | Budi |  | 2026-02-19 | 2026-02-20 | 2 | 0% | 2
1.35 | MOVING HISTORY PER LIST BARCODE | Baim |  | 2026-02-19 | 2026-02-20 | 2 | 0% | 2
1.36 | REPORT CANCEL KAIN KELUAR | Budi |  | 2026-02-21 | 2026-02-22 | 2 | 0% | 0
1.37 | REPORT CANCEL KAIN MASUK | Baim |  | 2026-02-21 | 2026-02-22 | 2 | 0% | 0
1.38 | REPORT COSTING | Budi |  | 2026-02-23 | 2026-02-24 | 2 | 0% | 2
1.39 | REPORT PEMARTAIAN | Baim |  | 2026-02-23 | 2026-02-24 | 2 | 0% | 2
1.40 | REPORT RESERVASI | Budi |  | 2026-02-25 | 2026-02-26 | 2 | 0% | 2
1.41 | REPORT RESUME KODE PARTAI | Baim |  | 2026-02-25 | 2026-02-26 | 2 | 0% | 2
1.42 | STK BLANK GD. PACKING | Budi |  | 2026-02-27 | 2026-02-28 | 2 | 0% | 1
1.43 | STOCK BALANCE KAIN GREY | Baim |  | 2026-02-27 | 2026-02-28 | 2 | 0% | 1
1.44 | STOCK GREY LEAD TIME PER GRADE | Budi |  | 2026-03-01 | 2026-03-02 | 2 | 0% | 1
1.45 | STOCK KAIN GREY (GRADE) | Baim |  | 2026-03-01 | 2026-03-02 | 2 | 0% | 1
1.46 | STOCK KAIN GREY (LW 22) | Budi |  | 2026-03-03 | 2026-03-04 | 2 | 0% | 2
1.47 | STOCK KAIN PASIF (ALL AREA) | Baim |  | 2026-03-03 | 2026-03-04 | 2 | 0% | 2
1.48 | STOCK LEADTIME | Budi |  | 2026-03-05 | 2026-03-06 | 2 | 0% | 2
1.49 | STOCK PER BARCODE | Baim |  | 2026-03-05 | 2026-03-06 | 2 | 0% | 2
1.50 | MOVING HISTORY - GUDANG GREY | Budi |  | 2026-03-07 | 2026-03-08 | 2 | 0% | 0
1 | Report |  |  |  | - |  |  | -
1.1 | REPORT - WM - MOVING HISTORY - GUDANG GREY | Billy, Baim |  | 2026-02-04 | 2026-02-10 | 7 | 0% | 5
1.2 | REPORT - WM - STOCK PER BARCODE | Baim |  | 2026-02-11 | 2026-02-17 | 7 | 0% | 5
1.3 | REPORT - WM - LAPORAN PERSEDIAAN GUDANG PACKING | Budi |  | 2026-02-11 | 2026-02-17 | 7 | 0% | 5
1.4 | REPORT - WM - LAPORAN GUDANG PACKING LEAD TIME | Baim |  | 2026-02-18 | 2026-02-24 | 7 | 0% | 5
1.5 | REPORT - WM - LIST KARTON PER KODE ORDER | Budi |  | 2026-02-18 | 2026-02-24 | 7 | 0% | 5
1.6 | REPORT - WM - MOVING HISTORY PER BARCODE | Baim |  | 2026-02-25 | 2026-03-03 | 7 | 0% | 5
1.7 | REPORT - WM - MOVING HISTORY PER LIST KARTON | Budi |  | 2026-02-25 | 2026-03-03 | 7 | 0% | 5
1.8 | REPORT - MM - STOCK KAIN GREY (GRADE) | Billy, Budi |  | 2026-02-04 | 2026-02-10 | 7 | 0% | 5
1.9 | REPORT - MM - STOCK LEADTIME | Baim |  | 2026-03-04 | 2026-03-10 | 7 | 0% | 5
1.10 | REPORT - MM - STOCK GREY LEAD TIME PER GRADE | Budi |  | 2026-03-04 | 2026-03-10 | 7 | 0% | 5
1.11 | REPORT - MM - STOCK BALANCE KAIN GREY | Budi |  | 2026-03-11 | 2026-03-17 | 7 | 0% | 5
1.12 | REPORT - MM - STOCK KAIN PASIF (ALL AREA) | Baim |  | 2026-03-11 | 2026-03-17 | 7 | 0% | 5
1.13 | REPORT - MM - STOCK KAIN GREY (LW 22) | Budi |  | 2026-03-18 | 2026-03-24 | 7 | 0% | 5
1.14 | REPORT - MM - REPORT RESERVASI | Budi |  | 2026-03-25 | 2026-03-31 | 7 | 0% | 5
1.15 | REPORT - MM - REPORT PEMARTAIAN | Budi |  | 2026-03-25 | 2026-03-31 | 7 | 0% | 5
1.16 | REPORT - MM - REPORT RESUME KODE PARTAI | Budi |  | 2026-04-01 | 2026-04-07 | 7 | 0% | 5
1.17 | REPORT - MM - BBK INTERN | Baim |  | 2026-04-01 | 2026-04-07 | 7 | 0% | 5
1.18 | REPORT - MM - Report Cancel Kain Masuk | Budi |  | 2026-04-08 | 2026-04-14 | 7 | 0% | 5
1.19 | REPORT - MM - Report Cancel Kain Keluar | Baim |  | 2026-04-08 | 2026-04-14 | 7 | 0% | 5
1.20 | REPORT - MM - List STK Intern dan Extern | Budi |  | 2026-04-15 | 2026-04-21 | 7 | 0% | 5
1.21 | REPORT - MM - Laporan Surat Jalan Sloc | Baim |  | 2026-04-15 | 2026-04-21 | 7 | 0% | 5
1.22 | REPORT - MM - Laporan Surat Jalan (P) | Budi |  | 2026-04-22 | 2026-04-28 | 7 | 0% | 5
1.23 | REPORT - WM - DASHBOARD LAYOUT PER BIN | Baim |  | 2026-04-22 | 2026-04-28 | 7 | 0% | 5
1.24 | REPORT - WM - MONITORING KAIN GREY | Budi |  | 2026-04-29 | 2026-05-05 | 7 | 0% | 5
1.25 | REPORT - CO - REPORT COSTING | Budi |  | 2026-04-29 | 2026-05-05 | 7 | 0% | 5
1.26 | REPORT - WM - DETAIL LIST KARTON PER RAK | Budi |  | 2026-05-06 | 2026-05-12 | 7 | 0% | 5
1.27 | REPORT - MM - STK Blank Gd. Packing | Budi |  | 2026-05-06 | 2026-05-12 | 7 | 0% | 5
2 | Interfaces |  |  |  | - |  |  | -
2.1 | INTERFACE BEA CUKAI | Billy, Budi |  | 2026-01-12 | 2026-01-16 | 5 | 0% | 5
2.2 | INTERFACE PRINT BARCODE | Billy, Baim, Budi |  | 2026-01-01 | 2026-01-10 | 10 | 0% | 6
2.3 | INTERFACE PRINT BARCODE BANYAK LIST KARTON | Billy, Baim |  | 2026-01-12 | 2026-01-16 | 5 | 0% | 5
3 | Forms |  |  |  | - |  |  | -
3.1 | Form Transfer Posting (ZSCMF001) | Billy, Budi |  | 2026-01-19 | 2026-01-22 | 4 | 0% | 4
3.2 | Form Purchase Order (ZSCMF002) | Billy, Baim |  | 2026-01-19 | 2026-01-22 | 4 | 0% | 4
3.3 | Form Good Receipt (ZSCMF003) | Baim |  | 2026-01-23 | 2026-01-28 | 6 | 0% | 4
3.4 | Form Good Issue (ZSCMF004) | Baim |  | 2026-01-29 | 2026-02-03 | 6 | 0% | 4
3.5 | Form Bukti Tanda Terima | Budi |  | 2026-01-23 | 2026-01-28 | 6 | 0% | 4
4 | Enhancement |  |  |  | - |  |  | -
4.1 | Custom field for qty in PCS at Report Stock | Billy, Budi |  | 2026-01-29 | 2026-02-03 | 6 | 0% | 4
Note on A7: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet.
Note on B7: Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on C7: Task Lead Enter the name of the Task Lead in this column.
Note on D7: Predecessor Tasks: You can use this column to enter the WBS of a predecessor for reference. The PRO version uses formulas to automatically calculate the Start Date based on the Predecessor.
Note on E7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on F7: End Date: The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on G7: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on H7: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on I7: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.
Note on B20: bram: Dipending oleh pa bily, fokus ke sistem PASSAP
Note on B23: BC: https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_PRODUCT_SRV//A_Product --> tabel pz_material https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_PRODUCT_SRV/A_ProductDescription --> tabel pz_material_description https://my430621-api.s4hana.cloud.sap/sap/opu/odata/sap/API_PRODUCT_SRV/A_ProductPlant --> tabel pz_material_plant

## a
RICEF BY LEUWITEX
|  | Project Start Date | 2025-11-25 | [6 empty] | Display Week | 1 |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8
|  | Project Lead | Billy | [9 empty] | 2025-11-24 | [6 empty] | 2025-12-01 | [6 empty] | 2025-12-08 | [6 empty] | 2025-12-15 | [6 empty] | 2025-12-22 | [6 empty] | 2025-12-29 | [6 empty] | 2026-01-05 | [6 empty] | 2026-01-12
 | time axis 2025-11-24 to 2026-01-18
WBS | Tipe | TASK | PIC a |  | PIC b | PIC c | PREDECESSOR | START | END | DAYS | % DONE | WORK DAYS | time axis 2025-11-24 to 2026-01-18
1 |  | SAP API development | [6 empty] | - |  |  | -
1.1 |  | INSTALL ECLIPSE, ADOBE LIFECYCLE DI PC | Baim, Budi | TRUE | Baim, Budi | Baim, Budi |  | 2025-11-26 | 2025-11-26 | 1 | 100% | 1
1.2 |  | BELAJAR KE SOLTIUS TENTANG SAP | Baim, Budi | TRUE | Baim, Budi | Baim, Budi |  | 2025-11-27 | 2026-02-01 | 67 | 40% | 47
1.3 |  | INTEGRASI API SAP KE PRINT BARCODE INTERNAL | Baim, Budi | TRUE | Baim, Budi | Baim, Budi |  | 2025-12-04 | 2025-12-10 | 7 | 100% | 5
1.4 |  | MAPPING IT INVENTORY | Baim | TRUE | Baim | Baim |  | 2025-12-18 | 2025-12-23 | 6 | 100% | 4
1.5 |  | BELAJAR MENDAFTARKAN API SAP | Baim, Budi | TRUE | Baim, Budi | TIDAK ADA SCHEDULE |  | 2025-12-30 | 2025-12-30 | 1 | 100% | 1
1.6 |  | MAPPING TABEL TAMBAHAN BEA CUKAI | Baim | TRUE | Baim | TIDAK ADA SCHEDULE |  | 2025-12-30 | 2026-01-08 | 10 | 100% | 8
1.7 |  | SIT | Baim, Budi | TRUE | Baim, Budi | TIDAK ADA SCHEDULE |  | 2026-01-06 | 2026-01-08 | 3 | 100% | 3
1.8 |  | INTEGRASI API SAP UNTUK BEA CUKAI | Baim | TRUE | Baim | Baim, Budi |  | 2026-01-09 | 2026-01-18 | 10 | 0% | 6
1.9 |  | BELAJAR MENGEDIT FORM SAP | Baim, Budi | TRUE | Baim, Budi | TIDAK ADA SCHEDULE |  | 2026-01-08 | 2026-01-08 | 1 | 100% | 1
1.10 | Form | Modifikasi Form Invoice (Barang Bekas, Avfal, BS, Maklon, Masker) | Baim | FALSE | Budi | Baim |  | 2026-01-09 | 2026-01-18 | 10 | 0% | 6
1.11 | Form | Modifikasi Form Surat Jalan (Barang Bekas, Avfal, BS, Maklon, Masker) | Budi | TRUE | Budi | Budi |  | 2026-01-09 | 2026-01-18 | 10 | 0% | 6
1.12 | Report | BBK INTERN | Budi | TRUE | Budi | TIDAK ADA SCHEDULE |  | 2025-01-19 | 2025-01-26 | 8 | 0% | 5
1.13 | Report | DASHBOARD LAYOUT PER BIN | Baim | TRUE | Baim | TIDAK ADA SCHEDULE |  | 2025-01-19 | 2025-01-26 | 8 | 0% | 5
1.14 | Report | DETAIL LIST KARTON PER RAK | Budi | TRUE | Budi | TIDAK ADA SCHEDULE |  | 2025-01-27 | 2025-02-03 | 8 | 0% | 6
1.15 | Report | LAPORAN GUDANG PACKING LEAD TIME | Baim | TRUE | Baim | TIDAK ADA SCHEDULE |  | 2025-01-27 | 2025-02-03 | 8 | 0% | 6
1.16 | Report | LAPORAN PERSEDIAAN GUDANG PACKING | Budi | TRUE | Budi | TIDAK ADA SCHEDULE |  | 2025-02-04 | 2025-02-11 | 8 | 0% | 6
1.17 | Report | LAPORAN SURAT JALAN (P) | Baim | TRUE | Baim | TIDAK ADA SCHEDULE |  | 2025-02-04 | 2025-02-11 | 8 | 0% | 6
1.18 | Report | LAPORAN SURAT JALAN SLOC | Budi | TRUE | Budi | TIDAK ADA SCHEDULE |  | 2025-02-12 | 2025-02-19 | 8 | 0% | 6
1.19 | Report | LIST KARTON PER KODE ORDER | Baim | TRUE | Baim | TIDAK ADA SCHEDULE |  | 2025-02-12 | 2025-02-19 | 8 | 0% | 6
1.20 | Report | LIST STK INTERN DAN EXTERN | Budi | TRUE | Budi | TIDAK ADA SCHEDULE |  | 2025-02-20 | 2025-02-27 | 8 | 0% | 6
1.21 | Report | MONITORING KAIN GREY | Baim | TRUE | Baim | TIDAK ADA SCHEDULE |  | 2025-02-20 | 2025-02-27 | 8 | 0% | 6
1.22 | Report | MOVING HISTORY PER LIST KARTON | Budi | TRUE | Budi | TIDAK ADA SCHEDULE |  | 2025-02-28 | 2025-03-07 | 8 | 0% | 6
1.23 | Report | MOVING HISTORY PER LIST BARCODE | Baim | TRUE | Baim | TIDAK ADA SCHEDULE |  | 2025-02-28 | 2025-03-07 | 8 | 0% | 6
1.24 | Report | REPORT CANCEL KAIN KELUAR | Budi | TRUE | Budi | TIDAK ADA SCHEDULE |  | 2025-03-08 | 2025-03-15 | 8 | 0% | 5
1.25 | Report | REPORT CANCEL KAIN MASUK | Baim | TRUE | Baim | TIDAK ADA SCHEDULE |  | 2025-03-08 | 2025-03-15 | 8 | 0% | 5
1.26 | Report | REPORT COSTING | Budi | TRUE | Budi | TIDAK ADA SCHEDULE |  | 2025-03-16 | 2025-03-23 | 8 | 0% | 5
1.27 | Report | REPORT PEMARTAIAN | Baim | TRUE | Baim | TIDAK ADA SCHEDULE |  | 2025-03-16 | 2025-03-23 | 8 | 0% | 5
1.28 | Report | REPORT RESERVASI | Budi | TRUE | Budi | TIDAK ADA SCHEDULE |  | 2025-03-24 | 2025-04-08 | 16 | 0% | 12
1.29 | Report | REPORT RESUME KODE PARTAI | Baim | TRUE | Baim | TIDAK ADA SCHEDULE |  | 2025-03-24 | 2025-04-08 | 16 | 0% | 12
1.30 | Report | STK BLANK GD. PACKING | Budi | TRUE | Budi | TIDAK ADA SCHEDULE |  | 2025-04-09 | 2025-04-16 | 8 | 0% | 6
1.31 | Report | STOCK BALANCE KAIN GREY | Baim | TRUE | Baim | TIDAK ADA SCHEDULE |  | 2025-04-09 | 2025-04-16 | 8 | 0% | 6
1.32 | Report | STOCK GREY LEAD TIME PER GRADE | Budi | TRUE | Budi | TIDAK ADA SCHEDULE |  | 2025-04-17 | 2025-04-24 | 8 | 0% | 6
1.33 | Report | STOCK KAIN GREY (GRADE) | Baim | TRUE | Baim | TIDAK ADA SCHEDULE |  | 2025-04-17 | 2025-04-24 | 8 | 0% | 6
1.34 | Report | STOCK KAIN GREY (LW 22) | Budi | TRUE | Budi | TIDAK ADA SCHEDULE |  | 2025-04-25 | 2025-05-02 | 8 | 0% | 6
1.35 | Report | STOCK KAIN PASIF (ALL AREA) | Baim | TRUE | Baim | TIDAK ADA SCHEDULE |  | 2025-04-25 | 2025-05-02 | 8 | 0% | 6
1.36 | Report | STOCK LEADTIME | Budi | TRUE | Budi | TIDAK ADA SCHEDULE |  | 2025-05-03 | 2025-05-10 | 8 | 0% | 5
1.37 | Report | STOCK PER BARCODE | Baim | TRUE | Baim | TIDAK ADA SCHEDULE |  | 2025-05-03 | 2025-05-10 | 8 | 0% | 5
1.38 | Report | MOVING HISTORY - GUDANG GREY | Budi | TRUE | Budi | TIDAK ADA SCHEDULE |  | 2025-05-11 | 2025-05-18 | 8 | 0% | 5
1 |  | Report | [6 empty] | - |  |  | -
1.1 |  | REPORT - WM - MOVING HISTORY - GUDANG GREY | Billy, Baim |  |  |  |  | 2026-02-04 | 2026-02-10 | 7 | 0% | 5
1.2 |  | REPORT - WM - STOCK PER BARCODE | Baim |  |  |  |  | 2026-02-11 | 2026-02-17 | 7 | 0% | 5
1.3 |  | REPORT - WM - LAPORAN PERSEDIAAN GUDANG PACKING | Budi |  |  |  |  | 2026-02-11 | 2026-02-17 | 7 | 0% | 5
1.4 |  | REPORT - WM - LAPORAN GUDANG PACKING LEAD TIME | Baim |  |  |  |  | 2026-02-18 | 2026-02-24 | 7 | 0% | 5
1.5 |  | REPORT - WM - LIST KARTON PER KODE ORDER | Budi |  |  |  |  | 2026-02-18 | 2026-02-24 | 7 | 0% | 5
1.6 |  | REPORT - WM - MOVING HISTORY PER BARCODE | Baim |  |  |  |  | 2026-02-25 | 2026-03-03 | 7 | 0% | 5
1.7 |  | REPORT - WM - MOVING HISTORY PER LIST KARTON | Budi |  |  |  |  | 2026-02-25 | 2026-03-03 | 7 | 0% | 5
1.8 |  | REPORT - MM - STOCK KAIN GREY (GRADE) | Billy, Budi |  |  |  |  | 2026-02-04 | 2026-02-10 | 7 | 0% | 5
1.9 |  | REPORT - MM - STOCK LEADTIME | Baim |  |  |  |  | 2026-03-04 | 2026-03-10 | 7 | 0% | 5
1.10 |  | REPORT - MM - STOCK GREY LEAD TIME PER GRADE | Budi |  |  |  |  | 2026-03-04 | 2026-03-10 | 7 | 0% | 5
1.11 |  | REPORT - MM - STOCK BALANCE KAIN GREY | Budi |  |  |  |  | 2026-03-11 | 2026-03-17 | 7 | 0% | 5
1.12 |  | REPORT - MM - STOCK KAIN PASIF (ALL AREA) | Baim |  |  |  |  | 2026-03-11 | 2026-03-17 | 7 | 0% | 5
1.13 |  | REPORT - MM - STOCK KAIN GREY (LW 22) | Budi |  |  |  |  | 2026-03-18 | 2026-03-24 | 7 | 0% | 5
1.14 |  | REPORT - MM - REPORT RESERVASI | Budi |  |  |  |  | 2026-03-25 | 2026-03-31 | 7 | 0% | 5
1.15 |  | REPORT - MM - REPORT PEMARTAIAN | Budi |  |  |  |  | 2026-03-25 | 2026-03-31 | 7 | 0% | 5
1.16 |  | REPORT - MM - REPORT RESUME KODE PARTAI | Budi |  |  |  |  | 2026-04-01 | 2026-04-07 | 7 | 0% | 5
1.17 |  | REPORT - MM - BBK INTERN | Baim |  |  |  |  | 2026-04-01 | 2026-04-07 | 7 | 0% | 5
1.18 |  | REPORT - MM - Report Cancel Kain Masuk | Budi |  |  |  |  | 2026-04-08 | 2026-04-14 | 7 | 0% | 5
1.19 |  | REPORT - MM - Report Cancel Kain Keluar | Baim |  |  |  |  | 2026-04-08 | 2026-04-14 | 7 | 0% | 5
1.20 |  | REPORT - MM - List STK Intern dan Extern | Budi |  |  |  |  | 2026-04-15 | 2026-04-21 | 7 | 0% | 5
1.21 |  | REPORT - MM - Laporan Surat Jalan Sloc | Baim |  |  |  |  | 2026-04-15 | 2026-04-21 | 7 | 0% | 5
1.22 |  | REPORT - MM - Laporan Surat Jalan (P) | Budi |  |  |  |  | 2026-04-22 | 2026-04-28 | 7 | 0% | 5
1.23 |  | REPORT - WM - DASHBOARD LAYOUT PER BIN | Baim |  |  |  |  | 2026-04-22 | 2026-04-28 | 7 | 0% | 5
1.24 |  | REPORT - WM - MONITORING KAIN GREY | Budi |  |  |  |  | 2026-04-29 | 2026-05-05 | 7 | 0% | 5
1.25 |  | REPORT - CO - REPORT COSTING | Budi |  |  |  |  | 2026-04-29 | 2026-05-05 | 7 | 0% | 5
1.26 |  | REPORT - WM - DETAIL LIST KARTON PER RAK | Budi |  |  |  |  | 2026-05-06 | 2026-05-12 | 7 | 0% | 5
1.27 |  | REPORT - MM - STK Blank Gd. Packing | Budi |  |  |  |  | 2026-05-06 | 2026-05-12 | 7 | 0% | 5
2 |  | Interfaces | [6 empty] | - |  |  | -
2.1 |  | INTERFACE BEA CUKAI | Billy, Budi |  |  |  |  | 2026-01-12 | 2026-01-16 | 5 | 0% | 5
2.2 |  | INTERFACE PRINT BARCODE | Billy, Baim, Budi |  |  |  |  | 2026-01-01 | 2026-01-10 | 10 | 0% | 6
2.3 |  | INTERFACE PRINT BARCODE BANYAK LIST KARTON | Billy, Baim |  |  |  |  | 2026-01-12 | 2026-01-16 | 5 | 0% | 5
3 |  | Forms | [6 empty] | - |  |  | -
3.1 |  | Form Transfer Posting (ZSCMF001) | Billy, Budi |  |  |  |  | 2026-01-19 | 2026-01-22 | 4 | 0% | 4
3.2 |  | Form Purchase Order (ZSCMF002) | Billy, Baim |  |  |  |  | 2026-01-19 | 2026-01-22 | 4 | 0% | 4
3.3 |  | Form Good Receipt (ZSCMF003) | Baim |  |  |  |  | 2026-01-23 | 2026-01-28 | 6 | 0% | 4
3.4 |  | Form Good Issue (ZSCMF004) | Baim |  |  |  |  | 2026-01-29 | 2026-02-03 | 6 | 0% | 4
3.5 |  | Form Bukti Tanda Terima | Budi |  |  |  |  | 2026-01-23 | 2026-01-28 | 6 | 0% | 4
4 |  | Enhancement | [6 empty] | - |  |  | -
4.1 |  | Custom field for qty in PCS at Report Stock | Billy, Budi |  |  |  |  | 2026-01-29 | 2026-02-03 | 6 | 0% | 4
Note on A7: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet.
Note on C7: Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on D7: Task Lead Enter the name of the Task Lead in this column.
Note on F7: Task Lead Enter the name of the Task Lead in this column.
Note on G7: Task Lead Enter the name of the Task Lead in this column.
Note on H7: Predecessor Tasks: You can use this column to enter the WBS of a predecessor for reference. The PRO version uses formulas to automatically calculate the Start Date based on the Predecessor.
Note on I7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on J7: End Date: The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on K7: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on L7: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on M7: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.

## GanttChartPro (hidden)
Gantt Chart Template Pro
Gantt Chart Template Pro is similar to this free version, but
it is more feature-packed. It also comes with other bonus content.
Learn About Gantt Chart Template Pro
https://www.vertex42.com/ExcelTemplates/excel-gantt-chart.html
The following link is a blog post that talks specifically about the
Pro version for Excel Online.
Gantt Chart Template Pro for Excel Online
Benefits and Features of Gantt Chart Template Pro
Simple Color-Coding
The Pro version includes a column for specifying the color of bars in the chart. For example,
you could change the color based on urgency or task lead.
Daily, Weekly, or Monthly View
The Pro version includes a drop-down next to the Display Week that lets you choose to display
the columns in the chart area as days, weeks, or months.
Use Work Days as an Input
By default, the Pro version is set up to have you enter Work Days instead of Calendar Days.
The expanded set of template rows provides more options for defining the Start date, End date,
and Duration of tasks. Define a task based on …
- Start date and End date
- Start date and Work days
- Start date and Calendar days
Easily Create Task Dependencies
Though you can still use your own formulas for creating task dependencies, the Pro version
includes template rows that calculate the Start date based on the WBS number that you enter
in the Predecessor column.
Exclude Holidays from Work Days
List holidays and other specific non-working days that you want to exclude from work days.
Customize Your Work Week
The versions designed for Excel 2010+ use the WORKDAY.INTL() and NETWORKDAYS.INTL()
functions that allow you define the work week as something other than Monday-Friday.
Learn More About Gantt Chart Template Pro

## Help (hidden)
Help
https://www.vertex42.com/ExcelTemplates/excel-gantt-chart.html
About This Template
This Gantt Chart Template provides an easy way to create a simple project schedule. You only need to know some basic spreadsheet operations, such as how to insert, delete, copy and paste rows and cells. For more advanced uses, such as defining task dependencies, you will need to know how to enter formulas.
Be sure to read the Getting Started Tips below. Watching the video demos for Gantt Chart Template Pro may also help you see how to use the spreadsheet.
Watch Demo Videos of the Pro Version on Vertex42.com
Please read the license agreement in the TermsOfUse worksheet to learn how you may or may not use and share this spreadsheet.
Getting Started Tips
• [Bracketed Text] is meant to be edited, like the project title and task descriptions.
| • Some of the labels include cell comments to provide extra information. | Label
• To adjust the range of dates shown in the Gantt chart, change the Display Week number.
• The Project Start Date is used to define the first week shown in the gantt chart.
• Insert new tasks using one of the methods listed below.
| • Define the task start date and duration (days) by editing the light green cells. | Input Cell
• If you see "#####" in a cell, widen the column to display the cell contents.
• Backup your file regularly to avoid losing data! Excel files get corrupted occasionally.
Inserting New Tasks (Rows)
When inserting and deleting tasks, you need to insert and delete entire rows. Some columns contain formulas (such as the End Date and the Work Days columns), so these formulas need to copied to the newly inserted rows.
METHOD 1 (recommended)
• Insert a new blank row by right-clicking on the row number and selecting Insert.
• With the new blank row selected, press Ctrl+d to copy the formulas and formatting down from the row above OR use the row drag handle to copy the formulas and formatting down.
METHOD 2
• Copy a row from the set of template rows at the bottom of the worksheet.
• Right-click on the row where you want to insert the new task and select Insert Copied Cells.
Method 2 will work, but Excel will split/fracture/duplicate conditional formatting rules rather than merging the rules. This can cause inefficiencies in very large and heavily modified files.
Help improve Excel by voting on a suggestion to fix this problem.
Using the Template Rows and Choosing a WBS Level
The set of template rows at the bottom of the Gantt Chart worksheet provide examples of different ways to format and define tasks for different WBS levels.
Each different WBS level uses a different formula in the WBS column.
You can either copy/paste/insert these template rows via Method 2 as explained above, OR you can just copy/paste the desired WBS cell when you want to change the WBS level.
If you leave a blank cell above a WBS number, the numbering will reset to 1.x.x. The formulas are meant for convenience, but you can manually enter the WBS numbers if you want to.
You can indent the task description for sub-tasks by entering leading spaces or using the Indent feature in Excel.
Creating Task Dependencies
You can enter the Start date manually, or define task dependencies using a formula. Below are some common options for defining the Start date:
A. | Enter the date manually (e.g. 1/3/2015)
B. | Reference the Project Start Date (e.g. =$E$4 )
C. | Set the Start date to the next Work Day after another task's End date.
• Use the formula =WORKDAY(enddate,1) where enddate is the reference to the End date of a predecessor task.
• For multiple predecessors, the formula would be =MAX(WORKDAY(enddate1,1),WORKDAY(enddate2,1))
D. | Set the Start date to the next Calendar Day after another task's End date.
• This formula is very simple: =enddate+1
• For multiple predecessors, the formula would be =MAX(enddate1,enddate2,enddate3)+1
E. | Set the Start date to a number of days before or after another date.
• This formula is just like the one in C or D, except that in place of the "1" you enter the number of days, such as =WORKDAY(enddate,5) or =WORKDAY(startdate,-5)
F. | Use a lookup formula and the Predecessor column to define the start date.
[The formulas for using this method are built into Gantt Chart Template Pro]
Changing the Color of the Bars in the Gantt Chart
[Advanced] The Gantt Chart is created using conditional formatting, so you can modify the conditional formatting rules to change the format to a different color. The Pro version includes a column where you can change the color by entering a color code ("b"=blue, "g"=green, etc.)
FAQs
Q: | How do I enter the Work Days instead of Calendar Days?
Entering work days instead of calendar days is a feature of the Pro version. There is nothing in the free version preventing you from entering your own formulas, though.
Q: | How do I calculate Calendar Days after entering the Start and End Dates?
You can calculate the duration in calendar days (including both start and end dates) using the formula =enddate-startdate+1
Q: | How do I change the Print Settings? (Excel 2010, 2013)
Select the entire range of cells you want to print and go to File > Print Area > Set Print Area. Then go to File > Page Setup or File > Print Preview and adjust the Scaling, Margins, and Page Orientation as desired.
Q: | How do I increase the range of dates displayed in the Gantt chart?
You will need to add columns to the right of the Gantt Chart via copy/paste. Copy and paste the columns in groups of 7. Afterwards, you will also probably need to update the print area.
Q: | How do I create a summary row that shows the MIN and MAX dates for all sub-tasks?
In the Start column, use the formula =MIN(range_of_start_dates)
In the End column, use the formula =MAX(range_of_end_dates)
In the Days column, use the formula =end_date-start_date+1
Q: | How do I calculate the %Complete for an entire category of tasks?
The %Complete for a group of tasks can be calculated from its sub tasks using the formula below, where "workdays" is a reference to the range of work day values and "complete" is a reference to the %complete for each of the subtasks.
=SUMPRODUCT(workdays,complete)/SUM(workdays)
Example: Let's say you have 3 sub tasks that are 10 days, 12 days, and 14 days long, respectively. If the first subtask is 50% complete and the others are 25% complete, you could calculate the overall percent complete for the group as: =(10*50%+12*25%+14*25%)/(10+12+14).
Q: | I've messed up the chart area somehow. How do I fix it?
Find a row that works, then copy the cells that make up the gantt chart area from that row into the row that is messed up.
© 2006-2025 Vertex42 LLC
Note on C16: This is an example comment.

## TermsOfUse (hidden)
Terms of Use
Gantt Chart Template, by Vertex42.com
https://www.vertex42.com/ExcelTemplates/excel-gantt-chart.html
© 2006-2025 Vertex42 LLC
This spreadsheet template, including all worksheets and associated content is a copyrighted work under the United States and other copyright laws.
You may download the spreadsheet template, make archival copies, and customize the template only for your personal use or use within your company or organization and not for resale or public sharing.
You may not remove or alter any Vertex42 logo, trademark, copyright, disclaimer, brand, terms of use, attribution, or other proprietary notices or marks within the template.
The template and any file, document, or other work including or derived from the template may NOT be sold, distributed, published to an online gallery, hosted on a website, or placed on any server in a way that makes it available to the general public.
Limited Private Sharing and Other Allowed Uses: See the complete license agreement to learn more about how you may or may not use this template.
View the Complete License Agreement
https://www.vertex42.com/licensing/EULA_privateuse.html

## b (hidden)
RICEF BY LEUWITEX ( update 6 January 2026 )
| Project Start Date | 2025-11-25 |  |  |  | Display Week | 1 |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8
| Project Lead | Billy | [6 empty] | 2025-11-24 | [6 empty] | 2025-12-01 | [6 empty] | 2025-12-08 | [6 empty] | 2025-12-15 | [6 empty] | 2025-12-22 | [6 empty] | 2025-12-29 | [6 empty] | 2026-01-05 | [6 empty] | 2026-01-12
 | time axis 2025-11-24 to 2026-01-18
WBS | TASK | PIC | PREDECESSOR | START | END | DAYS | % DONE | WORK DAYS | time axis 2025-11-24 to 2026-01-18
1 | SAP API development |  |  |  | - |  |  | -
1.1 | INSTALL ECLIPSE, ADOBE LIFECYCLE DI PC | Baim, Budi |  | 2025-11-26 | 2025-11-26 | 1 | 100% | 1
1.2 | TANYA2 KE SOLTIUS TENTANG SAP | Baim, Budi |  | 2025-11-27 | 2026-02-01 | 67 | 30% | 47
1.3 | INTEGRASI API SAP KE PRINT BARCODE INTERNAL | Baim, Budi |  | 2025-12-04 | 2025-12-10 | 7 | 100% | 5
1.4 | MAPPING IT INVENTORY | Baim |  | 2025-12-18 | 2025-12-23 | 6 | 100% | 4
1.5 | BELAJAR MENDAFTARKAN API SAP | Baim, Budi |  | 2025-12-30 | 2025-12-30 | 1 | 100% | 1
1.6 | MAPPING TABEL TAMBAHAN BEA CUKAI | Baim |  | 2025-12-30 | 2026-01-08 | 10 | 100% | 8
1.7 | SIT | Baim, Budi |  | 2026-01-06 | 2026-01-08 | 3 | 100% | 3
1.8 | INTEGRASI API SAP UNTUK BEA CUKAI | Baim |  | 2026-01-09 | 2026-01-18 | 10 | 0% | 6
1.9 | BELAJAR MENGEDIT FORM SAP | Baim, Budi |  | 2026-01-08 | 2026-01-08 | 1 | 80% | 1
1.10 | Modifikasi Form Invoice (Barang Bekas, Avfal, BS, Maklon, Masker) | Budi |  |  | - | 10 | 0% | -
1.11 | Modifikasi Form Surat Jalan (Barang Bekas, Avfal, BS, Maklon, Masker) | Budi |  |  | - | 10 | 0% | -
1.12 | BBK INTERN | Budi |  | 2025-01-19 | 2025-01-26 | 8 | 0% | 5
1.13 | DASHBOARD LAYOUT PER BIN | Baim |  | 2025-01-19 | 2025-01-26 | 8 | 0% | 5
1.14 | DETAIL LIST KARTON PER RAK | Budi |  | 2025-01-27 | 2025-02-03 | 8 | 0% | 6
1.15 | LAPORAN GUDANG PACKING LEAD TIME | Baim |  | 2025-01-27 | 2025-02-03 | 8 | 0% | 6
1.16 | LAPORAN PERSEDIAAN GUDANG PACKING | Budi |  | 2025-02-04 | 2025-02-11 | 8 | 0% | 6
1.17 | LAPORAN SURAT JALAN (P) | Baim |  | 2025-02-04 | 2025-02-11 | 8 | 0% | 6
1.18 | LAPORAN SURAT JALAN SLOC | Budi |  | 2025-02-12 | 2025-02-19 | 8 | 0% | 6
1.19 | LIST KARTON PER KODE ORDER | Baim |  | 2025-02-12 | 2025-02-19 | 8 | 0% | 6
1.20 | LIST STK INTERN DAN EXTERN | Budi |  | 2025-02-20 | 2025-02-27 | 8 | 0% | 6
1.21 | MONITORING KAIN GREY | Baim |  | 2025-02-20 | 2025-02-27 | 8 | 0% | 6
1.22 | MOVING HISTORY PER LIST KARTON | Budi |  | 2025-02-28 | 2025-03-07 | 8 | 0% | 6
1.23 | MOVING HISTORY PER LIST BARCODE | Baim |  | 2025-02-28 | 2025-03-07 | 8 | 0% | 6
1.24 | REPORT CANCEL KAIN KELUAR | Budi |  | 2025-03-08 | 2025-03-15 | 8 | 0% | 5
1.25 | REPORT CANCEL KAIN MASUK | Baim |  | 2025-03-08 | 2025-03-15 | 8 | 0% | 5
1.26 | REPORT COSTING | Budi |  | 2025-03-16 | 2025-03-23 | 8 | 0% | 5
1.27 | REPORT PEMARTAIAN | Baim |  | 2025-03-16 | 2025-03-23 | 8 | 0% | 5
1.28 | REPORT RESERVASI | Budi |  | 2025-03-24 | 2025-04-08 | 16 | 0% | 12
1.29 | REPORT RESUME KODE PARTAI | Baim |  | 2025-03-24 | 2025-04-08 | 16 | 0% | 12
1.30 | STK BLANK GD. PACKING | Budi |  | 2025-04-09 | 2025-04-16 | 8 | 0% | 6
1.31 | STOCK BALANCE KAIN GREY | Baim |  | 2025-04-09 | 2025-04-16 | 8 | 0% | 6
1.32 | STOCK GREY LEAD TIME PER GRADE | Budi |  | 2025-04-17 | 2025-04-24 | 8 | 0% | 6
1.33 | STOCK KAIN GREY (GRADE) | Baim |  | 2025-04-17 | 2025-04-24 | 8 | 0% | 6
1.34 | STOCK KAIN GREY (LW 22) | Budi |  | 2025-04-25 | 2025-05-02 | 8 | 0% | 6
1.35 | STOCK KAIN PASIF (ALL AREA) | Baim |  | 2025-04-25 | 2025-05-02 | 8 | 0% | 6
1.36 | STOCK LEADTIME | Budi |  | 2025-05-03 | 2025-05-10 | 8 | 0% | 5
1.37 | STOCK PER BARCODE | Baim |  | 2025-05-03 | 2025-05-10 | 8 | 0% | 5
1.38 | MOVING HISTORY - GUDANG GREY | Budi |  | 2025-05-11 | 2025-05-18 | 8 | 0% | 5
1 | Report |  |  |  | - |  |  | -
1.1 | REPORT - WM - MOVING HISTORY - GUDANG GREY | Billy, Baim |  | 2026-02-04 | 2026-02-10 | 7 | 0% | 5
1.2 | REPORT - WM - STOCK PER BARCODE | Baim |  | 2026-02-11 | 2026-02-17 | 7 | 0% | 5
1.3 | REPORT - WM - LAPORAN PERSEDIAAN GUDANG PACKING | Budi |  | 2026-02-11 | 2026-02-17 | 7 | 0% | 5
1.4 | REPORT - WM - LAPORAN GUDANG PACKING LEAD TIME | Baim |  | 2026-02-18 | 2026-02-24 | 7 | 0% | 5
1.5 | REPORT - WM - LIST KARTON PER KODE ORDER | Budi |  | 2026-02-18 | 2026-02-24 | 7 | 0% | 5
1.6 | REPORT - WM - MOVING HISTORY PER BARCODE | Baim |  | 2026-02-25 | 2026-03-03 | 7 | 0% | 5
1.7 | REPORT - WM - MOVING HISTORY PER LIST KARTON | Budi |  | 2026-02-25 | 2026-03-03 | 7 | 0% | 5
1.8 | REPORT - MM - STOCK KAIN GREY (GRADE) | Billy, Budi |  | 2026-02-04 | 2026-02-10 | 7 | 0% | 5
1.9 | REPORT - MM - STOCK LEADTIME | Baim |  | 2026-03-04 | 2026-03-10 | 7 | 0% | 5
1.10 | REPORT - MM - STOCK GREY LEAD TIME PER GRADE | Budi |  | 2026-03-04 | 2026-03-10 | 7 | 0% | 5
1.11 | REPORT - MM - STOCK BALANCE KAIN GREY | Budi |  | 2026-03-11 | 2026-03-17 | 7 | 0% | 5
1.12 | REPORT - MM - STOCK KAIN PASIF (ALL AREA) | Baim |  | 2026-03-11 | 2026-03-17 | 7 | 0% | 5
1.13 | REPORT - MM - STOCK KAIN GREY (LW 22) | Budi |  | 2026-03-18 | 2026-03-24 | 7 | 0% | 5
1.14 | REPORT - MM - REPORT RESERVASI | Budi |  | 2026-03-25 | 2026-03-31 | 7 | 0% | 5
1.15 | REPORT - MM - REPORT PEMARTAIAN | Budi |  | 2026-03-25 | 2026-03-31 | 7 | 0% | 5
1.16 | REPORT - MM - REPORT RESUME KODE PARTAI | Budi |  | 2026-04-01 | 2026-04-07 | 7 | 0% | 5
1.17 | REPORT - MM - BBK INTERN | Baim |  | 2026-04-01 | 2026-04-07 | 7 | 0% | 5
1.18 | REPORT - MM - Report Cancel Kain Masuk | Budi |  | 2026-04-08 | 2026-04-14 | 7 | 0% | 5
1.19 | REPORT - MM - Report Cancel Kain Keluar | Baim |  | 2026-04-08 | 2026-04-14 | 7 | 0% | 5
1.20 | REPORT - MM - List STK Intern dan Extern | Budi |  | 2026-04-15 | 2026-04-21 | 7 | 0% | 5
1.21 | REPORT - MM - Laporan Surat Jalan Sloc | Baim |  | 2026-04-15 | 2026-04-21 | 7 | 0% | 5
1.22 | REPORT - MM - Laporan Surat Jalan (P) | Budi |  | 2026-04-22 | 2026-04-28 | 7 | 0% | 5
1.23 | REPORT - WM - DASHBOARD LAYOUT PER BIN | Baim |  | 2026-04-22 | 2026-04-28 | 7 | 0% | 5
1.24 | REPORT - WM - MONITORING KAIN GREY | Budi |  | 2026-04-29 | 2026-05-05 | 7 | 0% | 5
1.25 | REPORT - CO - REPORT COSTING | Budi |  | 2026-04-29 | 2026-05-05 | 7 | 0% | 5
1.26 | REPORT - WM - DETAIL LIST KARTON PER RAK | Budi |  | 2026-05-06 | 2026-05-12 | 7 | 0% | 5
1.27 | REPORT - MM - STK Blank Gd. Packing | Budi |  | 2026-05-06 | 2026-05-12 | 7 | 0% | 5
2 | Interfaces |  |  |  | - |  |  | -
2.1 | INTERFACE BEA CUKAI | Billy, Budi |  | 2026-01-12 | 2026-01-16 | 5 | 0% | 5
2.2 | INTERFACE PRINT BARCODE | Billy, Baim, Budi |  | 2026-01-01 | 2026-01-10 | 10 | 0% | 6
2.3 | INTERFACE PRINT BARCODE BANYAK LIST KARTON | Billy, Baim |  | 2026-01-12 | 2026-01-16 | 5 | 0% | 5
3 | Forms |  |  |  | - |  |  | -
3.1 | Form Transfer Posting (ZSCMF001) | Billy, Budi |  | 2026-01-19 | 2026-01-22 | 4 | 0% | 4
3.2 | Form Purchase Order (ZSCMF002) | Billy, Baim |  | 2026-01-19 | 2026-01-22 | 4 | 0% | 4
3.3 | Form Good Receipt (ZSCMF003) | Baim |  | 2026-01-23 | 2026-01-28 | 6 | 0% | 4
3.4 | Form Good Issue (ZSCMF004) | Baim |  | 2026-01-29 | 2026-02-03 | 6 | 0% | 4
3.5 | Form Bukti Tanda Terima | Budi |  | 2026-01-23 | 2026-01-28 | 6 | 0% | 4
4 | Enhancement |  |  |  | - |  |  | -
4.1 | Custom field for qty in PCS at Report Stock | Billy, Budi |  | 2026-01-29 | 2026-02-03 | 6 | 0% | 4
Note on A7: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet.
Note on B7: Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on C7: Task Lead Enter the name of the Task Lead in this column.
Note on D7: Predecessor Tasks: You can use this column to enter the WBS of a predecessor for reference. The PRO version uses formulas to automatically calculate the Start Date based on the Predecessor.
Note on E7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on F7: End Date: The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on G7: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on H7: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on I7: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.

## c (hidden)
RICEF BY LEUWITEX
| Project Start Date | 2025-11-25 |  |  |  | Display Week | 1 |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8
| Project Lead | Billy | [6 empty] | 2025-11-24 | [6 empty] | 2025-12-01 | [6 empty] | 2025-12-08 | [6 empty] | 2025-12-15 | [6 empty] | 2025-12-22 | [6 empty] | 2025-12-29 | [6 empty] | 2026-01-05 | [6 empty] | 2026-01-12
 | time axis 2025-11-24 to 2026-01-18
WBS | TASK | PIC | PREDECESSOR | START | END | DAYS | % DONE | WORK DAYS | time axis 2025-11-24 to 2026-01-18
1 | BEFORE UAT |  |  |  | - |  |  | -
1.1 | Install Eclipse, Adobe lifecycle di PC | Baim, Budi |  | 2025-11-26 | 2025-11-26 | 1 | 100% | 1
1.2 | Tanya2 ke SOLTIUS tentang SAP | Baim, Budi |  | 2025-11-27 | 2026-02-01 | 67 | 30% | 47
1.3 | Integrasi API SAP ke Print Barcode Internal | Baim, Budi |  | 2025-12-04 | 2025-12-10 | 7 | 100% | 5
1.4 | Mapping IT Inventory | Baim |  | 2025-12-18 | 2025-12-23 | 6 | 100% | 4
1.5 | Integrasi API SAP untuk Bea Cukai | Baim, Budi |  | 2025-12-24 | 2026-01-06 | 14 | 0% | 10
1.6 | Modifikasi Form Invoice (Barang Bekas, Avfal, BS, Maklon, Masker) | Baim |  | 2025-12-22 | 2025-12-30 | 9 | 0% | 7
1.7 | Modifikasi Form Surat Jalan (Barang Bekas, Avfal, BS, Maklon, Masker) | Budi |  | 2025-12-22 | 2025-12-30 | 9 | 0% | 7
1.8 | Modifikasi Form Transfer Posting | Budi |  | 2025-12-31 | 2026-01-07 | 8 | 0% | 6
1.9 | Modifikasi Form Purchase Order | Baim |  | 2025-12-31 | 2026-01-07 | 8 | 0% | 6
1.10 | Modifikasi Form Good Receipt | Budi |  | 2026-08-01 | 2026-08-08 | 8 | 0% | 5
1.11 | Modifikasi Form Good Issue | Baim |  | 2026-08-01 | 2026-08-08 | 8 | 0% | 5
1.12 | Modifikasi Form Bukti Tanda Terima | Budi |  | 2026-08-09 | 2026-08-16 | 8 | 0% | 5
2 | AFTER UAT(9 Feb 2026) |  |  |  | - |  |  | -
1 | Report |  |  |  | - |  |  | -
1.1 | REPORT - WM - MOVING HISTORY - GUDANG GREY | Billy, Baim |  | 2026-02-04 | 2026-02-10 | 7 | 0% | 5
1.2 | REPORT - WM - STOCK PER BARCODE | Baim |  | 2026-02-11 | 2026-02-17 | 7 | 0% | 5
1.3 | REPORT - WM - LAPORAN PERSEDIAAN GUDANG PACKING | Budi |  | 2026-02-11 | 2026-02-17 | 7 | 0% | 5
1.4 | REPORT - WM - LAPORAN GUDANG PACKING LEAD TIME | Baim |  | 2026-02-18 | 2026-02-24 | 7 | 0% | 5
1.5 | REPORT - WM - LIST KARTON PER KODE ORDER | Budi |  | 2026-02-18 | 2026-02-24 | 7 | 0% | 5
1.6 | REPORT - WM - MOVING HISTORY PER BARCODE | Baim |  | 2026-02-25 | 2026-03-03 | 7 | 0% | 5
1.7 | REPORT - WM - MOVING HISTORY PER LIST KARTON | Budi |  | 2026-02-25 | 2026-03-03 | 7 | 0% | 5
1.8 | REPORT - MM - STOCK KAIN GREY (GRADE) | Billy, Budi |  | 2026-02-04 | 2026-02-10 | 7 | 0% | 5
1.9 | REPORT - MM - STOCK LEADTIME | Baim |  | 2026-03-04 | 2026-03-10 | 7 | 0% | 5
1.10 | REPORT - MM - STOCK GREY LEAD TIME PER GRADE | Budi |  | 2026-03-04 | 2026-03-10 | 7 | 0% | 5
1.11 | REPORT - MM - STOCK BALANCE KAIN GREY | Budi |  | 2026-03-11 | 2026-03-17 | 7 | 0% | 5
1.12 | REPORT - MM - STOCK KAIN PASIF (ALL AREA) | Baim |  | 2026-03-11 | 2026-03-17 | 7 | 0% | 5
1.13 | REPORT - MM - STOCK KAIN GREY (LW 22) | Budi |  | 2026-03-18 | 2026-03-24 | 7 | 0% | 5
1.14 | REPORT - MM - REPORT RESERVASI | Budi |  | 2026-03-25 | 2026-03-31 | 7 | 0% | 5
1.15 | REPORT - MM - REPORT PEMARTAIAN | Budi |  | 2026-03-25 | 2026-03-31 | 7 | 0% | 5
1.16 | REPORT - MM - REPORT RESUME KODE PARTAI | Budi |  | 2026-04-01 | 2026-04-07 | 7 | 0% | 5
1.17 | REPORT - MM - BBK INTERN | Baim |  | 2026-04-01 | 2026-04-07 | 7 | 0% | 5
1.18 | REPORT - MM - Report Cancel Kain Masuk | Budi |  | 2026-04-08 | 2026-04-14 | 7 | 0% | 5
1.19 | REPORT - MM - Report Cancel Kain Keluar | Baim |  | 2026-04-08 | 2026-04-14 | 7 | 0% | 5
1.20 | REPORT - MM - List STK Intern dan Extern | Budi |  | 2026-04-15 | 2026-04-21 | 7 | 0% | 5
1.21 | REPORT - MM - Laporan Surat Jalan Sloc | Baim |  | 2026-04-15 | 2026-04-21 | 7 | 0% | 5
1.22 | REPORT - MM - Laporan Surat Jalan (P) | Budi |  | 2026-04-22 | 2026-04-28 | 7 | 0% | 5
1.23 | REPORT - WM - DASHBOARD LAYOUT PER BIN | Baim |  | 2026-04-22 | 2026-04-28 | 7 | 0% | 5
1.24 | REPORT - WM - MONITORING KAIN GREY | Budi |  | 2026-04-29 | 2026-05-05 | 7 | 0% | 5
1.25 | REPORT - CO - REPORT COSTING | Budi |  | 2026-04-29 | 2026-05-05 | 7 | 0% | 5
1.26 | REPORT - WM - DETAIL LIST KARTON PER RAK | Budi |  | 2026-05-06 | 2026-05-12 | 7 | 0% | 5
1.27 | REPORT - MM - STK Blank Gd. Packing | Budi |  | 2026-05-06 | 2026-05-12 | 7 | 0% | 5
2 | Interfaces |  |  |  | - |  |  | -
2.1 | INTERFACE BEA CUKAI | Billy, Budi |  | 2026-01-12 | 2026-01-16 | 5 | 0% | 5
2.2 | INTERFACE PRINT BARCODE | Billy, Baim, Budi |  | 2026-01-01 | 2026-01-10 | 10 | 0% | 6
2.3 | INTERFACE PRINT BARCODE BANYAK LIST KARTON | Billy, Baim |  | 2026-01-12 | 2026-01-16 | 5 | 0% | 5
3 | Forms |  |  |  | - |  |  | -
3.1 | Form Transfer Posting (ZSCMF001) | Billy, Budi |  | 2026-01-19 | 2026-01-22 | 4 | 0% | 4
3.2 | Form Purchase Order (ZSCMF002) | Billy, Baim |  | 2026-01-19 | 2026-01-22 | 4 | 0% | 4
3.3 | Form Good Receipt (ZSCMF003) | Baim |  | 2026-01-23 | 2026-01-28 | 6 | 0% | 4
3.4 | Form Good Issue (ZSCMF004) | Baim |  | 2026-01-29 | 2026-02-03 | 6 | 0% | 4
3.5 | Form Bukti Tanda Terima | Budi |  | 2026-01-23 | 2026-01-28 | 6 | 0% | 4
4 | Enhancement |  |  |  | - |  |  | -
4.1 | Custom field for qty in PCS at Report Stock | Billy, Budi |  | 2026-01-29 | 2026-02-03 | 6 | 0% | 4
Note on A7: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet.
Note on B7: Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on C7: Task Lead Enter the name of the Task Lead in this column.
Note on D7: Predecessor Tasks: You can use this column to enter the WBS of a predecessor for reference. The PRO version uses formulas to automatically calculate the Start Date based on the Predecessor.
Note on E7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on F7: End Date: The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on G7: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on H7: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on I7: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.

## Update Project
Update per 10 January 2026
1.mapping tabel BC tambahan sudah selesai dan sudah diberikan ke Soltiust (point 1.6)
2.SIT dari Soltius sudah selesai
3.Pengajaran pengditan form dari Soltius sudah dilakukan, kemungkinan butuh waktu untuk mencoba2

## DASHBOARD LAYOUT PER BIN
back
REMARKS
[23 empty] | 1. | Tidak ada report standar SAP yang menampilkan informasi dalam bentuk dashboard
[23 empty] | 2. | Untuk kebutuhan dashboard ini disarankan tetap menggunakan program yang sudah ada dimana untuk sumber datanya memanfaatkan API dari SAP
1. Query nya
2. Struktur Tabel
Tabel tm_storage_bin
Keterangan
e_area | e_type | e_ini_rak | e_kolom_rak | e_baris_rak | e_alamat
LJ1 | FLOOR | FR | GH | 1B | FR-GH-1B
LJ1 | FLOOR | FR | GH | 1C | FR-GH-1C
LJ1 | FLOOR | FR | GH | 1D | FR-GH-1D
LJ1 | FLOOR | FR | GH | 20A | FR-GH-20A
LJ1 | FLOOR | FR | GH | 20B | FR-GH-20B
Tabel tm_grstock_co
Keterangan
i_barcode | e_charname | e_jns | e_loc | d_potong | d_doc | d_posting | e_area | e_create_by | e_sloc | e_ori_sloc | e_jenis_produksi | e_produksi | i_docrun | i_material | e_material | e_jns_kain | i_qty | e_uom | e_grade | e_jl | i_mesin | d_year | e_desc
LD2508140015 | @11 220; @12 20; @13 ; @14 3.457; @15 ; @16 WOOVEN; @17 POLOS; @18 ; @19 ; @20 13-08-2025; | WOOVEN | E1-07-03 | 2025-08-13 | 2025-08-14 | 2025-08-14 | LJ1 |  |  |  | WOOVEN | MASSAL | 7866278 | LD_716_LST_28138_58 | BARBEI 58 | GREY | 177 | YARD | A | POLOS | 220 | 2000 | UPL_STOCK_25
LS3631924 | @11 ; @12 19; @13 ; @14 ; @15 ; @16 WOOVEN; @17 ; @18 ; @19 ; @20 13-04-2023; | WOOVEN | 2005-05-01 | 2023-04-13 | 2023-04-16 | 2023-04-16 | LJ1 | GD_GREY | GREY | ISGREY | WOOVEN | MASSAL | 7748518 | LS_020_BSY_20375_44 | CRYSTAL 44 | GREY | 82.4 | YARD | A |  |  | 2024
LS3631921 | @11 ; @12 19; @13 ; @14 ; @15 ; @16 WOOVEN; @17 ; @18 ; @19 ; @20 13-04-2023; | WOOVEN | 2005-05-01 | 2023-04-13 | 2023-04-16 | 2023-04-16 | LJ1 | GD_GREY | GREY | ISGREY | WOOVEN | MASSAL | 7748518 | LS_020_BSY_20375_44 | CRYSTAL 44 | GREY | 78.3 | YARD | B |  |  | 2024
LS3631929 | @11 ; @12 19; @13 ; @14 ; @15 ; @16 WOOVEN; @17 ; @18 ; @19 ; @20 13-04-2023; | WOOVEN | 2005-05-01 | 2023-04-13 | 2023-04-17 | 2023-04-16 | LJ1 | GD_GREY | GREY | ISGREY | WOOVEN | MASSAL | 7748649 | LS_020_BSY_20375_44 | CRYSTAL 44 | GREY | 155.1 | YARD | C3 |  |  | 2024
LS3631935 | @11 ; @12 19; @13 ; @14 ; @15 ; @16 WOOVEN; @17 ; @18 ; @19 ; @20 13-04-2023; | WOOVEN | 2005-05-01 | 2023-04-13 | 2023-04-16 | 2023-04-16 | LJ1 | GD_GREY | GREY | ISGREY | WOOVEN | MASSAL | 7748518 | LS_020_BSY_20375_44 | CRYSTAL 44 | GREY | 194.6 | YARD | X |  |  | 2024
LS3631931 | @11 ; @12 19; @13 ; @14 ; @15 ; @16 WOOVEN; @17 ; @18 ; @19 ; @20 13-04-2023; | WOOVEN | 2005-05-01 | 2023-04-13 | 2023-04-16 | 2023-04-16 | LJ1 | GD_GREY | GREY | ISGREY | WOOVEN | MASSAL | 7748518 | LS_021_BSY_20375_44 | CRYSTAL 44 | GREY | 156.7 | YARD | B |  |  | 2024
Tabel tr_in_head
Keterangan
i_docrun | i_docnum | d_doc | d_posting | e_doc_text | e_create_by | d_create | e_plant | e_ori_plant | e_sloc | e_ori_sloc | e_stock_type | e_ori_stock_type | e_modify_by | d_modify | e_mvt | f_cancel | e_upload_desc | i_docreff | d_year
7838217 | TIG-250102-00001 | 2025-01-02 | 2025-01-02 | MASUK_70125_68_SUM | gdgr1 | 2025-01-02 08:17 | LWT | LWT | GREY | ISGREY |  |  |  |  | 581 | f |  |  | 2025
7838218 | TIG-250102-00002 | 2025-01-02 | 2025-01-02 | masuk_12385_58_SUM | gdgr1 | 2025-01-02 08:31 | LWT | LWT | GREY | ISGREY |  |  |  |  | 581 | f |  |  | 2025
7838219 | TIG-250102-00003 | 2025-01-02 | 2025-01-02 | MASUK_12385_58_SUM | gdgr1 | 2025-01-02 08:38 | LWT | LWT | GREY | ISGREY |  |  |  |  | 581 | f |  |  | 2025
7838220 | TIG-250102-00004 | 2025-01-02 | 2025-01-02 | MASUK_40818_72__SUM | gdgr1 | 2025-01-02 08:41 | LWT | LWT | GREY | ISGREY |  |  |  |  | 581 | f |  |  | 2025
7838221 | TIG-250102-00005 | 2025-01-02 | 2025-01-02 | MASUK_12385_58_SUM | gdgr1 | 2025-01-02 08:45 | LWT | LWT | GREY | ISGREY |  |  |  |  | 581 | f |  |  | 2025
Tabel tr_in_detail
Keterangan
i_docrun | i_docnum | i_barcode | i_brc | i_item | i_qty | e_uom | i_material | e_material | e_plant | e_grade | e_loc | e_jns | e_typ_prod | e_charname | e_buyer | e_kode_order | f_cancel | e_upload_desc | i_docreff | d_year
7841011 | TIG-250122-00017 | LD2501180272 | 2501180272 | 6 | 224 | YARD | LD_710_LST_44618_68 | BESLON 68 |  | A | DYE | WOOVEN | MASSAL | @11 06; @12 20; @13 ; @14 11.502; @15 ; @16 WOOVEN; @17 POLOS; @18 ; @19 ; @20 18-01-2025; |  |  | f |  |  | 2025
7838778 | TIG-250106-00033 | KT2501050380 | 2501050380 | 13 | 221 | YARD | KT_001_LST_10919_58 | WOOL PEACH 58 |  | B | DYE | WOOVEN | MASSAL | @11 71; @12 8; @13 ; @14 1; @15 ; @16 WOOVEN; @17 POLOS; @18 ; @19 ; @20 04-01-2025; |  |  | f |  |  | 2025
7838778 | TIG-250106-00033 | KT2501040306 | 2501040306 | 10 | 300 | YARD | KT_001_LST_10919_58 | WOOL PEACH 58 |  | A | DYE | WOOVEN | MASSAL | @11 71; @12 9; @13 ; @14 7.34; @15 ; @16 WOOVEN; @17 POLOS; @18 ; @19 ; @20 04-01-2025; |  |  | f |  |  | 2025
7838778 | TIG-250106-00033 | KT2501050419 | 2501050419 | 14 | 294 | YARD | KT_001_LST_10919_58 | WOOL PEACH 58 |  | A | DYE | WOOVEN | MASSAL | @11 78; @12 8; @13 ; @14 1; @15 ; @16 WOOVEN; @17 POLOS; @18 ; @19 ; @20 05-01-2025; |  |  | f |  |  | 2025
7838778 | TIG-250106-00033 | KT2501050611 | 2501050611 | 15 | 299 | YARD | KT_001_LST_10919_58 | WOOL PEACH 58 |  | A | DYE | WOOVEN | MASSAL | @11 76; @12 9; @13 ; @14 4.46; @15 ; @16 WOOVEN; @17 POLOS; @18 ; @19 ; @20 05-01-2025; |  |  | f |  |  | 2025
Tabel tr_out_detail
Keterangan
i_docrun | i_docnum | i_barcode | i_brc | i_item | i_qty | e_uom | i_material | e_material | e_plant | e_grade | e_loc | e_jns | e_typ_prod | e_charname | e_buyer | e_kode_order | f_cancel | e_upload_desc | i_docreff | d_year
7852291 | TOG-250430-00008 | LD2504290007 | 2504290007 | 3 | 140 | YARD | LD_713_LST_44618_68 | BESLON 68 |  | A |  | WOOVEN | MASSAL | @11 33; @12 13; @13 ; @14 6.702; @15 ; @16 WOOVEN; @17 POLOS; @18 ; @19 ; @20 28-04-2025; |  |  | f |  |  | 2025
7852291 | TOG-250430-00008 | LD2504300104 | 2504300104 | 4 | 227 | YARD | LD_713_LST_44618_68 | BESLON 68 |  | A |  | WOOVEN | MASSAL | @11 23; @12 13; @13 ; @14 12.770; @15 ; @16 WOOVEN; @17 POLOS; @18 ; @19 ; @20 29-04-2025; |  |  | f |  |  | 2025
7852291 | TOG-250430-00008 | LD2504270249 | 2504270249 | 5 | 67 | YARD | LD_713_LST_44618_68 | BESLON 68 |  | C3 | F-01-01 | WOOVEN | MASSAL | @11 5; @12 19; @13 ; @14 17.715; @15 ; @16 WOOVEN; @17 POLOS; @18 ; @19 ; @20 27-04-2025; |  |  | f |  |  | 2025
7852292 | TOG-250430-00009 | LD2504290019 | 2504290019 | 1 | 228 | YARD | LD_715_LST_44618_68 | BESLON 68 |  | A |  | WOOVEN | MASSAL | @11 22; @12 13; @13 ; @14 12.728; @15 ; @16 WOOVEN; @17 POLOS; @18 ; @19 ; @20 28-04-2025; |  |  | f |  |  | 2025
7852292 | TOG-250430-00009 | LD2504300067 | 2504300067 | 2 | 227 | YARD | LD_715_LST_44618_68 | BESLON 68 |  | A |  | WOOVEN | MASSAL | @11 38; @12 8; @13 ; @14 3.794; @15 ; @16 WOOVEN; @17 POLOS; @18 ; @19 ; @20 29-04-2025; |  |  | f |  |  | 2025
7852292 | TOG-250430-00009 | LD2504300049 | 2504300049 | 3 | 225 | YARD | LD_715_LST_44618_68 | BESLON 68 |  | A |  | WOOVEN | MASSAL | @11 48; @12 8; @13 ; @14 12.778; @15 ; @16 WOOVEN; @17 POLOS; @18 ; @19 ; @20 29-04-2025; |  |  | f |  |  | 2025
Tabel tr_out_head
Keterangan
i_docrun | i_docnum | d_doc | d_posting | e_doc_text | e_create_by | d_create | e_plant | e_ori_plant | e_sloc | e_ori_sloc | e_stock_type | e_ori_stock_type | e_modify_by | d_modify | e_mvt | i_doc_rsv | e_kode_order | i_no_partai | i_buyer | e_buyer | f_cancel | e_upload_desc | i_docreff | d_year
7838226 | TOG-250102-00001 | 2025-01-02 | 2025-01-02 | LCHXO 13 LANG-FEB | gdgr1 | 2025-01-02 09:03 | LWT | LWT | DYE | GREY |  |  |  |  | 311 | 1012733 | LCHXO | 13 |  | WELLFULL | f |  |  | 2025
7838228 | TOG-250102-00002 | 2025-01-02 | 2025-01-02 | LCHXO 14 LANG-FEB | gdgr1 | 2025-01-02 09:08 | LWT | LWT | DYE | GREY |  |  |  |  | 311 | 1012733 | LCHXO | 14 |  | WELLFULL | f |  |  | 2025
7838230 | TOG-250102-00003 | 2025-01-02 | 2025-01-02 | LCHXO 15 LANG-FEB | gdgr1 | 2025-01-02 09:11 | LWT | LWT | DYE | GREY |  |  |  |  | 311 | 1012733 | LCHXO | 15 |  | WELLFULL | f |  |  | 2025
7838231 | TOG-250102-00004 | 2025-01-02 | 2025-01-02 | LCHXO 16 LANG-FEB | gdgr1 | 2025-01-02 09:13 | LWT | LWT | DYE | GREY |  |  |  |  | 311 | 1012733 | LCHXO | 16 |  | WELLFULL | f |  |  | 2025
Note on C90: bram: SELECT SB.e_area, SB.e_type, SB.e_ini_rak, SB.e_alamat, SB.e_kolom_rak, SB.e_kolom_rak::numeric as e_kolom_urut, SB.e_baris_rak, SB.e_baris_rak::numeric as e_baris_urut, COALESCE(sum(ST.i_qty), 0) as qty, COALESCE(count(ST.barcode), 0) as pcs, STRING_AGG(DISTINCT ST.last_doc_in, ', ') AS i_doc FROM tm_storage_bin SB LEFT JOIN f_calc_stock(:p_tanggal, :p_sloc, :p_tahun, null) ST ON SB.e_alamat = ST.e_loc WHERE ST.stock = 0 AND SB.e_ini_rak = :ini_rak AND SB.e_area = :area AND SB.e_type = :tipe GROUP BY SB.e_area, SB.e_type, SB.e_ini_rak, SB.e_alamat, SB.e_kolom_rak, SB.e_kolom_rak, SB.e_baris_rak, SB.e_baris_rak`
Note on A105: bram: Kode Area 1. LJ1 2. LJ2
Note on B105: bram: Tipe Rak : 1.LINE 2.FLOOR 3.MANUAL 4.NITIP 5.IHI 6.MANUAL-BARU 7.
Note on C105: bram: Inisial Rak
Note on D105: bram: Kode Kolom Rak
Note on E105: bram: kode Baris Rak
Note on A142: bram: Kode Barcode
Note on C142: bram: Jenis Kain
Note on E142: bram: Tgl Potong kain
Note on H142: bram: Kode Area
Note on I142: bram: User Create
Note on J142: bram: Kode sloc
Note on K142: bram: Asal sloc (barang masuk darimana ke gudang)
Note on L142: bram: Jenis Produksi
Note on M142: bram: Kategori produksi
Note on N142: bram: No Kartu Proses
Note on O142: bram: Kode Material
Note on P142: bram: Nama Material
Note on Q142: bram: Jenis Kain
Note on R142: bram: Qty Kain
Note on S142: bram: Satuan
Note on T142: bram: Grade Kain
Note on U142: bram: Jenis JL
Note on V142: bram: Nomor Mesin
Note on W142: bram: taun stock
Note on X142: bram: Deskripsi/keterangan
Note on A177: bram: No Kartu Proses
Note on D177: bram: tgl posting
Note on F177: bram: user Created
Note on G177: bram: tgl buat
Note on H177: bram: kode plant
Note on I177: bram: asal plant
Note on J177: bram: kode sloc
Note on K177: bram: Asal sloc (barang masuk darimana ke gudang)
Note on N177: bram: user yg update
Note on O177: bram: tgl update
Note on P177: bram: mvt
Note on Q177: bram: flag cancel f = non cancel t = cancel
Note on T177: bram: tahun
Note on A212: bram: No Kartu Proses
Note on C212: bram: kode barcode
Note on D212: bram: runing number barcode
Note on F212: bram: qty barang
Note on G212: bram: satuan barang
Note on H212: bram: kode material
Note on I212: bram: nama material
Note on J212: bram: kode plant
Note on K212: bram: grade kain
Note on M212: bram: jenis kain
Note on N212: bram: jenis produksi
Note on P212: bram: kode buyer
Note on Q212: bram: kode order
Note on R212: bram: flag cancel f = non cancel t = cancel
Note on U212: bram: tahun
Note on A247: bram: No Kartu Proses
Note on C247: bram: kode barcode
Note on D247: bram: runing number barcode
Note on F247: bram: qty barang
Note on G247: bram: satuan barang
Note on H247: bram: kode material
Note on I247: bram: nama material
Note on J247: bram: kode plant
Note on K247: bram: grade kain
Note on M247: bram: jenis kain
Note on N247: bram: jenis produksi
Note on P247: bram: kode buyer
Note on Q247: bram: kode order
Note on R247: bram: flag cancel f = non cancel t = cancel
Note on U247: bram: tahun
Note on A287: bram: No Kartu Proses
Note on D287: bram: tgl posting
Note on F287: bram: user Created
Note on G287: bram: tgl buat
Note on H287: bram: kode plant
Note on I287: bram: asal plant
Note on J287: bram: kode sloc
Note on K287: bram: Asal sloc (barang masuk darimana ke gudang)
Note on N287: bram: user yg update
Note on O287: bram: tgl update
Note on P287: bram: mvt
Note on Q287: bram: flag cancel f = non cancel t = cancel
Note on T287: bram: tahun

## GUDANG PACKING LEAD TIME (fix)
back
LAPORAN GUDANG PACKING LEAD TIME (SEMUA PERIODE,< 1 BULAN, 1 - 3 BULAN, >3 - 6 BULAN, >6 - 12 BULAN, >1 - 2 TAHUN, >2 TAHUN)
DETAIL BARANG BERDASARKAN JENIS KAIN LEAD TIME
REMARKS
|  | 1. | Tidak ada report standar SAP yang menampilkan informasi per Barcode dikarenakan Barcode berada di level charateristic batch
|  | 2. | Untuk kebutuhan report ini disarankan tetap menggunakan program yang sudah ada dimana untuk sumber datanya memanfaatkan API dari SAP

## LIST KARTON PER KODE ORDER(fix)
back
LIST KARTON PER KODE ORDER (FILTER PENCARIAN DI GUDANG PACKING)
REMARKS
|  | 1. | Tidak ada report standar SAP yang menampilkan informasi per Barcode dikarenakan Barcode berada di level charateristic batch
|  | 2. | Untuk kebutuhan report ini disarankan tetap menggunakan program yang sudah ada dimana untuk sumber datanya memanfaatkan API dari SAP

## MONITORING KAIN GREY
back
REMARKS
| 1. | Tidak ada report standar SAP yang menampilkan informasi per Barcode dikarenakan Barcode berada di level charateristic batch
| 2. | Untuk kebutuhan report ini disarankan tetap menggunakan program yang sudah ada dimana untuk sumber datanya memanfaatkan API dari SAP

## REPORT CANCEL KAIN MASUK
PRO SAP | [12 empty] | back
Tampilan pada SAP bisa mengeluarkan data untuk report dibawah dengan filterisasi data yang sesuai dengan SAP, dan tampilan SAP
Di SAP tampilan report bisa ditampilkan sesuai kebutuhan dengan cara filterisasi
CONS SAP
untuk detail data sampai level grade bisa ditampilkan tetapi di report yang berbeda yaitu report batch
Secara SAP tampilan data tidak bisa sesuai actual yang ada leuwitex dikarenakan untuk bisa sampai detail seperti dibawah harus di custom untuk reportnya
REPORT CANCEL KAIN MASUK
NO | DOC CANCEL | BARCODE | MATERIAL | MATERIAL NAME | GRADE | TANGGAL DOC | NO MESIN | QTY | SATUAN | DESC | DARI SLOC | KE SLOC | DOC DI CANCEL
1 | 7872988 | LD2509200190 | LD_701_INO_12582_58 | MALIKI Z-BLACK 58" | A | 01/10/2025 | 19 | 305 | YARD | SALAH CORAK | ISGREY | GREY | 7872985
2 | 7873910 | JB25100490 | JB_I00_BS_41125_58 | COBRA 58_BS | BS | 09/10/2025 | 6 | 129.5 | YARD | SALAH TANGGAL | ISGREY | GREY | 7873908
3 | 7873910 | JB25100491 | JB_I00_BS_41125_58 | COBRA 58_BS | BS | 09/10/2025 | 6 | 97.5 | YARD | SALAH TANGGAL | ISGREY | GREY | 7873908
4 | 7873912 | JB25100490 | JB_I00_BS_41125_58 | COBRA 58_BS | BS | 09/10/2025 | 6 | 129.5 | YARD | SALAH TANGGAL | ISGREY | GREY | 7873911
5 | 7873912 | JB25100491 | JB_I00_BS_41125_58 | COBRA 58_BS | BS | 09/10/2025 | 6 | 97.5 | YARD | SALAH TANGGAL | ISGREY | GREY | 7873911
6 | 7873952 | JB25092127 | JB_000_BS_41125_58 | BS | BS | 09/10/2025 | 6 | 129.5 | YARD | CANCEL SALAH MATERIAL | ISGREY | GREY | 7873360
7 | 7873952 | JB25092128 | JB_000_BS_41125_58 | BS | BS | 09/10/2025 | 6 | 97.5 | YARD | CANCEL SALAH MATERIAL | ISGREY | GREY | 7873360
8 | 7874350 | LD2510110014 | LD_716_LST_48387_58 | MALIKI STRETCH 58 | A | 13/10/2025 | 20 | 281 | YARD |  | ISGREY | GREY | 7874341
9 | 7874350 | LD2510110242 | LD_716_LST_48387_58 | MALIKI STRETCH 58 | A | 13/10/2025 | 13 | 281 | YARD |  | ISGREY | GREY | 7874341
10 | 7874350 | LD2510110326 | LD_716_LST_48387_58 | MALIKI STRETCH 58 | B | 13/10/2025 | 19 | 282 | YARD |  | ISGREY | GREY | 7874341
11 | 7874350 | LD2510110336 | LD_716_LST_28138_58 | BARBEI 58 | A | 13/10/2025 | 19 | 280 | YARD |  | ISGREY | GREY | 7874341
12 | 7874350 | LD2510110344 | LD_716_LST_48387_58 | MALIKI STRETCH 58 | A | 13/10/2025 | 19 | 275 | YARD |  | ISGREY | GREY | 7874341
13 | 7874350 | LD2510120030 | LD_716_LST_48387_58 | MALIKI STRETCH 58 | A | 13/10/2025 | 16 | 105 | YARD |  | ISGREY | GREY | 7874341
14 | 7874350 | LD2510120031 | LD_716_LST_48387_58 | MALIKI STRETCH 58 | B | 13/10/2025 | 16 | 161 | YARD |  | ISGREY | GREY | 7874341
15 | 7874350 | LD2510120137 | LD_716_LST_48387_58 | MALIKI STRETCH 58 | A | 13/10/2025 | 20 | 275 | YARD |  | ISGREY | GREY | 7874341
16 | 7874350 | LD2510120144 | LD_716_LST_48387_58 | MALIKI STRETCH 58 | A | 13/10/2025 | 20 | 281 | YARD |  | ISGREY | GREY | 7874341
17 | 7874350 | LD2510120177 | LD_716_LST_48387_58 | MALIKI STRETCH 58 | A | 13/10/2025 | 20 | 274 | YARD |  | ISGREY | GREY | 7874341
18 | 7874350 | LD2510120211 | LD_716_LST_48387_58 | MALIKI STRETCH 58 | A | 13/10/2025 | 20 | 281 | YARD |  | ISGREY | GREY | 7874341
19 | 7874350 | LD2510120228 | LD_716_LST_48387_58 | MALIKI STRETCH 58 | C3 | 13/10/2025 | 20 | 274 | YARD |  | ISGREY | GREY | 7874341
20 | 7874350 | LD2510120238 | LD_716_LST_48387_58 | MALIKI STRETCH 58 | C3 | 13/10/2025 | 20 | 281 | YARD |  | ISGREY | GREY | 7874341
21 | 7874508 | LD2510140142 | LD_100_LST_12385_58 | MALIKI STRETCH 58 | A | 14/10/2025 | 05 | 285 | YARD |  | ISGREY | GREY | 7874497
22 | 7874508 | LD2510140203 | LD_100_LST_12385_58 | MALIKI STRETCH 58 | C3 | 14/10/2025 | 16 | 281 | YARD |  | ISGREY | GREY | 7874497
23 | 7874512 | LD2510140142 | LD_100_LST_12385_58 | MALIKI STRETCH 58 | A | 14/10/2025 | 05 | 285 | YARD | SALAH SCAN | ISGREY | GREY | 7874511
24 | 7875099 | LD2510190145 | LD_717_LST_48387_58 | NEW MALIKI STRETCH 58 | A | 19/10/2025 | 20 | 280 | YARD | SALAH SCAN | ISGREY | GREY | 7875083